## Component 4
Monitoring and Evaluation Report for Quarter Ending December 2014
Component 4 | [8 empty] | Score | Rating Code
Common Activities Management and Communications | [8 empty] | 5 | HS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements | Score | Rating Code
NA | NA | NA | NA |  |  | A 4.1 | Recruitment of a service provider to develop the Monitoring and evaluation System | Activity A 4.1 Completed Service Provider in place since June 2014 and M&E Progress Reporting shifted to Result Area 2 A 2.1.1 | 5 | HS
[6 empty] | A 4.2 | Design and Imnplementation of a PSDP Communication and Visibilituy Plan | Communication and visibility plan approved; PSDP News letter launched; 4 press releaseds of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced | 5 | HS
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | A 4.1 Recruitment of a service provider for Development of M&E System |  |  | 5 | Service Provider recruited by May 2014 and is on the job since then
2 | A 4.2 Implementation Agency for Communications Plan |  |  | 5 | Service Provider recruited by May 2014 and is on the job since then
3 | . |  |  | . | .
4 | . |  |  | . | .