## Overall Summary
Monitoring and Evaluation Report (Summary) : December 2014
Overall Summary
Result Area / Component | [5 empty] | Rating | Rating Code | Remarks on Significant Achievements
RESULT AREA 1: CAPACITY AND COMPETITIVENESS OF SMME’S AND COMMUNITY BASED ORGANISATION (CBOS) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [5 empty] | 2.66 | MS | • 70 SMMEs Audited Training and Capacity building yet to start in 2015. • Report and Action Plans for Beef Value chain completed and Public Private Dialogue conducted, Work in progress in 2 other structured value chains, • 5 Emerging value chains and Morula and Honey Opportunity studies in progress. Final reports expected in early 2015.
RESULT AREA 2: SERVICE DELIVERY OF TARGETED INTERMEDIARY ORGANISATIONS (IOs) AND BUSINESS DEVELOPMENT SERVICE PROVIDERS (BDSP) IS ENHANCED | [5 empty] | 3 | MS | • BOCCIM Action Plan as an apex Body elaborated; • Monitoring and Evaluation System Portal has gone live, pending training of staff and transfer of Portal to BOCCIM server; • Other capacity building actions have not yet started and some are in progress.
RESULT AREA 3: BUSINESS ENVIRONMENT FOR ENTERPRISES IS IMPROVED (REDUCTION OF RED TAPE AND PILOT ON IMPROVED ACCESS TO FINANCE BY SMMEs) | [5 empty] | 3.25 | S | • Trade Facilitation Advisory Group and NTCPN needs assesment developed; • Micro Finance Policy Framework developed and submitted to MTI and MFDP; • MTI supported on Monitoring and Evaluation.
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY | [5 empty] | 5 | HS | • Service Provider to develop and maintain M&E System and Portal recruited and in place since June 2014 • Communication and visibility plan approved; PSDP News letter launched; 4 press releaseds of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced
4 <HS< =5 | HS | 3 <S< =4 | S | 2<MS<=3 | 2 <MS< =3 | MS | 1 <MU< =2 | MU | 0 <U< =1 | U | HU =0 | HU
Justification for Result Areas Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Result Area Awarded HS ou HU |  |  | Rating |  | Justification for Extreme score
1 | Component 4 |  |  | 5 |  | The two service providers for M&E system and Communications are in place and delivering as expected. Their presence is felt and seen by a number of stakeholders
2 | . |  |  | . |  | .
3 | . |  |  | . |  | .
4 | . |  |  | . |  | .