## Result Area 1 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 1: Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors
Activity No. | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Status / Achievements | Score |  | RATING | Reporting Responsibility and Method
1.1.1 | Structured value chains analysis and preparation of capacity building action plans | Previous studies and proposals | Three value chains identified that show potential to be strengthened in a published study | M & E Output Verification http://www.webtestopq.co.bw/documents/3QUtDc.pdf | 2014-08-18 | 2015-02-28 | Projects on Beef Completed, Horticulture and tourism in progress | 4 | SATISFACTORY | S | BOCCIM Staff – direct system update
1.1.2 | Emerging value chains analysis and preparation of capacity building action plans | No action plan exists | Five value chains in eight sub-sector capacity building actions plans to support SMMEs and IOs are developed and validated by February 2015 | PSDP M&E Report; Analysis and Development Study report and SMMEs Audit reports | 2014-07-30 | 2015-02-28 | Projects on Dairy, Leather, Piggery, Poultry and Goats in progress | 3 | MODERATELY SATISFACTORY | MS | BOCCIM Staff – direct system update
1.2.1 | Development of action plans for honey and morula CBOs and SMMEs | No opportunity study exists | Honey and Morula Action Plan opportunity studies conducted and action plans for honey and morula in place by September 2014 | PSDP M&E Reports; Contracts Awarded and Reports Tracking the Contract; Action plans Completed | 2014-06-16 | 2014-09-30 | Study started and in progress | 2 | MODERATELY UNSATISFACTORY | MU | BOCCIM Staff – direct system update
1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | No PSDP audit and need assessment | 100 SMME’s are audited | PSDP M&E Reports; SMME diagnostic report | 2014-07-14 | 2014-11-07 | Audit of 70 SMMEs out of 100 complete | 5 | HIGHLY SATISFACTORY | HS | BOCCIM Staff – direct system update
1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, public works including energy efficiency | No PSDP tailored capacity training done | 70 SMMe's and 30 Micro enterprises as well as CBOs are audited and an Action Plan for Capacity Building developed and implemented by Dec 2015 ; 10 SMMEs are implementing environmental protection plans | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2015-01-05 | 2015-12-30 | The activity has not started as it is planned for Jan 2015, hence the number of SMME’S & CBO’s to be trained is yet to be determined. | NA | NA | NA | BOCCIM Staff – direct system update
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | . | . | .