## Result Area 1
Result Area Activity Monitoring Report (Summary) : December 2014
RESULT AREA 1: | [8 empty] | Score | Rating Code
CAPACITY AND COMPETITIVENESS OF SMMEs AND COMMUNITY BASED ORGANISATION (CBO'S) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [8 empty] | 2.66 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements | Score | Rating Code
IND 1.1 | 3.5 | S | Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans | Projects on Beef Completed, Horticulture and tourism in progress | 4 | S
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans | Projects on Dairy, Leather, Piggery, Poultry and Goats in progress | 3 | MS
IND 1.2 | 2 | MU | Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014. |  |  | A 1.2 | Value Added wild / Natural Product Opportunity Study
[6 empty] | A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs | Study started and in progress | 2 | MU
IND 1.3 | 2.5 | MS | At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015. |  |  | A 1.3 | SME's Diagnostics (Baseline studies)
[6 empty] | A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | Auditof 70 SMME's out of 100 complete | 5 | HS
[6 empty] | A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | Activity yet to start | NA | NA
IND 1.4 | NA | NA | At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015
IND 1.5 | NA | NA | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015.
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | A 1.3.1 Diagnostics for 70 SMMe's |  |  | 5 | The task was successfully completed in time
2 | . |  |  | . | .
3 | . |  |  | . | .
4 | . |  |  | . | .