## Result Area 2 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 2: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Activity No. | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Status / Achievements | Score | RATING CODE | RATING | Reporting Responsibility
2.1.1 | Internal Monitoring and Evaluation of PSDP | Web based M&E system is not available | Web based M&E system is fully operational | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | Monitoring and Evaluation Portal is operational to be followed by training | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | Review of Mandates not taken place | BOCCIM established as Apex Body for Private Sector in Botswana | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | BOCCIM action plan as an apex body elaborated | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
2.1.3 | BOCCIM capacity building to render better services to its members | No Membership satisfaction survey carried out | BOCCIM Membership increases by 10% by December 2015 | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | In Progress | 2 | MODERATELY UNSATISFACTORY | MU | CDE / BOCCIM Staff – direct system update;
2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | DNA | DNA | PSDP M&E Reports; | DNA | 2015-12-01 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.1.4 | Assistance to the establishment of market intelligence information system/web based platform | No MIIS | An operational MIIS | PSDP M&E Reports; Hits on website | 2014-10-01 | 2015-06-30 | In progress (One visit by Consultant) | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
2.2.1 | Assistance to BITC in Export Development and Promotion | No Export Strategy is in place at BITC. The PSDP identified SMMES are not exporting. | One export strategy implemented, 3 partnerships are established with external trading partners outside Botswana’s borders. Ten SMMEs are export ready. | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Only three training programmes done | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Only Beef PPD is done | 2 | MODERATELY UNSATISFACTORY | MU | CDE / BOCCIM Staff – direct system update;
2.3.3 | Assistance to the tourism sector in partnership with BTO and HATAB | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.3.4 | Assistance to honey sector associations | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.4.1 | Support the development of a National Quality Policy | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.4.3 | Support the process of certification for SMEs | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | . | . | .