## Result Area 2
Result Area Activity Monitoring Report (Summary) : December 2014
RESULT AREA 2: | [8 empty] | Score | Rating Code
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced. | [8 empty] | 2.9 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements | Score | Rating Code
IND 2.1 | 3.33 | S | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 10% by December 2015. • PSDP Web based M&E system is operational by December 2014. |  |  | A 2.1 | Capiciyty Building of BOCCIM
[6 empty] | A 2.1.1 | Internal Monitoring and Evaluation of PSDP | Monitoring and Evaluation Portal is operational to be followed by training | 4 | S
[6 empty] | A 2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | BOCCIM action plan as an apex body elaborated | 4 | S
[6 empty] | A 2.1.3 | BOCCIM capacity building to render better services to its members | In Progress | 2 | MU
[6 empty] | A 2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | Not Started | NA | NA
IND 2.2 | 3 | MS | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs - June 2015. |  |  | A 2.1.4 | Assistance to the establishment of market intelligence information system/web based platform for networking and information / Public and private dialogue, etc… | In Progress | 3 | MS
Ind 2.3 | NA | NA | Capacity building of BITC is conducted • An export strategy with respective action plan is adopted and implementation of the action plan starts in December 2015. • Three partnerships are established with external trading partners by December 2015. • At least 10 of the PSDP targeted SMMEs are qualified for export by BITC by December 2015. |  |  | A 2.2 | Capacity Building of BITC
[6 empty] | A 2.2.1 | Assistance to BITC in Export Development and Promotion | Not Started | NA | NA
[6 empty] | A 2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | Not Started | NA | NA
Ind 2.4 | 2.5 | MS | Capacity building of Intermediary Organisations and sector associations is conducted. • Number of private firms using TSIs and BDSPs services increased by 10% by December 2015. • At least 70% of SMMEs and CBOs benefiting from PSDP intervention are satisfied with the quality of service provided by IOs and BDSPs. • Recommendations developed and submitted to MTI by December 2015 for improving competitiveness and export of Botswana Beef. • At least three new products and/or services introduced by IOs by December 2015. |  |  | A 2.3 | Capacity Building of Intermediart Organisations and Sector Associations
[6 empty] | A 2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) | Only three training programmes done | 3 | MS
[6 empty] | A 2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | Only Beef PPD is done | 2 | MU
[6 empty] | A 2.3 3 | Assistance to the tourism sector in partnership with BTO and HATAB | Not Started | NA | NA
[6 empty] | A 2.3.4 | Assistance to honey sector associations | Not Started | NA | NA
IND 2.5 | NA | NA | Capacity building conducted for BOBS on Quality Certification • Draft National Quality Policy is developed and submitted to MTI by June 2015. • BOBS staff members are trained in audit and inspection services and ten service providers are capacitated in auditing and certification of agro-industry (horticulture, diary, beef) and manufacturing by December 2015. • SMME certification system is in place by September 2015. |  |  | A 2.4 | Capacity Building for BOBS on Quality and Certification
[6 empty] | A 2.4.1 | Support the development of a National Quality Policy | Not Started | NA | NA
[6 empty] | A 2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | Not Started | NA | NA
[6 empty] | A 2.4.3 | Support the process of certification for SMEs | Not Started | NA | NA
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | . |  |  | . | .
2 | . |  |  | . | .
3 | . |  |  | . | .
4 | . |  |  | . | .