## Result Area 3 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 3: Business Environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Activity No. | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Status / Achievements | Score | RATING CODE | RATING | Reporting Responsibility
3.1.1 | Establish trade facilitation group and provide capacity building | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Trade Facilitation Advisory Group and NTCPN needs assesment developed | 4 | Satisfactory | S | CDE / BOCCIM Staff – direct system update;
3.1.2 | Training of TFAG and NTCPN on negotiation and trade facilitation | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
3.1.3 | Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
3.2.1 | Draft a microfinance policy framework | No Policy | DNA | Activity Progress Reports | DNA | DNA | Draft Microfinance Policy Developed and submitted to MTI and MFDP | 5 | Highly Satisfactory | HS | CDE / BOCCIM Staff – direct system update;
3.2.2 | Draft a micro-finance Act for Botswana | No Act | DNA | Activity Progress Reports | DNA | Dec 154 | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
3.3.1 | Review the registration process and tax compliance | No Review | DNA | Activity Progress Reports | DNA | 2015-12-30 | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
3.3.2 | Review of labour laws and recommend labour productivity improvement strategies | DNA | DNA | Activity Progress Reports | DNA | 2015-12-30 | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | . | . | .