## Progressive
Performance of each Log Frame Indicator Progressive Quarter Wise (Summary) December 2014 with Interin Report for 28th February 2015
Result Area One :Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 1.1 | Action plans to support SMMEs and IOs are developed foe eight valuchains and eight sub sectors by February 2015 | NA | S | S | . | . | . | . | . | .
Ind 1.2 | Studies are carried out for development of Honey and Morula Value Chains by September 2014. | HU | MU | MS | . | . | . | . | . | .
Ind 1.3 | At least 70 SMMEs are strengthened on management, operations by December 2015. | MS | MS | MU | . | . | . | . | . | Some activities that are now due to start have not done so well hence the grading has gone down
Ind 1.4 | 30 CBO’s are trained on management, marketing, quality standards and accounting by December 2015 | NA | NA | HU | . | . | . | . | . | Some activities that are now due to start have not done so well hence the grading has gone down In This case A 1.4.1 which contributes partly to this Log Frame Indicator has fallen to 0 from NA
Ind 1.5 | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. | NA | NA | HU | . | . | . | . | . | same as above
Result Area Two: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 2.1 | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana and M&E is Operational by December 2014 | MU | S | S | . | . | . | . | . | .
Ind 2.2 | A web based market intelligence information system is developed for use by SMMEs - June 2015. | U | MS | MS | . | . | . | . | . | .
Ind 2.3 | Capacity building of BITC is conducted by December 2015 | NA | NA | U | . | . | . | . | . | Activity A 2.2.1 and A 2.2.2 should have started by now but have not so well and they fell from NA to 1 and this caused Log Frame Indicator 2.3 to fall from NA to 1
Ind 2.4 | Capacity building of CBO's and IO's is conducted by December 2015 | NA | MS | MS | . | . | . | . |  | .
Ind 2.5 | Capacity building of BOBS is conducted by December 2015 | NA | NA | NA | . | . | . | . | . | .
Result Area Three: Business environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 3.1 | Capacity building conducted on trade and specific negotiation skills | NA | S | S | . | . | . | . | . | .
Ind 3.2 | Improved Policy Framework to access finance | NA | HS | MS | . | . | . | . | . | This Log frame indicator has two contributors A 3.2.1 and A 3.2.2 where as the first is over the second is now due and has not moved as planned thus this was downgraded to 0 Hence the fall in the Rating for Ind 3.2
Ind 3.3 | Improved Business Environment (Ease of Doing Business) | NA | NA | MS | . | . | . | . | . | The contributors to this log frame Indicator are A 3.3.1 and are now due to start and are at MS level hence this fall in rating
Component Four: Management and Communications
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
NOTA | Performance Management and Communications | MS | HS | HS | . | . | . | . | . | .
|  |  | . | . | . | . | . | . | . | .
NOTA | Not Applicable | . | . | . | . | . | . | . | NA | Not Due to Start
HS | 4< HS <=5 | S | 3< S <=4 |  |  | MS | 2< MS <=3 |  | MU | 1< MU <=2
U | 0< U <=1 | HU | HU =0 |  |  | . | . | . | . | .