## Result Area 1(D)
Monitoring and Evaluation Interim Report for the period 1st January 2015 to 28 Feb 2015
Result Area 1: Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors
Contributing Activity Number | Description of Activity | BASELINE | TARGET | OUTPUT / SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievements |  |  |  |  | Score | Rating Code | Rating | Reporting Responsibility and Method
A 1.1 | Value Chains Analysis and Development
A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Previous studies and proposals | Three value chains identified that show potential to be strengthened in a published study | M & E Output Verification http://www.webtestopq.co.bw/documents/3QUtDc.pdf | 2018-08-19 | 2019-03-01 | Projects on Beef Completed, Three action items are being implemented. (1) Management for Commercial Farmers (2) Upgrading capacity of Farmers Association. (3) Technical Tools of graduating communal Farmers. Horticulture and tourism in progress. No report submitted yet |  |  |  |  | 4 | Satisfactory | S | BOCCIM Staff – direct system update
A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | No action plan exists | Five value chains in eight sub-sector capacity building actions plans to support SMMEs and IOs are developed and validated by February 2015 | PSDP M&E Report; Analysis and Development Study report and SMMEs Audit reports | 2018-07-31 | 2019-03-01 | Final report submitted for review by CDE but still pending since 02 February 2015, contract extended to 28th February 2015. |  |  |  |  | 3 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
A 1.2 | Value Added wild / Natural Product Opportunity Study
A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | No opportunity study exists | Honey and Morula Action Plan opportunity studies conducted and action plans for honey and morula in place by September 2014 | PSDP M&E Reports; Contracts Awarded and Reports Tracking the Contract; Action plans Completed | 2018-06-17 | 2018-10-01 | Action plan for Honey Submitted and Morula being finalised, contract extended till 28 February 2015. |  |  |  |  | 3 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
A 1.3 | SME's Diagnostics (Baseline studies)
A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | No PSDP audit and need assessment | 100 SMME’s are audited | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2018-07-15 | 2018-11-08 | Team for the Diagnosis of SMMEs (BWP 1414/01) |  | Team Leader preparing final report not yet complete |  |  | 5 | Highly Satisfactory | HS | BOCCIM Staff – direct system update
[7 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Local Consultants completed 22 SMMEs out of a total of ____SMME's
[7 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | BNPC completed 28 out of __ SMMEs
[7 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | BIH Completed 14 out of 15 SMME's
[7 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | LEA completed 9 SMME's including 2 CBO's
[7 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | CEDA to Complrte 10 SMME's by 31st January 2015
[7 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Capacity Building of local staff on SMMe Diagnostics File Completed and closed
[7 empty] | PSDP Mission Logistics (BWP/1404/01 |  | No Data
[7 empty] | SMME Diagnostics for Micros (File Number Requested) |  | Yet to start
A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | No PSDP tailored capacity training done | 70 SMMe's and 30 Micro enterprises as well as CBOs are audited and an Action Plan for Capacity Building developed and implemented by Dec 2015 ; 10 SMMEs are implementing environmental protection plans | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2019-01-06 | 2019-12-31 | Support to poultry sector (BWP 1444/01) |  | (1)funds committed and contract to be signed by 30 January 2015 (2)Consultant first mission begins 2 February 2015 |  |  | 0 | Highly Unsatisfactory | HU | BOCCIM Staff – direct system update
[7 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | file at commitment level- commitment of funds by 20th February 2015
[7 empty] | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | file at commitment level- commitment of funds by 20th February 2015
[7 empty] | SMEs trade missions-Result Area1 (BWP 1313/01) |  | Three SMEs from the Diary sector participated at the 9th African Diary Conference and Exhibition held in Harare, Zimbabwe from the 24 to 26 September, 2013.
[7 empty] | Group training in management Finance (BWP 1446/01) |  | TOR and budget finalized. Follow up PA
[7 empty] | Management training for Micros and CBOs |  | selection of service provider done. Follow up Commitment
[7 empty] | Group training in Business Planning for SMEs |  | TOR and budget finalized. Follow up PA
[7 empty] | Participation of SMMEs to trade missions & trainings |  | TOR and budget to be prepared. Request file number
[7 empty] | Individual Coaching of SMMEs |  | Activity under preparation. Request file number
[7 empty] | SME Development Experts |  | Activity under preparation. Request file number
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | . | . | .