## Result Area 1
Result Area Activity Monitoring Report (Summary) : 28th February 2015
RESULT AREA 1: | [12 empty] | Score | Rating Code
CAPACITY AND COMPETITIVENESS OF SMMEs AND COMMUNITY BASED ORGANISATION (CBO'S) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [12 empty] | 1.6 | MU
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | Score | Rating Code
IND 1.1 | 3.5 | S | Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Projects on Beef Completed, Three action items are being implemented. (1) Management for Commercial Farmers (2) Upgrading capacity of Farmers Association. (3) Technical Tools of graduating communal Farmers. Horticulture and tourism in progress. No report submitted yet |  |  |  |  | 4 | S
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | Final report submitted for review by CDE but still pending since 02 February 2015, contract extended to 28th February 2015. |  |  |  |  | 3 | MS
IND 1.2 | 3 | MS | Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014. |  |  | A 1.2 | Value Added wild / Natural Product Opportunity Study
[6 empty] | A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | Action plan for Honey Submitted and Morula being finalised, contract extended till 28 February 2015. |  |  |  |  | 3 | MS
IND 1.3 | 2.5 | MU | At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015. |  |  | A 1.3 | SME's Diagnostics (Baseline studies)
[6 empty] | A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | Team for the Diagnosis of SMMEs (BWP 1414/01) |  | Team Leader preparing final report not yet complete |  |  | 5 | HS
[8 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Local Consultants completed 22 SMMEs out of a total of ____SMME's
[8 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | BNPC completed 28 out of __ SMMEs
[8 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | BIH Completed 14 out of 15 SMME's
[8 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | LEA completed 9 SMME's including 2 CBO's
[8 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | CEDA to Complrte 10 SMME's by 31st January 2015
[8 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Capacity Building of local staff on SMMe Diagnostics File Completed and closed
[8 empty] | PSDP Mission Logistics (BWP/1404/01 |  | No Data
[8 empty] | SMME Diagnostics for Micros (File Number Requested) |  | Yet to start
[6 empty] | A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | Support to poultry sector (BWP 1444/01) |  | (1)funds committed and contract to be signed by 30 January 2015 (2)Consultant first mission begins 2 February 2015 |  |  | 0 | HU
[8 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | file at commitment level- commitment of funds by 20th February 2015
IND 1.4 | 0 | HU | At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015 |  |  |  |  | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | file at commitment level- commitment of funds by 20th February 2015
[8 empty] | SMEs trade missions-Result Area1 (BWP 1313/01) |  | Three SMEs from the Diary sector participated at the 9th African Diary Conference and Exhibition held in Harare, Zimbabwe from the 24 to 26 September, 2013.
[8 empty] | Group training in management Finance (BWP 1446/01) |  | TOR and budget finalized. Follow up PA
[8 empty] | Management training for Micros and CBOs |  | selection of service provider done. Follow up Commitment
[8 empty] | Group training in Business Planning for SMEs |  | TOR and budget finalized. Follow up PA
[8 empty] | Participation of SMMEs to trade missions & trainings |  | TOR and budget to be prepared. Request file number
[8 empty] | Individual Coaching of SMMEs |  | Activity under preparation. Request file number
IND 1.5 | 0 | HU | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. |  |  |  |  | SME Development Experts |  | Activity under preparation. Request file number
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | A 1.3.1 Diagnostics for 70 SMMe's |  |  | 5 | The task was successfully completed in time
2 | . |  |  | . | .
3 | . |  |  | . | .
4 | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt abd Suggestions for way forward
1 | A 1.1.1 Structured value chains analysis and preparation of capacity building Action plans |  |  | 4 | Though the contract ends in August 2015 as shown in the weekly report The contract stipulates that all deliverables must be complete two months before that date or in June 2015. Further no progress is reported after 31st December 2014 if this continues the rating may need to be down graded
2 | A1.1.2 Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) |  |  | 3 | The contract has been extended to 28th Feb 2015 (The report does not specify if the MC has been taken in confidence or approval of the competent authourity has been taken for this extension. Also, as per the weekly report the consultant has submitted the final report before the 2nd February weekly meeting; yet as per subsequent reports the report is pending review by CDE till the date of this report.
3 | A1.2.1 Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) |  |  | 3 | As per the completion dates in the weekly report the second part of this activity (Morula Study and Action Report) will becone due on 1st March; consequently the rating will fall.
4 | A 1.3.1 Diagnostics of SMMEs (BNPC, BIH, Local consultants) |  |  | 3 | This subactivity had been graded HS in the last report as on 31st December 2014 the number of SMME audits completed were more than 70 out of 100 when 70 was the target. The progress during 1st January 2015 to 28 February 2015 has been below expectations and major tasks like the team leaders report and outstanding Audits have not neen completed
5 | A 1.4.1 Capacity Building of SMME's and CBO's for upgrading their Competiveness |  |  | 0 | As of 28th Feb all these sub activities should have started but the latest weekly report indicated no progress or action in hand. The pending actions need to be done and if necessary approval of the compitent authourity needs to be taken and completion dates revised