## Result Area 2 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 2: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Contributing Activity Number | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievement |  | Score | RATING CODE | RATING | Reporting Responsibility
A 2.1 | Capacity Building of BOCCIM
A 2.1.1 | Internal Monitoring and Evaluation of PSDP | Web based M&E system is not available | Web based M&E system is fully operational | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | final report submitted and training schedule for 3rd to 5th March 2015 |  | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
A 2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | Review of Mandates not taken place | BOCCIM established as Apex Body for Private Sector in Botswana | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | Review of the mandates and establish BOCCIM as an Apex body (BOT/1402/01) | The final report ith recommendations to establish BOCCIM as an apex body has been submitted. | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
[7 empty] | review of BOCCIM Constitution (BWP/140/01) | Reports of the work done reieved for uploading by M&E team but Progress not given in weekly report
[7 empty] | BOCCIM Membership model (BWP/1402/01) | Reports of the work done reieved for uploading by M&E team but Progress not given in weekly report
[7 empty] | Consultative Workshop for BOCCIM (BWP/1416/01) | Reports of the work done reieved for uploading by M&E team but Progress not given in weekly report
[7 empty] | BOCCIM NBC (BWP /1438/01) | Reports of the work done reieved for uploading by M&E team but Progress not given in weekly report
A 2.1.3 | BOCCIM capacity building to render better services to its members | No Membership satisfaction survey carried out | BOCCIM Membership increases by 10% by December 2015 | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | Inception Report Submitted |  | 2 | MODERATELY UNSATISFACTORY | MU | CDE / BOCCIM Staff – direct system update;
A 2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | DNA | DNA | PSDP M&E Reports; | DNA | 2015-12-01 | TOR and Budget and budget to be prepared and start by March 2015 |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
A 2.1.4 | Assistance to the establishment of market intelligence information system/web based platform | No MIIS | An operational MIIS | PSDP M&E Reports; Hits on website | 2014-10-01 | 2015-06-30 | Benchmarking Boccim Web Portal (BWP/1434/01) | Mission for the market intelligence completed in November 2014 | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
[7 empty] | Feasibility study for the market intelligence being done under Value chain analysis for beef, tourism, and horticulture sectors | Web based platform for networking and information dissemination will be established under Result Area 2. The First mission was undertaken in december 2014. Mission report has been submitted and approved
[7 empty] | Assistance to the establishment of market intelligence information | TOR and Budget to be prepared
A 2.2 | Capacity Building of BITC
A 2.2.1 | Assistance to BITC in Export Development and Promotion | No Export Strategy is in place at BITC. The PSDP identified SMMES are not exporting. | One export strategy implemented, 3 partnerships are established with external trading partners outside Botswana’s borders. Ten SMMEs are export ready. | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2015-01-05 | 2015-12-30 | Assistance to BITC in Export Development and Promotion – contract signed, first mission for the consultant starts on the 13 February 2015. |  | 1 |  | U | CDE / BOCCIM Staff – direct system update;
A 2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2015-01-05 | 2015-12-30 | Participation of Ios to trade missions & trainings - (BWP/1307/01) | WTO International Trade & Development course, Geneva, Switzerland. Completed | 1 | UNSATISFACTORY | U | CDE / BOCCIM Staff – direct system update;
[7 empty] | participation of Ios to trade missions & trainings - (BWP/1307/01) | support for training on Exports and Investment Promotion Programme –report submitted, Dublin Ireland.
[7 empty] | BITC sector association experts - (BWP/1503/01) | contract signed and deskwork has started.
A 2.3 | Capacity Building of Intermediary Organisations and Sector Associations
A 2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | 62 local staff from Intermediary Organisation were trained- the activity has been completed and closed. |  | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
A 2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | PPD Meeting on Beef Value Chain (BWP/1428/01) | Succesfully Completed | 2 | MODERATELY UNSATISFACTORY | MU | CDE / BOCCIM Staff – direct system update;
[7 empty] | Management Tools for Commercial farmers (BWP/1508/01) | PA preparation.
[7 empty] | Technical Tools for Graduating communal farmers (BWP/1510/01) | PA preparation.
[7 empty] | upgrading Capacity of farmers Associations (BWP/1511/01) | PA preparation.
2.3.3 | Assistance to the tourism sector in partnership with BTO and HATAB | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Assistance to the tourism sector in partnership with BTO and HATAB | TOR and Budget to be prepared. to start in March 2015 | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
[7 empty] | HATAB Tourism Conference(BWP/1443/01) | Activity to take place in April 2015.
A 2.3.4 | Assistance to honey sector associations | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | TOR and Budget to be prepared to start April 2015. |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
A 2.4 | Capacity Building for BOBS on Quality and Certification
A 2.4.1 | Support the development of a National Quality Policy | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
A 2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
.
A 2.4.3 | Support the process of certification for SMEs | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 |  | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . |  | . | . | . | . | .