## Result Area 3
Result Area Activity Monitoring Report (Summary) : December 2014
RESULT AREA 3: | [6 empty] | Score | Rating Code
Business environment (reduction of red tape and pilot on accessing finance) for enterprises is enhanced. | [6 empty] | 3.25 | S
Log Frame Indicator Number | Score | Rating Code | Description of Indicator | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements | Score | Rating Code
IND 3.1 | 4 | S | Capacity building conducted on trade and specific negotiation skills • Recommendations submitted by PSDP to MTI on the reduction of; the cost of doing business; and the cost and time required for registration and operationalization of SMMEs in Botswana by June 2015. • Members of the Trade Facilitation and Advisory Group (TFAG) and National Committee on Trade Policy and Negotiations (NCTPN) are trained on MTI Trade Capacity Building Strategy by June 2015. • At least 10 IO staff members are trained in EPA implementation by September 2015 | A 3.1 | Capacity Building on Trade and Specific Negotiation Skills
|  |  |  | A 3.1.1 | Establish trade facilitation group and provide capacity building | Trade Facilitation Advisory Group and NTCPN needs assesment Developed | 4 | S
|  |  |  | A 3.1.2 | Training of TFAG and NTCPN on negotiation and trade facilitation | Yet to start | NA | NA
|  |  |  | A 3.1.3 | Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation | Yet to start | NA | NA
IND 3.2 | 2.5 | MS | Improved Policy Framework to access finance • At least 1 new financial product (post loan support mechanism) targeting SMMEs is introduced by commercial banks and or other financial institutions supporting SMME financing by December 2015 • 30 SMME’s under PSDP are assisted to prepare their business plans for submission to commercial banks and other financial institutions by December 2015. • At least 5 PSDP SMMEs assisted are accessing finance by February 2016. • Micro finance policy framework is established and presented to Government for adoption by September 2014. • A microfinance Act is drafted and submitted to government by September 2014. | A 3.2 | Policy Framework to Improve Access to Finance
|  |  |  | A 3.2.1 | Draft a microfinance policy framework | Draft Microfinance Policy Developed and submitted to MTI and MFDP | 5 | HS
|  |  |  | A 3.2.2 | Draft a micro-finance Act for Botswana | Yet to start | NA | NA
IND 3.3 | NA | NA | Improved Business Environment (Ease of Doing Business) • A compilation of recommendations submitted to MTI by December 2015 to simplify tax registration with a view to improve tax compliance by SMMEs. • A compilation of labour laws affecting SMMEs with recommendations for reforms submitted to MTI by December 2015. | A 3.3 | Improving Business Environment (Ease of Doing Business)
|  |  |  | A 3.3.1 | Review the registration process and tax compliance | Yet to start | NA | NA
|  |  |  | A 3.3.2 | Review of labour laws and recommend labour productivity improvement strategies | Yet to start | NA | NA