## Overall Summary
Monitoring and Evaluation Report (Summary) : 1st April to 30 June
Result Area / Component |  |  | Rating | Rating Code | Remarks on Significant Achievements
RESULT AREA 1: CAPACITY AND COMPETITIVENESS OF SMME’S AND COMMUNITY BASED ORGANISATION (CBOS) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS |  |  | 3 | MS | There has been quite an overall improvement from the last quarter particularly in activity A1.4. There are however a number of alerts which must be attended to in order to prevent the rating from being affected negatively.
RESULT AREA 2: SERVICE DELIVERY OF TARGETED INTERMEDIARY ORGANISATIONS (IOs) AND BUSINESS DEVELOPMENT SERVICE PROVIDERS (BDSP) IS ENHANCED |  |  | 3 | MS | There has been a slight improvement in this result area as a result of increased scores in A2.3.1 and A2.3.2 and activates commencing under A2.4. Some alerts have been given which would have to be attended to.
RESULT AREA 3: BUSINESS ENVIRONMENT FOR ENTERPRISES IS IMPROVED (REDUCTION OF RED TAPE AND PILOT ON IMPROVED ACCESS TO FINANCE BY SMMEs) |  |  | 4 | S | Very little change from the last report. The indicator is doing quite well and will be monitored closely in going forward.
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY |  |  | 5 | HS | No Change visible as compared to previous report
4< HS <=5 | 3< S <=4 | 2< MS <=3 | 1< MU <=2 |  | 0< U <=1 | HU =0