## Result Area 1
Result Area Activity Monitoring Report (Summary) : 30 June 2015
RESULT AREA 1: | [12 empty] | Sub- Activity Score | Score | Rating Code
CAPACITY AND COMPETITIVENESS OF SMMEs AND COMMUNITY BASED ORGANISATION (CBO'S) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [12 empty] | . | 2.96 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 1.1 | 3 | MS | Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Projects on Beef Completed and the final VC report submitted October 2014. Pursuant to the action plans of the report and the recommendations made, three action items are being implemented. (1) Management tools for Commercial Farmers (2) Upgrading capacity of Farmers Association. (3) Technical Tools of graduating communal Farmers. Horticulture and tourism in progress. The Horticulture report has been received and is now under review (18 June 2015). Tourism VCAD: received and currently under review (26 June 2015). Reports have been distributed to the stakeholders. |  |  |  |  | . | 3 | MS
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | All Five Final reports submitted by the consultant and have been reviewed by CDE as of 25 February 2015. Reformatted final report received by PSDP for comments to the consultants by 5 April 2015. Feedback on new report format submitted to HCL, 10 April 2015. Follow up to be made on final submission of all reports. Comments provided to HCL by 22 April 2015. An organisation for implementing action plans will be identified in October 2015. |  |  |  |  | . | 3 | MS
IND 1.2 | 2 | MU | Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014. |  |  | A 1.2 | Value Added wild / Natural Product Opportunity Study
[6 empty] | A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | Action plan for Honey Submitted and Morula being finalised. Reports received and approved. Final Payment being processed. Honey Technical Guide under evaluation (follow up actions). Secondary actions based on recommendations to be elaborated. Recruitment of Honey Expert to assist SMMEs and CBOs under review. No progress on Morula. Field missions have been completed. Recruitment of Honey Expert to assist SMMEs and CBOs under review. Contract submitted for approval. It is expected that capacity building and implementation of action plans from the report will begin in September 2015. |  |  |  |  | . | 2 | MU
IND 1.3 | 4 | S | At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015. |  |  | A 1.3 | SME's Diagnostics (Baseline studies)
[6 empty] | A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | Team for the Diagnosis of SMMEs (BWP 1414/01) |  | Team leader final report complete and submitted. What remains are administrative actions by the PSDP unit. |  |  | 4 | 4 | S
[8 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Local Consultants completed 22 SMMEs out of a total of ___22_SMME's. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | BNPC completed 28 out of _28 SMMEs. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | BIH Completed 15 out of 15 SMME's. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | LEA completed 9 SMME's including 2 CBO's. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | CEDA Completed 10/10 SMME's by 31st January 2015. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Capacity Building of local staff on SMME Diagnostics File Completed and closed |  |  | 4
[8 empty] | PSDP Mission Logistics (BWP/1404/01 |  | This entailed a provisional budget to cover SMME site visits by the PSDP team. The site visit reports have been completed and made available . This will then be able to trigger an evaluation from the M&E team. |  |  | 4
[8 empty] | SMME Diagnostics for Micros (File Number Requested) |  | These were completed. Interventions have started in which they will be attending workshops and they will also get mentors. |  |  | 4
IND 1.3 Cont.. | 4 Cont.. | S | Cont… |  |  | A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | Support to poultry sector (BWP 1444/01) |  | File de-committed due to the fact that the action was cancelled. No clear explanation as to why this was the case has been forthcoming. However, the poultry companies are being assisted with some attending Occupational Safety and Health Training, Business Management Training and TBT Certification (work in progress). |  |  | . | 2.25 | MS
[8 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | Progress made in that all consultant have begun their missions and the activity is on-going. Arrangements under way for ICT, Bakery and Poultry expert trips, foreseen in June-July Time frame. ICT expert expected 2 July 2015 – 25 July. |  |  | 3
IND 1.4 | 2.25 | MS | At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015 |  |  |  |  | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | Progress made: Consultants have begun their missions and the activity is on-going.. Economarkets to commence local support, following introduction meetings. Contracting on-going for local consultant support. Third expert identified, with possible start-up of October 2015. The first such intervention began in march and a number of similar interventions are on-going. Any evaluation on impact could reasonably be done from September. |  |  | 3
[8 empty] | Group training in management Finance (BWP 1446/01) |  | TOR and budget finalized. Selection and PA to be finalised. It is difficult to measure the extent of the progress in the absence of a definite date for the group training. |  |  | 2
[8 empty] | Management training for Micros and CBOs |  | (1) Selection of service provider done. Follow up on-going. (2) Letters distributed to attendees and follow-up to commence on 27 May 2015. It is difficult to measure the extent of the progress in the absence of a definite date for the group training. |  |  | 2
[8 empty] | Group training in Business Planning for SMEs |  | TOR and budget finalized. Follow up PA. Budget Approved. Contract being drafted for approval and signature. It is difficult to measure the extent of the progress in the absence of a definite date for the group training. |  |  | 2
[8 empty] | Participation of SMMEs to trade missions & trainings. In terms of trade missions and training the file number has still not been obtained since the last report |  | TOR and budget to be prepared. Again, it is difficult to measure the extent of the progress in the absence of a definite date for the group training. |  |  | 2
[8 empty] | Individual Coaching of SMMEs |  | Activity under preparation. Request file number. Financial offer and documentation to be submitted 13th April 2015 for commitment. There is a relationship that has been established with a few organisations that offer expert services. The delays are due to administrative constraints. |  |  | 2
[8 empty] | SME Development Experts |  | Activity under preparation. File number request is on-going |  |  | 2
IND 1.5 | 3.5 | S | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. |  |  | A1.5 | Technical Advisors and short term Experts
[6 empty] | A.1.5.1 |  | Technical advisor in Agro industry (BOT/1401/01) |  | Final report submitted. File closed. This advisor is in relation to A1.1.1 which action is taking place on the recommendations of this report. |  |  | 4 | 3.5 | S
[8 empty] | Service Provider for assistance in construction and public works (BWP1431/01) |  | Inception Report submitted. File number requested, awaiting profile of service provider. Modules for workshop sessions have been approved, workshop completed from 15th June to 19th June 2015. Workshop report and Sunday Standard article under preparation. A training report is expected before the end of July 2015. |  |  | 3.5
[8 empty] | Service Provider for assistance to clean energy companies (BWP/1426/01) |  | Final report was submitted in March 2015and the file has been closed well before the contract date lapsed. The service consisted of three missions: 1) Capacity needs assessment of 8 SMMEs, 2) Plant Assessments and Business Plans, 3) Feedback Meetings and Action Plans. An awareness training workshop was also conducted for 19 enterprises on 5th March 2015. |  |  | 3.5
[8 empty] | Short-term Experts (PSDP support staff) BWP/1305/01, BWP/1407/01, BWP/1311/01, BWP/1442/01 |  | Support to PSDP junior experts and interns. The following files have been closed (BWP/1305/01, BWP/1407/01, BWP/1311/01). The only active file is BWP/1442/01 which is the payment of PSDP experts and Interns. |  |  | 3
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
1 | A1.1.1 Structured value chains analysis and preparation of capacity building Action plans |  |  | 3 | The contract expires in August 2015 and it was expected that this activity should have been completed two months before, which is in June. The activity is thus running behind because action items are still being implemented and reviews for the reports on Horticulture and Tourism VCs still taking place with no deadlines when they would be complete. In the absence of work-plans, projecting targets has presented challenges for the progress of the activity and these should be developed as a matter of priority.
2 | A1.1.2 Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) |  |  | 3 | The internal review of the reports is on going and the dates have been changed from March to August 2015, as a result of the poor quality of the initial report. The project tools that show the extension, end and change of project activities and plans should be shared with the team as a whole so as to allow for their use by all relevant PSDP staff.
3 | A1.2.1 Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) |  |  | 3 | Some progress made, however the indicator score must be downgraded to Moderately Unsatisfactory because the activity was meant to be completed on 28 February but has not been completed yet.
4 | A 1.3.1 Diagnostics of SMMEs (BNPC, BIH, Local consultants) |  |  | 4 | The indicator should be upgraded to 4 due to the fact that reports have all been submitted. As well, all the audits have been completed and the team leader file has been closed. Payments for SMMEs (Interim and Final) to be followed up on.
5 | A 1.4.1 Capacity Building of SMME's and CBO's for upgrading their Competiveness |  |  | 2.25 | With regards to support to the SMEs by senior experts in service, expert missions have begun and are still on-going. The first such intervention began in March 2015 and a number of similar interventions are on-going. Any evaluation on impact could reasonably be done from September 2015. The score for these sub activity is thus upgraded. With regard to the Technical Support to SMMEs by Managers Without Boarders, the consultants have also begun their missions and the activity is on-going. The sub activity score is thus upgraded. In terms of the group training in management finance, Management training for Micros and CBOs, Group training in Business Planning for SMEs and Participation of SMMEs to trade missions & trainings, it is difficult to measure the extent of the progress in the absence of a definite date for the group training.
6 | A1.5.1 Technical Advisors and short term Experts |  |  | 3.5 | With the lack of a work-plan specifying the time frame for which the advisory services in the agro industry were to be conducted, it is difficult to assess whether such services were delivered on time. Until such clarity is resolved, then a scoring of satisfactory is appropriate. In terms of the activity pertaining to the Service provider for assistance in Construction and Public Works, the Workshop has taken place on time and the sub activity indicator should be upgraded. With respect to the short term experts support to PSDP staff, payments for BWP/1442/01 are still to be followed up on from the last quarterly report. The sub-activity score should thus receive a moderately satisfactory rating, even though the overall score of the Activity as a whole is satisfactory.