## Component 4 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY
Contributing Activity Number | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievement | Score | RATING CODE | RATING | Reporting Responsibility
. | .
A 4.1 | Recruitment of a service provider for the design of PSDP Monitoring and Evaluation (M&E) System | No M&E System | Online M&E System operational | Consultants engaged and system developed | 28-05-14 | 31-01-16 | Activity A 4.1 Completed Service Provider in place since June 2014 and M&E Progress Reporting shifted to Result Area 2 A 2.1.1 | 5 | HIGHLY SATISFACTORY | HS | CDE / BOCCIM Staff – direct system update;
A 4.2 | Design and implement PSDP Communication and Visibility Plan | No Communication and Visibility Plan | Effective implementation of the Communication and Visibility Plan | Plan is developed | 14/05/2014 | 14-01-16 | Communication and visibility plan approved; PSDP News letter launched; 4 press releases of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced. | 5 | HIGHLY SATISFACTORY | HS | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Applicable |  | DNA | Data Not Available |  | .