## Result Area 1 (D)
Monitoring and Evaluation Interim Report for the period 1st April to 30th June
Result Area 1: Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors
Contributing Activity Number | Description of Activity | BASELINE | TARGET | OUTPUT / SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievements |  |  |  |  | Score | Rating Code | Rating | Reporting Responsibility and Method
A 1.1 | Value Chains Analysis and Development
A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Previous studies and proposals | Three value chains identified that show potential to be strengthened in a published study | M & E Output Verification http://www.webtestopq.co.bw/documents/3QUtDc.pdf | 2014-08-18 | 2015-02-28 | Projects on Beef Completed and the final VC report submitted October 2014. Pursuant to the action plans of the report and the recommendations made, three action items are being implemented. (1) Management tools for Commercial Farmers (2) Upgrading capacity of Farmers Association. (3) Technical Tools of graduating communal Farmers. Horticulture and tourism in progress. The Horticulture report has been received and is now under review (18 June 2015). Tourism VCAD: received and currently under review (26 June 2015). Reports have been distributed to the stakeholders. |  |  |  |  | 3 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | No action plan exists | Five value chains in eight sub-sector capacity building actions plans to support SMMEs and IOs are developed and validated by February 2015 | PSDP M&E Report; Analysis and Development Study report and SMMEs Audit reports | 2014-07-30 | 2015-02-28 | All Five Final reports submitted by the consultant and have been reviewed by CDE as of 25 February 2015. Reformatted final report received by PSDP for comments to the consultants by 5 April 2015. Feedback on new report format submitted to HCL, 10 April 2015. Follow up to be made on final submission of all reports. Comments provided to HCL by 22 April 2015. An organisation for implementing action plans will be identified in October 2015. |  |  |  |  | 3 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
A 1.2 | Value Added wild / Natural Product Opportunity Study
A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | No opportunity study exists | Honey and Morula Action Plan opportunity studies conducted and action plans for honey and morula in place by September 2014 | PSDP M&E Reports; Contracts Awarded and Reports Tracking the Contract; Action plans Completed | 2014-06-16 | 2014-09-30 | Action plan for Honey Submitted and Morula being finalised. Reports received and approved. Final Payment being processed. Honey Technical Guide under evaluation (follow up actions). Secondary actions based on recommendations to be elaborated. Recruitment of Honey Expert to assist SMMEs and CBOs under review. No progress on Morula. Field missions have been completed. Recruitment of Honey Expert to assist SMMEs and CBOs under review. Contract submitted for approval. It is expected that capacity building and implementation of action plans from the report will begin in September 2015. |  |  |  |  | 2 | Moderately Unsatisfactory | MU | BOCCIM Staff – direct system update
A 1.3 | SME's Diagnostics (Baseline studies)
A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | No PSDP audit and need assessment | 100 SMME’s are audited | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2014-07-14 | 2014-11-07 | Team for the Diagnosis of SMMEs (BWP 1414/01) |  | Team leader final report complete and submitted. What remains are administrative actions by the PSDP unit. |  |  | 4 | Satisfactory | S | BOCCIM Staff – direct system update
[7 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Local Consultants completed 22 SMMEs out of a total of ___22_SMME's. What remains is administrative work to be completed by PSDP.
[7 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | BNPC completed 28 out of _28 SMMEs. What remains is administrative work to be completed by PSDP.
[7 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | BIH Completed 15 out of 15 SMME's. What remains is administrative work to be completed by PSDP.
[7 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | LEA completed 9 SMME's including 2 CBO's. What remains is administrative work to be completed by PSDP.
[7 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | CEDA to Complete 10 SMME's by 31st January 2015
[7 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Capacity Building of local staff on SMMe Diagnostics File Completed and closed
[7 empty] | PSDP Mission Logistics (BWP/1404/01 |  | This entailed a provisional budget to cover SMME site visits by the PSDP team. The site visit reports have been completed and made available . This will then be able to trigger an evaluation from the M&E team.
[7 empty] | SMME Diagnostics for Micros (File Number Requested) |  | These were completed. Interventions have started in which they will be attending workshops and they will also get mentors.
A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | No PSDP tailored capacity training done | 70 SMMe's and 30 Micro enterprises as well as CBOs are audited and an Action Plan for Capacity Building developed and implemented by Dec 2015 ; 10 SMMEs are implementing environmental protection plans | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2015-01-05 | 2015-12-30 | Support to poultry sector (BWP 1444/01) |  | File de-committed due to the fact that the action was cancelled. No clear explanation as to why this was the case has been forthcoming. However, the poultry companies are being assisted with some attending Occupational Safety and Health Training, Business Management Training and TBT Certification (work in progress). |  |  | 2.25 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
[7 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | Progress made in that all consultant have begun their missions and the activity is on-going. Arrangements under way for ICT, Bakery and Poultry expert trips, foreseen in June-July Time frame. ICT expert expected 2 July 2015 – 25 July.
[7 empty] | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | Progress made: Consultants have begun their missions and the activity is on-going.. Economarkets to commence local support, following introduction meetings. Contracting on-going for local consultant support. Third expert identified, with possible start-up of October 2015. The first such intervention began in march and a number of similar interventions are on-going. Any evaluation on impact could reasonably be done from September.
[7 empty] | SMEs trade missions-Result Area1 (BWP 1313/01) |  | Three SMEs from the Diary sector participated at the 9th African Diary Conference and Exhibition held in Harare, Zimbabwe from the 24 to 26 September, 2013.
[7 empty] | Group training in management Finance (BWP 1446/01) |  | TOR and budget finalized. Selection and PA to be finalised. It is difficult to measure the extent of the progress in the absence of a definite date for the group training.
[7 empty] | Management training for Micros and CBOs |  | (1) Selection of service provider done. Follow up on-going. (2) Letters distributed to attendees and follow-up to commence on 27 May 2015. It is difficult to measure the extent of the progress in the absence of a definite date for the group training.
[7 empty] | Group training in Business Planning for SMEs |  | TOR and budget finalized. Follow up PA. Budget Approved. Contract being drafted for approval and signature. It is difficult to measure the extent of the progress in the absence of a definite date for the group training.
[7 empty] | Participation of SMMEs to trade missions & trainings. In terms of trade missions and training the file number has still not been obtained since the last report |  | TOR and budget to be prepared. Again, it is difficult to measure the extent of the progress in the absence of a definite date for the group training.
[7 empty] | Individual Coaching of SMMEs |  | Activity under preparation. Request file number. Financial offer and documentation to be submitted 13th April 2015 for commitment. There is a relationship that has been established with a few organisations that offer expert services. The delays are due to administrative constraints.
[7 empty] | SME Development Experts |  | Activity under preparation. File number request is on-going
A1.5 | Technical Advisors and Short-term Experts
A1.5.1 | Technical Advisors and Short-term Experts | . | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. | . | 2014-09-11 | 2015-10-31 | Technical advisor in Agro industry (BOT/1401/01) |  | Final report submitted. File closed. This advisor is in relation to A1.1.1 which action is taking place on the recommendations of this report. |  |  | 3.5 | Satisfactory | S | BOCCIM Staff – direct system update
[7 empty] | Service Provider for assistance in construction and public works (BWP1431/01) |  | Inception Report submitted. File number requested, awaiting profile of service provider. Modules for workshop sessions have been approved, workshop completed from 15th June to 19th June 2015. Workshop report and Sunday Standard article under preparation. A training report is expected before the end of July 2015.
[7 empty] | Service Provider for assistance to clean energy companies (BWP/1426/01) |  | Final report was submitted in March 2015and the file has been closed well before the contract date lapsed. The service consisted of three missions: 1) Capacity needs assessment of 8 SMMEs, 2) Plant Assessments and Business Plans, 3) Feedback Meetings and Action Plans. An awareness training workshop was also conducted for 19 enterprises on 5th March 2015.
[7 empty] | Short-term Experts (PSDP support staff) BWP/1305/01, BWP/1407/01, BWP/1311/01, BWP/1442/01 |  | Support to PSDP junior experts and interns. The following files have been closed (BWP/1305/01, BWP/1407/01, BWP/1311/01). The only active file is BWP/1442/01 which is the payment of PSDP experts and Interns.
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0 | .
NA | Not Applicable |  | DNA | Data Not Available |  | .