## Result Area 1
Result Area Activity Monitoring Report (Summary) : Quarter Ending 30th Septemper 2015
RESULT AREA 1: | [12 empty] | Sub- Activity Score | Score | Rating Code
CAPACITY AND COMPETITIVENESS OF SMMEs AND COMMUNITY BASED ORGANISATION (CBO'S) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [12 empty] | . | 2.3 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 1.1 | 2 | MU | Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | No further progress from the last quarterly report has been observed. |  |  |  |  | . | 2 | MU
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | No further progress from the last quarterly report has been observed. |  |  |  |  | . | 2 | MU
IND 1.2 | 1 | U | Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014. |  |  | A 1.2 | Value Added wild / Natural Product Opportunity Study
[6 empty] | A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | No further progress has been reported although the contract of this activity was extended August 2015 which has long passed. |  |  |  |  | . | 1 | U
IND 1.3 | 4 | S | At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015. |  |  | A 1.3 | SME's Diagnostics (Baseline studies)
[6 empty] | A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | Team for the Diagnosis of SMMEs (BWP 1414/01) |  | Successfully completed and evaluation in progress |  |  | 4 | 4 | S
[8 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | PSDP Mission Logistics (BWP/1404/01 |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SMME Diagnostics for Micros (File Number Requested) |  | Successfully completed and evaluation in progress |  |  | 4
IND 1.3 Cont.. | 4 Cont.. | S | Cont.… |  |  | A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | Support to poultry sector (BWP 1444/01) |  | File de-committed due to the fact that the action was cancelled. No clear explanation as to why this was the case has been forthcoming. However, the poultry companies are being assisted with some attending Occupational Safety and Health Training, Business Management Training and TBT Certification (work in progress). |  |  | N/A | 1 | U
[8 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | Textile, Tourism, Furniture, Ink manufacturing and ICT completed. Backer, poultry under progress. |  |  | 3
IND 1.4 | 1 | U | At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015 |  |  |  |  | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | No further progress has been reported |  |  | 2
[8 empty] | Group training in management Finance (BWP 1446/01) |  | No progress since last report only budget finalised and activity yet to start although it was due to be completed by 31 July 2015 |  |  | 0
[8 empty] | Management training for Micros and CBOs |  | First training was completed from 15th to 26th June 2015 and the next was scheduled for August 2015. Report still not received even though it was expected on Monday 17 August 2015. |  |  | 1.5
[8 empty] | Group training in Business Planning for SMEs |  | Budget was finalised and no indication that the activity had started even though it was due to be finished on 21 August 2015. |  |  | 1.5
[8 empty] | Participation of SMMEs to trade missions & trainings. In terms of trade missions and training the file number has still not been obtained since the last report |  | No further progress although should have started in June 2015. |  |  | 0
[8 empty] | Individual Coaching of SMMEs |  | No progress since last report and this should have started on 18th May 2015 |  |  | 0
[8 empty] | SME Development Experts |  | No further progress should have started May 2015 |  |  | 0
IND 1.5 | 3.8 | S | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. |  |  | A1.5 | Technical Advisors and short term Experts
[6 empty] | A.1.5.1 |  | Technical advisor in Agro industry (BOT/1401/01) |  | Successfully completed |  |  | 4 | 3.8 | S
[8 empty] | Service Provider for assistance in construction and public works (BWP1431/01) |  | Interim payment done and final report under preparation for completion before end of October |  |  | 3.5
[8 empty] | Service Provider for assistance to clean energy companies (BWP/1426/01) |  | Final report was submitted in March 2015 and the file has been closed well before the contract date lapsed. The service consisted of three missions: 1) Capacity needs assessment of 8 SMMEs, 2) Plant Assessments and Business Plans, 3) Feedback Meetings and Action Plans. An awareness training workshop was also conducted for 19 enterprises on 5th March 2015. |  |  | 3.5
[8 empty] | Short-term Experts (PSDP support staff) BWP/1305/01, BWP/1407/01, BWP/1311/01, BWP/1442/01 |  | Successfully completed and file closed |  |  | 4
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Applicable
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | 1.4.1 Group training in management Finance (BWP 1446/01) |  |  | 0 | No progress since last report only budget finalised and activity yet to start although it was due to be completed by 31 July 2015
2 | 1.4.1 Participation of SMMEs to trade missions & trainings. In terms of trade missions and training the file number has still not been obtained since the last report |  |  | 0 | No further progress reported although should have started in June 2015.
3 | 1.4.1 Individual Coaching of SMMEs |  |  | 0 | No progress since last report and this should have started on 18th May 2015
4 | 1.4.1SME Development Experts |  |  | 0 | No further progress even though the activity should have started May 2015
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
1 | A1.1.1 Structured value chains analysis and preparation of capacity building Action plans |  |  | 2 | The indicator has been down graded to 2 moderately unsatisfactory due to the fact that there has been no change since the quarterly report. The activity is still running behind because action items are still be implemented. Tourism and horticulture value chain are set to be on going in the September weekly report even though the contract expired in August 2015.
2 | A1.1.2 Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) |  |  | 2 | The indicator has fallen from 2.5 to 2 moderately unsatisfactory there has no further progress since the quarterly report. The activity has to be finished on May 2015 although it wash scheduled to be completed by August 2015 still the activity is running behind.
3 | A1.2.1 Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) |  |  | 1 | The indicator has been downgraded from 1.5 to 1 as there has been very little progress since the last report and the activity was scheduled to be completed on 28th February 2015. The activity is running behind.
4 | A 1.3.1 Diagnostics of SMMEs (BNPC, BIH, Local consultants) |  |  | 4 | Successfully completed hence no change in score. Evaluation in progress and the result of evaluation will determine the final score. Initially evaluation carried out with positive feedback from the SMMEs. Although it was found that the time taken between audit and subsequent intervention was too long. time spent during intervention was considered to be short t by SMMEs beneficiaries. Increased visibility of PSDP through radio and newspapers will be important on going forward. further evaluations is still on-going.
5 | A 1.4.1 Capacity Building of SMME's and CBO's for upgrading their Competiveness |  |  | 1 | The indicator has fallen from 1.9 to 1 which is unsatisfactory because a number of activities due to be completed in June and July have not been finalised yet. As well some activities have not been reported to have started on time.
6 | A1.5.1 Technical Advisors and short term Experts |  |  | 3.8 | Activities successfully completed. As such, the indicator has improved to a satisfactory rating.