## Result Area 2
Result Area Activity Monitoring Report (Summary) : 30th September 2015
RESULT AREA 2: | [12 empty] | Sub-Activity Score | Score | Rating Code
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced. | [12 empty] | . | 3.4 | S
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 2.1 | 4.3 | S | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 10% by December 2015. • PSDP Web based M&E system is operational by December 2014. |  |  | A 2.1 | Capacity Building of BOCCIM
[6 empty] | A 2.1.1 | Internal Monitoring and Evaluation of PSDP | Running smoothly as per schedule |  |  |  |  | . | 4.5 | S
[6 empty] | A 2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | Review of the mandates and establish BOCCIM as an Apex body (BOT/1402/01) |  | Successfully completed |  |  | . | 5 | HS
[8 empty] | Review of BOCCIM Constitution (BWP/1401/01 ) |  | Successfully completed |  |  | .
[8 empty] | BOCCIM Membership Model (BWP/1402/01 ) |  | Successfully completed |  |  | .
[8 empty] | Consultative Workshops for BOCCIM (BWP/1416/01 ) |  | Successfully completed |  |  | .
[6 empty] | A 2.1.3 | BOCCIM capacity building to render better services to its members (BWP/1437/01) | Final report has been received and it is being reviewed. This task should be completed by 31 August 2015. Additional attachments are expected from Business Botswana to go with the final version . |  |  |  |  | . | 3.5 | S
[6 empty] | A 2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | TOR and Budget still to be prepared. The activity falls under foreseen projects. |  |  |  |  | . | N/A | N/A
|  |  | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs - June 2015. |  |  | A 2.1.4 | Assistance to the establishment of market intelligence information system/web based platform for networking and information / Public and private dialogue, etc… (BWP/1434/01) | Benchmarking BOCCIM web Portal (BWP/1434/01) |  | File closed. BOCCIM to reimburse PSDP |  |  | . | N/A | N/A
[8 empty] | Feasibility study for the market intelligence being done under Value chain analysis for beef, tourism, and horticulture sectors (BWP/1310/01 ). |  | On hold till PSDP is transferred to BOCCIM |  |  | .
[8 empty] | Assistance to the establishment of market intelligence information |  | Project on hold till PSDP is transferred to BOCCIM |  |  | .
Ind 2.2 | 4 | S | Capacity building of BITC is conducted • An export strategy with respective action plan is adopted and implementation of the action plan starts in December 2015. • Three partnerships are established with external trading partners by December 2015. • At least 10 of the PSDP targeted SMMEs are qualified for export by BITC by December 2015. |  |  | A 2.2 | Capacity Building of BITC
[6 empty] | A 2.2.1 | Assistance to BITC in Export Development and Promotion (BWP/1406/01) | Training completed |  |  |  |  | . | 4 | S
[6 empty] | A 2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | Participation of IOs to trade missions & trainings – (BWP/1307/01) |  | Successfully completed |  |  | . | 4 | S
[8 empty] | Participation of IOs to trade missions & trainings – (BWP/1308/01) |  | Successfully completed |  |  | .
[8 empty] | BITC sector association experts- .(BWP/1503/01) |  | Successfully completed, report to be received |  |  | .
Ind 2.3 | 2 | MU | Capacity building of Intermediary Organisations and sector associations is conducted. • Number of private firms using TSIs and BDSPs services increased by 10% by December 2015. • At least 70% of SMMEs and CBOs benefiting from PSDP intervention are satisfied with the quality of service provided by IOs and BDSPs. • Recommendations developed and submitted to MTI by December 2015 for improving competitiveness and export of Botswana Beef. • At least three new products and/or services introduced by IOs by December 2015. |  |  | A 2.3 | Capacity Building of Intermediary Organisations and Sector Associations
[6 empty] | A 2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) (BWP/1420/01) | 62 local staff from Intermediary Organisation were trained- the activity has been completed and closed. |  |  |  |  | . | 4 | S
[6 empty] | A 2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | PPD Meeting on Beef Value Chain (BWP/1428/01) |  | Successfully Completed. All payments approved in FAST. Submit payments to the bank and justifications. |  |  | 4 | 3.1 | S
[8 empty] | Management Tools for Commercial farmers (BWP/1508/01) |  | Comments have been sent to the consultant to be consolidated. Request has been sent to consultant to submit request for final payment such that we are able to close the file before transfer. |  |  | 2.5
[8 empty] | Technical Tools for Graduating communal farmers (BWP/1510/01) |  | Contract extended till September 2015 and the final interim report has been paid |  |  | 3
[8 empty] | Upgrading Capacity of farmers Associations (BWP/1511/01) |  | The ICSA experts will be coming for their second mission during the week of the 5 September for group training |  |  | 2.5
[8 empty] | SME's Sensitisation on foot and mouth Diseases |  | The local foot and mouth disease will be having a group training in Maun during the week of the 5 September together with the experts from ICSA. |  |  | 3.5
[6 empty] | A 2.3 3 | Assistance to the tourism sector in partnership with BTO and HATAB | Assistance to the tourism sector in partnership with BTO and HATAB |  | According to the September weekly reports, the file number is still to be requested, although in the June report, the activity had already began to be rolled out. |  |  | 2 | 3 | MS
[8 empty] | HATAB Tourism conference (BWP/1443/01) |  | Activity completed and file has been de-committed. |  |  | 4
[6 empty] | A 2.3.4 | Assistance to honey sector associations | The file is reflected to have been committed although this was meant to have started in April. |  |  |  |  | 0 | 0 | HU
IND 2.4 | 3.66 | S | Capacity building conducted for BOBS on Quality Certification Draft National Quality Policy is developed and submitted to MTI by June. |  |  | A 2.4 | Capacity Building for BOBS on Quality and Certification
[6 empty] | A 2.4.1 | Support the development of a National Quality Policy | This forms part of the ACP/TBT programme. Validation of report completed. Phase one and phase two were completed within the review period. Phase three will be completed in the second half of the year |  |  |  |  | 4 | 3.7 | S
[6 empty] | A 2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | This forms part of the ACP/TBT programme. Validation of report completed. Phase one and phase two were completed within the review period. Phase three will be completed in the second half of the year |  |  |  |  | 3.5
[6 empty] | A 2.4.3 | Support the process of certification for SMEs | TBT Workshop commenced with beneficiaries and service providers at BOBS. There was a free five days consultancy offered to the beneficiaries |  |  |  |  | 3.5
IND 2.5 | 2.5 | MS | Technical Advisors and short term experts |  |  | A.2.5 | Technical Advisors and short term experts
[6 empty] | A2.5.1 | Technical Advisor in Tourism (BWP/1408/01) | Contract has been terminated due to performance issues of the consultant. These performance issues have yet to be indicated to the PSDP Monitoring Unit. |  |  |  |  | 0 | 2.25 | MS
[6 empty] | A2.5.1 | Anthropologist for Tsodilo Hills | Second mission completed and currently reviewing interim report |  |  |  |  | 3.5
[6 empty] | A.2.5.1 | Branding and marketing Tsodilo Hills(BWP/1518/01) | Branding and market strategy for Tsodilo world heritage completed. Mission currently awaiting her inception report which is expected end of August 2015 |  |  |  |  | 2.5
[6 empty] | A2.5.2 | Short-term Experts (PSDP support staff) BWP/1305/01, BWP/1407/01 ,BWP/1311/01, BWP/1442/01 | According the September weekly meetings, follow up payment for BWP/1442/01 and its continuation in year three is still to be undertaken. |  |  |  |  | 3
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | HATAB and BTO | U | 0< U <=1 | HU | HU=0 | NA | . | Not Applicable
.
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | 2.3.4 Assistance to honey sector associations |  |  | 0 | TOR and Budget to be prepared to start April 2015 but as of 30th June 2015, this had not happened yet.
2 | A2.5.1 Technical Advisor in Tourism (BWP/1408/01) |  |  | 0 | Contract has been terminated due to performance issues of the consultant.
3 | A 2.1.2 Review of the mandates and establish BOCCIM as an Apex body |  |  | 5 | PSDP/CDE has completed all their responsibilities and handed over the reports to BOCCIM for further action therefore the score has been upgraded to 5. Following this action from BOCCIM, the M&E team also conduct a follow up.
. | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Observations, Lessons Learnt and Suggestions for way forward
1 | A 2.1.1 Internal Monitoring and Evaluation of PSDP |  |  | 4.5 | There is an improvement in the alignment of the weekly progress report and the inputs required for the M&E framework. Further efforts required to enhance the quality of the weekly report minutes and an improvement in the internal communication systems.
2 | A 2.1.2 Review of the mandates and establish BOCCIM as an Apex body |  |  | 5 | The activity has been completed and the file has been closed. BOCCIM is implementing recommendations. The reviewed constitution was accepted at a BOCCIM general meeting, and is now undergoing a process of registration with the competent authority. Work-plans and end of activity reports would be useful to trigger future evaluations.
3 | A2.1.3 BOCCIM capacity building to render better services to its members |  |  | 3.5 | The Interim report was yet to be submitted by the consultant in June and yet the contract was meant to end in April 2015.
4 | A 2.1.5 Training BOCCIM and other IOs in policy research, lobbying & advocacy |  |  | NA | ToR and Budget still to be prepared. The activity falls under foreseen projects.
5 | A 2.1.4 Assistance to the establishment of market intelligence information |  |  | NA | On hold till PSDP transferred to Business Botswana.
6 | A 2.2.1 Assistance to BITC in Export Development and Promotion (BWP/1406/01) |  |  | 4 | There have been significant achievements in the indicator and it should be upgraded to moderately satisfactory.
7 | A 2.2.2 Assistance to BITC for implementation of its new strategy (sector approach) |  |  | 4 | Out of the three parts two parts are completed. Inception report for profiling ICT and mining sectors for potential investors is still to be submitted. The indicator should be downgraded as a result of this. Sector profiles are to be presented to BITC management by the consultants. Final report still pending and the project is to be taken over by BITC.
8 | A 2.3.1 Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) (BWP/1420/01) |  |  | 4 | The activity has been completed and closed. M&E team to conduct an evaluation.
9 | A 2.3.2 Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export |  |  | 3.1 | In terms of the Management Tools for Commercial farmers, indicator was downgraded from 3 to 2.5 because the payments are still being processed beyond the end dates of the contracts. With respect to the Upgrading Capacity of farmers Associations, the sub-activity score was downgraded due to the fact that the PSDP coordination team has not provided the monitoring team with an update on the progress being made. In terms of the SME's Sensitisation on foot and mouth Disease, the sub-activity score was upgraded because there is some progress that was observed in the report.
10 | A2.3.4 Assistance to the tourism sector in partnership with BTO and HATAB |  |  | 2 | According to the September weekly reports, the file number is still to be requested, although in the June report, the activity had already begun to be rolled out. As such, the activity score was downgraded to 2.
11 | A2.3.4 Assistance to honey sector associations |  |  | 0 | Indicator should be changed to Highly unsatisfactory due to the fact the activity was supposed to begin in April but the ToRs and the budget are still to be prepared.
12 | A 2.4 Capacity Building for BOBS on Quality and Certification and all sub activities |  |  | 4 | These were supposed to start in May and April 2015. The terms of references are still to be prepared. Although the TBT Workshop commenced with beneficiaries and service providers at BOBS. The Activity should be awarded an unsatisfactory score because of the failure to meet the initial timetable.
13 | A2.5.1 Branding and marketing Tsodilo Hills |  |  | 2.5 | The coordination team is currently awaiting the consultant's inception report which was expected by the end of August 2015. There is no indication in the September weekly report as to whether this has taken place. As such, the sub activity was downgraded to 2.5.