## Progressive
Performance of each Log Frame Indicator Progressive Quarter Wise (Summary) 31st October 2015
.
Result Area One :Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 1.1 | Action plans to support SMMEs and IOs are developed foe eight value chains and eight sub sectors by February 2015 | NA | S | S | S | MS | S | . | . | The indicator showed an improvement. The activities were completed and final reports submitted. ITC contract has been extended to the 30th of December 2015. Approval for Tourism report value chain still pending but the activity has been completed and a draft report has been submitted
Ind 1.2 | Studies are carried out for development of Honey and Morula Value Chains by September 2014. | HU | MU | MS | MS | MU | S | . | . | The indicator showed an improvement. The activities were completed and final reports submitted. The reviews of the final report were also completed.
Ind 1.3 | At least 70 SMMEs are strengthened on management, operations by December 2015. | MS | MS | MU | MU | S | S | . | . | This activities under this indicator have been completed.
Ind 1.4 | 30 CBO’s are trained on management, marketing, quality standards and accounting by December 2015 | NA | NA | HU | HU | MS | MS | . | . | The indicator remains moderately satisfactory. Some alerts were made with regards to Participation of SMMEs to missions and trainings in which the activity was dropped. As well, with respect to SMME development experts, the sub-activity attracted a score of unsatisfactory because no progress had been made and yet it is was expected to have commenced in May and completed in December 2015.
Ind 1.5 | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. | NA | NA | HU | HU | S | S | . | . | Activities have been completed and the rating remains satisfactory
Result Area Two: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 2.1 | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana and M&E is Operational by December 2014 | MU | S | S | S | S | S | . | . | No change from last quarter
Ind 2.2 | A web based market intelligence information system is developed for use by SMMEs - June 2015. | U | MS | MS | S | S | S | . | . | No change from last quarter
Ind 2.3 | Capacity building of BITC is conducted by December 2015 | NA | NA | U | MS | MS | S | . | . | Indicator has improved due to the fact that many of the activities are going according to schedule and some of them have been completed.
Ind 2.4 | Capacity building of CBO's and IO's is conducted by December 2015 | NA | MS | MS | MS | S | S | . | . | No change from last quarter. Progress on this activity is on-going.
Ind 2.5 | Capacity building of BOBS is conducted by December 2015 | NA | NA | NA | NA | MU | MS | . | . | Some progress has been observed, however, A2.5.1 brought the overall rating down due to an unsatisfactory scoring as a result of performance issues.
Result Area Three: Business environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 3.1 | Capacity building conducted on trade and specific negotiation skills | NA | S | S | S | S | S | . | . | No overall change from last quarter.
Ind 3.2 | Improved Policy Framework to access finance | NA | HS | MS | MS | HS | HS | . | . | A3.2.2 was dropped from the list of activities by the MC.
Ind 3.3 | Improved Business Environment (Ease of Doing Business) | NA | NA | MS | MU | S | S | . | . | Indicator doing well and activities have been completed.
Component Four: Management and Communications
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
NA | Performance Management and Communications | MS | HS | HS | HS | HS | HS | . | . | No change from last quarter
NA | Not Applicable | . | . | . | . | . | . | . | NA | Not Due to Start
HS | 4< HS <=5 | S | 3< S <=4 |  |  | MS | 2< MS <=3 |  | MU | 1< MU <=2
U | 0< U <=1 | HU | HU =0 |  |  | . | . | . | . | .