## Evaluation
Results of Assessment of Completed Activities
S. No | Result Area | Activity | Feedback / Remarks on Completed Activities |  | Recommendations on Action to be taken
1 | RA 1 | A.1.3.1 Diagnostics of SMMEs (BNPC, BIH, Local consultants) | There were 6 SMMEs evaluated. There are indications that there is generally an increase in production, employment and financial turnover. |  | Evaluations ongoing.
2 | RA 2 | A2.3.1 Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) (BWP/1420/01) | 3 IOs/ Service providers interviewed. General satisfaction expressed about the usefulness of the tool. There was however a view that the number of days it takes to deploy the tool were too many. |  | It will be useful to ensure same people conducting the audits are also conducting the interventions. |  | `
3 | RA 3 | Draft a microfinance policy framework (BWP/1403/01), (BWP/1418/01), (BWP/1415/01) | 2 Financial Institutions interviewed. They were generally happy with the democratic and deliberative process that led to the adoption of the Micro-financing framework. |  | Hopeful implementaiton efforts by government will improve. As well, there should be clear lines of reponsibility for implementation.
Lessons Learnt and Way forward Result Area and Activity Wise
S. No | Result Area | Activity | Lessons learnt in Execution | Remedial Action / Improvements Possible |  | Remarks
1 | RA 1 | A.1.3.1 Diagnostics of SMMEs (BNPC, BIH, Local consultants) | 1) Time spent on interventions was too short; 2) the time taken between audit and intervention was too long; 3) Some SMMEs thought assistance included financial aid; 4) Wider marketing of PSDP initiatives will be benificial. | Same people conducting audits should conduct interventions; improve visibility of PSDP by advertising in a wider media network |  | .
2 | RA 2 | A2.3.1 Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) (BWP/1420/01) | 1) Accessibility challenges for SMMEs in remote areas; 2) Gaps in keeping contact with SMMEs post intervention; 3) Time taken for audits too long; 4) IOs should be involved in the recruitment of SMMEs; 5) Diagnostic tool has its limitations | Review diagnostic tool for improvements; create network between IOs and SMMEs ; create clear lines of responsibility for implementation, which should form part of each activity |  | .
3 | RA 3 | Draft a microfinance policy framework (BWP/1403/01), (BWP/1418/01), (BWP/1415/01) | 1) Democratic process at consultative workshop lauded; 2) Potential impact of the draft microfinance policy framework servincing the informal sector of Botswana | BB to push policy issues through more contact with MTI (and Government in general). |  | .