## Overall Summary
Monitoring and Evaluation Report (Summary) : 31st October 2015
Result Area / Component |  |  | Rating | Rating Code | Remarks on Significant Achievements
RESULT AREA 1: CAPACITY AND COMPETITIVENESS OF SMME’S AND COMMUNITY BASED ORGANISATION (CBOS) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS |  |  | 3.4 | S | There has been an overall improvement from the last quarter. Areas in responsible for this improvement include, A1.1.1 (Structured Value Chains) and A1.1.2 (Emerging Value Chains) and A1.2.1 (Action Plans for Honey and Morula)in which the majority activities have been completed. There has also been an overall improvement in A1.4.1, particularly in the areas of individual coaching of SMMEs, management training for Micros and CBOs and the technical support to SMMEs by Senior Experts in Service and Managers without Borders. There are however some areas of concern which will require attention.
RESULT AREA 2: SERVICE DELIVERY OF TARGETED INTERMEDIARY ORGANISATIONS (IOs) AND BUSINESS DEVELOPMENT SERVICE PROVIDERS (BDSP) IS ENHANCED |  |  | 3.7 | S | There has been a slight improvement in this result area as a result of improved scores in A2.3.1 (Training and Coaching of IOs) and A2.3.2 (Assistance to the meat sector), and activates commencing under A2.4 which relate to Capacity Building for BOBS on Quality and Certification. Some alerts have been given which would have to be attended to. It should be noted that some activities were put on hold until the transfer of PSDP from CDE to BOCCIM was complete. One major area of concern is the fact that under the Technical Advisor in Tourism (A2.5.1), the contract wsa cancelled due to performance issues of the consultant.
RESULT AREA 3: BUSINESS ENVIRONMENT FOR ENTERPRISES IS IMPROVED (REDUCTION OF RED TAPE AND PILOT ON IMPROVED ACCESS TO FINANCE BY SMMEs) |  |  | 3.8 | S | Very little change from the last report. The Result Area is doing very well and will be monitored closely in going forward. It is however noted that there was no observed progress under A3.1.2 (Training of TFAG and NTCPN on negotiation and trade facilitation) and A3.1.3 (Capacity building of MTI on trade issues).
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY |  |  | 5 | HS | No Change visible as compared to previous report
4< HS <=5 | 3< S <=4 | 2< MS <=3 | 1< MU <=2 |  | 0< U <=1 | HU =0 | .