## Result Area 1
Result Area Activity Monitoring Report (Summary) : 31st October 2015
RESULT AREA 1: | [12 empty] | Sub- Activity Score | Score | Rating Code
CAPACITY AND COMPETITIVENESS OF SMMEs AND COMMUNITY BASED ORGANISATION (CBO'S) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [12 empty] | . | 3.4528 | S
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 1.1 | 3.5 | S | Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | The Management tools for commercial farmers has been completed. The Technical tools for graduating communal farmers has also been completed. Upgrading capacity of famers association and sensitisation of farmers on foot and mouth disease is on-going. The Horticulture report has been received and the review by all stakeholders has since been completed on 19th August 2015. The ITC contract has been extended to the 30th of December 2015. Approval for Tourism report value chain still pending but the activity has been completed and a draft report has been submitted. |  |  |  |  | . | 3.5 | S
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | All final reports including follow-ups were submitted by 20 May 2015. Process of identifying and organisation for implementing action plans is currently on-going. |  |  |  |  | . | 3.5 | S
IND 1.2 | 3.1 | S | Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014. |  |  | A 1.2 | Value Added wild / Natural Product Opportunity Study
[6 empty] | A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | Opportunity study for honey and morula was done and completed. All final documents had been received by 20th February 2015. A new activity was started for the upgrading of honey and morula CBOs and associations. File for this activity has been closed. |  |  |  |  | . | 3.1 | S
IND 1.3 | 4 | S | At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015. |  |  | A 1.3 | SME's Diagnostics (Baseline studies)
[6 empty] | A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | Team for the Diagnosis of SMMEs (BWP 1414/01) |  | Successfully completed and evaluation in progress |  |  | 4 | 4 | S
[8 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | PSDP Mission Logistics (BWP/1404/01 |  | Successfully completed and evaluation in progress |  |  | 4
[8 empty] | SMME Diagnostics for Micros (File Number Requested) |  | Successfully completed and evaluation in progress |  |  | 4
IND 1.3 Cont.. | 4 Cont.. | S | Cont.… |  |  | A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | Support to poultry sector (BWP 1444/01) |  | File de-committed due to the fact that the action was cancelled. No clear explanation as to why this was the case has been forthcoming from the service provider. |  |  | N/A | 2.8667 | MS
[8 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | Textile, Tourism, Furniture, Ink manufacturing and ICT completed. Bakery, poultry began in February 2015 and under progress. To date 5 experts have been received. |  |  | 3.5
IND 1.4 | 3 | MS | At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015 |  |  |  |  | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | First two interventions have been completed and one is on-going, |  |  | 3.5
[8 empty] | Group training in management Finance (BWP 1446/01) |  | Group training in management finance put off until January 2016 due to transfer to BB of PSDP. Activity had been approved in May. |  |  | 2
[8 empty] | Management training for Micros and CBOs |  | The companies in agro processing were being assisted with some attending Occupational Safety and Health Training (end of July to beginning of august), Business Management Training and TBT Certification (6th to 10th July and 10th to 14th august). |  |  | 3.1
[8 empty] | Group training in Business Planning for SMEs |  | Same as Group training in management finance |  |  | 2
[8 empty] | Participation of SMMEs to trade missions & trainings. In terms of trade missions and training the file number has still not been obtained since the last report |  | This has been since removed as an activity. This was an administrative decision and clarity needs to be sought on this. |  |  | NA
[8 empty] | Individual Coaching of SMMEs |  | This took place with Economarkets consulting. The contract was signed on the 5th of June and was to end in November 2015. The final report was submitted on 15th September 2015. |  |  | 3.1
IND 1.5 | 3.8 | S | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. |  |  | A1.5 | Technical Advisors and short term Experts
[6 empty] | A.1.5.1 |  | Technical advisor in Agro industry (BOT/1401/01) |  | Successfully completed |  |  | 4 | 3.75 | S
[8 empty] | Service Provider for assistance in construction and public works (BWP1431/01) |  | Interim payment done and final report under preparation for completion before end of October |  |  | 3.5
[8 empty] | Service Provider for assistance to clean energy companies (BWP/1426/01) |  | Final report was submitted in March 2015 and the file has been closed well before the contract date lapsed. The service consisted of three missions: 1) Capacity needs assessment of 8 SMMEs, 2) Plant Assessments and Business Plans, 3) Feedback Meetings and Action Plans. An awareness training workshop was also conducted for 19 enterprises on 5th March 2015. |  |  | 3.5
[8 empty] | Short-term Experts (PSDP support staff) BWP/1305/01, BWP/1407/01, BWP/1311/01, BWP/1442/01 |  | Successfully completed and file closed |  |  | 4
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Applicable
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
1 | A1.1.1 Structured value chains analysis and preparation of capacity building Action plans |  |  | 3.5 | With this activity, the Management tools for commercial farmers has been completed. The Technical tools for graduating communal farmers has also been completed. Upgrading capacity of famers association and sensitisation of farmers on foot and mouth disease is on-going. The Horticulture report has been received and the review by all stakeholders has since been completed on 19th August 2015. The ITC contract has been extended to the 30th of December 2015. Approval for Tourism report value chain still pending but the activity has been completed and a draft report has been submitted. Taking all of this into account, the indicator attracts a satisfactory score.
2 | A1.1.2 Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) |  |  | 3.5 | The indicator rating has been upgraded to 3.5 which is satisfactory. This is due to the fact that all the final reports including follow-ups were submitted by 20 May 2015. Process of identifying and organisation for implementing action plans is currently on-going.
3 | A1.2.1 Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) |  |  | 3.1 | The indicator attracted a score of 3.1. The Opportunity Study for honey and morula was successfully completed. All final documents had been received by 20th February 2015. A new activity was started for the upgrading of honey and morula CBOs and associations. The file for this activity has been closed.
4 | A 1.3.1 Diagnostics of SMMEs (BNPC, BIH, Local consultants) |  |  | 4 | Successfully completed hence no change in score. Evaluation in progress and the result of evaluation will determine the final score. Initially evaluation carried out with positive feedback from the SMMEs. Although it was found that the time taken between audit and subsequent intervention was too long. time spent during intervention was considered to be short t by SMMEs beneficiaries. Increased visibility of PSDP through radio and newspapers will be important on going forward. further evaluations is still on-going.
5 | A 1.4.1 Capacity Building of SMME's and CBO's for upgrading their Competiveness |  |  | 3 | The indicator has risen to 3 (which is moderately satisfactory) due to the following reasons. Under the technical support to SMEs by senior experts in service, 5 experts have been received so far, with two more currently undertaking their missions. With the technical support to SMMEs by Managers without borders, the first two interventions have been completed and one is on-going. With the group training in management finance, an alert is sent that this activity had been suspended until January 2016 due to transfer of PSDP to BB. In terms of the management training for Micros and CBOs, a number of trainings have been completed which are, Occupational Safety and Health for agro processing companies and Business Management Training and TBT Certification. With the individual coaching of SMMEs, the final report was submitted in September 2015. An alert is sent that the Participation of SMMEs to trade missing and trainings has since been removed as an activity in the monitoring framework. An alert is also sent with respect to the SME Development Experts to the extent that no further progress has been recorded and the activity should have started in May 2015 to finish in December 2015.