## Overall Summary
Monitoring and Evaluation Report (Summary) : 12th February 2016
Result Area / Component | [5 empty] | Rating | Rating Code | Remarks on Significant Achievements
RESULT AREA 1: CAPACITY AND COMPETITIVENESS OF SMME’S AND COMMUNITY BASED ORGANISATION (CBOS) INCLUDING VALUE CHAINS IS STRENGTHENED | [5 empty] | NA | NA | Some activities, although carried over into the new logframe, from the old one, have effectively been completed and are undergoing the requisite stages before their files can be decommitted. These include the value chains in A1.1.1 (Structured value chains analysis and preparation of capacity building Action plans) and A1.1.2. (Emerging value chains analysis and preparation of capacity building Action plans) In some instances, delays have been caused by stakeholders not cooperating fully with the PSDP coordination team (such as A1.2.3, Assistance to the Botswana National Beef Producers Union ). However, for many of the projects, the delay can be attributed to the fact that many of the service providers contracted are not familiar with the EDF rules. Indeed, the PSDP coordinating unit has also had to spend some time familiarising themselves with these rules. In a number of cases, some activities were merged because it was more efficient to do so, and increase the maximum budget for the combined activities, as per the requirements of the EDF rules.
RESULT AREA 2: SERVICE DELIVERY OF TARGETED INTERMEDIARY ORGANISATIONS (IOs) AND BUSINESS DEVELOPMENT SERVICE PROVIDERS (BDSPs) IS ENHANCED | [5 empty] | NA | NA | As with Result Area 1, numerous activities have attracted a rating of NA, owing to the fact that they are yet to commence. As well, there have been some delays experienced because of the time taken to adapt to the new EDF procedures. There are noted improvements however in: A2.7.1, Capacity building and skills development for the Tsodilo Community Trust Members; and in A2.1.2 Local Expert engaged to work with BB in the implementation of a new governance structure. Areas that have remained the same since the last quarter are the Internal M&E of PSDP and Branding and Marketing of the Tsodilo World Heritage Site. These latter activities are continuing as expected. In one activity, A2.5.1, BITC has expressed that the funds that were allocated, were not enough to undertake it, as they were also earmarked to be used for A2.4.1.
RESULT AREA 3: INFORMATION DISSEMINATION AND AWARENESS FOR TRADE AGREEMENTS ENHANCED | [5 empty] | NA | NA | There are two indicators with planned activities in this Result Area. Both activities are expected to commence in April 2016.
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY | [5 empty] | 5 | HS | No Change visible as compared to previous report
4< HS <=5 | . | 3< S <=4 | . | 2< MS <=3 | . | 1< MU <=2 | . | 0< U <=1 | . | HU =0 | . | .