## Progressive
Performance of each Log Frame Indicator Progressive Quarter Wise (Summary) 12th February 2016
.
Result Area One :Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016 | Q1 2017
Ind 1.1 | Seven (7) Value Chains with respective action plans in seven (7) sub sectors are validated and realization of opportunities identified with lead organizations by October 2016 | S | . | . | . | . | Activities in this indicator have been completed and are undergoing the final stages before the files are de-committed.
Ind 1.2 | Capacity of beef farmers associations in two (2) regions is strengthened in order to be more competitive in the local, regional and international market by October 2016. | NA | . | . | . | . | Only one activity has been completed which relates to the Upgrading Capacity of Beef farmers Associations. The other two activities are yet to begin.
Ind 1.3 | Capacity of at least one (1) honey and morula association is strengthened and at least four (4) beekeeping experts are trained by June 2016. | S | . | . | . | . | The indicator has one activity in which the final report has been submitted and final payments are being processed.
Ind 1.4 | Two (2) raw material supply chain study are carried out with respective action plans for honey and morula CBOs and SMMEs are developed and validated by October 2016. | NA | . | . | . | . | The sole activity in this indicator is yet to commence.
Ind 1.5 | At least 70 SMMEs are strengthened on management, operations in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by October 2016. | NA | . | . | . | . | The numerous sub-activities under this indicator are yet to commence.
Ind 1.6 | At least four (4) SMMEs are assisted in quality standards and certification is obtained by August 2016. | NA | . | . | . | . | There are two activities in this indicator which are yet to commence.
Ind 1.7 | Thirty (30) micro-enterprises and Community Based Organizations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance and mentoring by October 2016. | NA | . | . | . | . | There are two activities in this indicator which are yet to commence.
Ind 1.8 | Forty (40) SMMEs and CBOs have participated in environmental awareness activities by September 2015. | NA | . | . | . | . | The sole activity in this indicator was subsumed under Indicator 1.5 and it is therefore suggested that this indicator is dispensed with.
Ind 1.9 | Five (5) interns are placed at enterprises by March 2016. | MS | . | . | . | . | There is one activity under this indicator which is on-going. The National Internship office has been contacted and the various beneficiary enterprises are also to be contacted.
Result Area Two: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced.
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016 | Q1 2017
Ind 2.1 | BB is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 5%. | MS | . | . | . | . | An international expert has been procured and has started working with the local one.
Ind 2.2 | BB is fully capacitated on Web based M&E system by Dec 2015. | S | . | . | . | . | M&E system has been established and is running smoothly at BB.
Ind 2.3 | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs – October 2016. | NA | . | . | . | . | The sole activity in this indicator is yet to commence owing to adaption of EDF rules.
Ind 2.4 | Curriculum on export development promotion is developed for BITC by June 2016. | NA | . | . | . | . | The sole activity in this indicator is yet to commence owing to adaption of EDF rules.
Ind 2.5 | BITC and clients with export potential are trained on export to regional and international markets by August 2016. | NA | . | . | . | . | BITC have expressed that the EUR 35,000 which was set aside to undertake activities in both Ind 2.4 and Ind 2.5 was not enough, and as such, this activity cannot be rolled out.
Ind 2.6 | At least one (1) MoU with IO is signed by October 2016. | NA | . | . | . | . | The activity is yet to commence.
Ind 2.7 | Local capacity of at least one (1) community trust to manage a heritage site by October 2016. | S | . | . | . | . | The sole activity in this indicator has been completed. The final report is now pending.
Ind 2.8 | At least one (1) new cultural tourism product is developed by June 2016. | MS | . | . | . | . | No change from the last quarter
Result Area Three: Business environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016 | Q1 2017
Ind 3.1 | At least ten (10) NSA is trained in implementation of trade agreement by June 2016 | NA | . | . | . | . | Activity is yet to commence
Ind 3.2 | Two (2) workshops are conducted on international trade opportunities by June 2016 | NA | . | . | . | . | Activity is yet to commence
Component Four: Management and Communications
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016 | Q1 2017
NA | Performance Management and Communications | HS | . | . | . | . | Dialogue Sachi and Sachi contract extended to June 2016. M&E system established and running smoothly. Indicator doing well for this quarter.
NA | Not Applicable | . | . | . | . | . | . | . | NA | Not Due to Start
HS | 4< HS <=5 | S | 3< S <=4 |  |  | MS | 2< MS <=3 |  | MU | 1< MU <=2
U | 0< U <=1 | HU | HU =0 |  |  | . | . | . | . | .