## Result Area 1
Result Area Activity Monitoring Report (Summary) : 12th February 2016
RESULT AREA 1: | [12 empty] | Sub- Activity Score | Score | Rating Code
Capacity and competitiveness of SMMEs and Community Based Organisations (CBOs) including value chains is strengthened. | [13 empty] | . | .
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 1.1 | 3.5 | S | Seven (7) Value Chains with respective action plans in seven (7) sub sectors are validated and realization of opportunities identified with lead organizations by October 2016 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Tourism value chain has been finalised with the Report completed. Technical guides have been developed and are completed, although this goes beyond the deliverables of the contract. |  |  |  |  | . | 3.5 | S
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | This activity has been completed and payment is being processed. Technical guides have been developed and are completed, although this goes beyond the deliverables of the contract. |  |  |  |  | . | 3.5 | S
IND 1.2 | NA | NA | Capacity of beef farmers associations in two (2) regions is strengthened in order to be more competitive in the local, regional and international market by October 2016. |  |  | A 1.2 | Capacity Building of Beef Farmers Associations
[6 empty] | A 1.2.1 | Upgrading Capacity of Beef farmers Associations | The regions in question are Ghazi and Ngami land. The Farmers association invited an Irish association (ICSA) to capacitate them under an activity financed by PSDP. The assistance was geared at making the local associations run their operations more effectively. These associations are in operation and lobbying for their members. The activity has been completed and payment is being processed for both associations. |  |  |  |  | . | 4 | S
[6 empty] | A1.2.2 | A select number of commercial beef farmers will be taken on a benchmarking mission to UK | There is an agricultural Show to the UK entitled "Royal III Counties" expected to commence from the 17th to the 19th of June. |  |  |  |  | . | NA | NA
[6 empty] | A1.2.3 | Assistance to the Botswana National Beef Producers Union | Activity had not yet begun due to the fact that the Ministry of Agriculture had not yet provided information that is pertinent to its commencement. |  |  |  |  | . | NA | NA
IND 1.3 | 4 | S | Capacity of at least one (1) honey and morula association is strengthened and at least four (4) beekeeping experts are trained by June 2016. |  |  | A1.3 | Wild / Natural Product Capacity Building
[6 empty] | A1.3.1 | Assistance to Associations and experts to enable them to become more structured | The activity was carried over from CDE. The consultant has forwarded the final report and copies of the business plan have been worked on with the beekeeping associations, as well as draft article for news letter. The Honey technical guides are now being finalised with the beekeeping expert. Final payment is being processed. |  |  |  |  | . | 4 | S
IND 1.4 | NA | NA | Two (2) raw material supply chain study are carried out with respective action plans for honey and morula CBOs and SMMEs are developed and validated by October 2016. |  |  | A1.4 | Raw Material Supply Chain Studies
[6 empty] | A1.4.1 | Development of action plans for honey and morula CBOs and SMMEs | Budget is finalised and the ToRs are being finalised. Tender will be launched in February but the activity is set to commence in April until the end of June. |  |  |  |  | . | NA | NA
IND 1.5 | NA | NA | At least 70 SMMEs are strengthened on management, operations in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by October 2016. |  |  | A 1.5 | Strengthening of SMMEs on Management Operations
[6 empty] | A1.5.1 | Business Plan Preparation (Quality Control) |  |  | Tender being prepared. Expert expected to have been procured from mid-February to early March 2016. |  |  | . | NA | NA
[6 empty] | A1.5.2 | Provisions of finance and management coaching by Local Experts SMMEs and CBOs - North |  |  | Competitive Tender was sent out on the 5th February and the deadline for Reponses is the 5th of March 2016. The Activity is expected to have began by 1st April to 30th June. The budget has been increased to 35,000 because a workshop has been included before the mentorship is to begin. |  |  | . | NA
[6 empty] | A1.5.3 | Individual training and Coaching to improve market access by SMMEs |  |  | ToR were revised so as to combine 5 days market strategy activity with the 5 days sales and distribution strategy. The new budget is now EUR 45,000 for 24 beneficiaries. |  |  | . | NA
[6 empty] | A1.5.4 | Mentoring in Agro to support SMMEs |  |  | Tender being prepared. Expert expected to have been procured from mid-February to early March 2016. Activity to begin in mid April and run until August. ToRs are still awaiting input from the Ministry of Agriculture. |  |  | . | NA
[6 empty] | A1.5.5 | Individual coaching and mentoring of SMMEs and CBOs in Tourism sector |  |  | ToRs ready and tender being prepared. Expert expected to have been procured from mid-February to early March 2016. Activity to begin in mid April and run until August. |  |  | . | NA
[6 empty] | A1.5.6 | Site visits to SMMEs to evaluate progress made |  |  | Questionnaire and selection criteria have been developed. Comments expected from PSDP Coordination Unit by 23rd February 2016. |  |  | . | NA
[6 empty] | A1.5.7 | Human Resource Management, Including Productivity enhancement systems |  |  | This is to be combined with a workshop on environmental awareness. Budget is to be a maximum of EUR 30,000. The Combined terms of reference are still being developed. The start up date will be around mid-May to end of July. |  |  | . | NA
[6 empty] | A1.5.8 | Upgrading service of companies in the Hospitality industry |  |  | Tender dossier was launched on the 2nd of February. The deadline for submission of tender is now 29th February. |  |  | . | NA
IND 1.6 | NA | NA | At least four (4) SMMEs are assisted in quality standards and certification is obtained by August 2016 |  |  | A 1.6 | Capacity Building of SMME's for Quality Standards and Certification
[6 empty] | A1.6.1 | Training and mentoring of SMMEs on Standards and Certification Processes | Simplified tender sent out to consultants on 05/02/16. The deadline of submission for this tender is the 5th of March. This activity is expected to commence on 8th of March to 30th July 2016. |  |  |  |  | . | NA | NA
[6 empty] | A1.6.2 | Facilitation of SMMEs to acquire BoBs Certification | The activity is expected to start on 1st July to 30th September 2016. The budget is still to be determined because it is going to be a contributory budget : SMMEs will pay half. |  |  |  |  | . | NA
IND 1.7 | NA | NA | Thirty (30) micro-enterprises and Community Based Organizations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance and mentoring by October 2016. |  |  | A.1.7 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A.1.7.1 | Strengthening of SMME’s and CBOs through the development of competent Human Resources and facilitating access to markets through information and communication. | Group training in Business Plan |  | To be noted: Procurement processes experiencing delays as a result of change in procedures from CDE to EDF rules. File sent to the BB CEO and awaiting authorisation. One Contract has been signed with service provider on the 5th of February. Tentative dates for training beneficiaries from the south are: 29/02-05/03 and for beneficiaries from the north, the training is from: 21st March to 25th March 2016 |  |  | . | NA | NA
[8 empty] | Mentoring of micro enterprises in Finance and Accounting |  | This will also include Group training in Management Finance. The maximum budget is 40,000. Tender expected to be launched on 11th of February. |  |  | . | NA
IND 1.8 | NA | NA | Forty (40) SMMEs and CBOs have participated in environmental awareness activities by September 2015. |  |  | A.1.8 | Participation of SMMEs in Environmental Awareness
[6 empty] | A1.8.1 | A workshop to be conducted on Environmental awareness. | One day workshop to be incorporated with human resources training. |  |  |  |  | . | NA | NA
IND 1.9 | 2.1 | MS | Five (5) interns are placed at enterprises by March 2016. |  |  | A1.9 | Placement of Interns
[6 empty] | A1.9.1 | Collaborate with the National Internship Department on the provision of Interns to PSDP Beneficiaries | ToRs prepared. National Internship office has been contacted and were supportive of the idea. Enterprise are to be contacted. Activity on-going. |  |  |  |  | . | 2.1 | MS
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
. | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
1 | A 1.1.1Seven (7) Value Chains with respective action plans in seven (7) sub sectors are validated and realization of opportunities identified with lead organizations by October 201 |  |  | 3.5 | It is noted that the technical guides, while related to the activity, actually go beyond the scope of the experts deliverables. This activity was effectively completed under CDE and is now undergoing the final stages before the file can be decommited. This is the same for activity A1.1.2.
2 | A 1.2.3 Assistance to the Botswana National Beef Producers Union |  |  | NA | There has been an observed delay in this activity due to communication difficulties between the Ministry of Agriculture and the PSDP coordinating unit. It should however be noted that the work plan from the coordination unit has not yet provided dates about when this is to commence.
3 | A1.5.2 Provisions of finance and management coaching by Local Experts SMMEs and CBOs - North, |  |  | NA | With respect to the the budget has been increased to EUR 30,000 because a workshop has also been incorporated as part of the activity, before the mentorship programme begins.
4 | A1.5.3 Individual training and Coaching to improve market access by SMMEs, |  |  | NA | This has been developed as a combination of two activities: 5 days market strategy activity and the 5 days sales and distribution strategy. The reason for combining these events is rooted in the change from CDE to EDF rules. Under CDE rules, the ceiling for individual tenders for consultants was EUR 30,000. Under the EDF rules, the ceiling is EUR 20,000. Instead of having numerous individual activities that are less than EUR 20,000, the PSDP Coordinating Unit has seen it fit to combine these smaller activities so that they become multiple, instead of individual tenders, thereby transcending the problem of the low ceiling. It is also administratively more efficient to deal with these activities in this manner.
5 | A1.5.7 Human Resource Management, Including Productivity enhancement systems |  |  | NA | This activity is to incorporate the workshop on environmental awareness (under A1.8.1), with a maximum budget of EUR 30,000.
6 | A1.6.2 Facilitation of SMMEs to acquire BoBs Certification |  |  | NA | The budget for this activity is still to be determined because it will be a contributory budget in which the SMMEs pay half.
7 | A1.7.1 Strengthening of SMME’s and CBOs through the development of competent Human Resources and facilitating access to markets through information and communication. |  |  | NA | In terms of Group Training in Business Plan, it is to be noted that only one contract out of multiple trainings has been signed, and on this basis, it is more appropriate to award a score of NA. In terms of Mentoring of micro enterprises in Finance and Accounting, the activity is now to be combined with Group Training in Management Finance. The new maximum budget is now EUR 40,000.
8 | A1.8.1 A workshop to be conducted on Environmental awareness. |  |  | NA | This Indicator ought to be removed as it has been subsumed under another activity elsewhere.
9 | Multiple activities |  |  | . | It is to be noted that with many of the activities, procurement processes were experiencing delays as a result of change in procedures from CDE to EDF rules.