## Result Area 2
Result Area Activity Monitoring Report (Summary) : 12th February 2016
RESULT AREA 2: | [12 empty] | Sub- Activity Score | Score | Rating Code
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced. | [12 empty] | . | . | .
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 2.1 | 3 | MS | BB is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 5%. |  |  | A 2.1 | Restructuring of BB
[6 empty] | A 2.1.1 | Engagement of International Experts and local consultants who will collaborate on developing BB as an Apex body structure | Two existing files are opened for the coaching of a local service provider, but this activity is still to be resumed. There has been communication with the International Expert seeking their views on the proposed ToRs, which should be in concert with the EDF rules. |  |  |  |  | . | NA | NA
[6 empty] | A2 .1.2 | Local Expert engaged to work with BB in the implementation of a new governance structure. | This activity is linked to the above one. An international expert will work with local one, but activities are separated because it is a separate contract. The expert has now been engaged for a shorter period with a more focused scope, with two or three deliverables removed from the ToRs. This has also led to a reduction in the budget for the implementation of this activity. The implementation has started and the consultants office has been secured. The inception report is expected by 12.02.16. . The local expert has begun working with the international consultant. |  |  |  |  | . | 3 | MS
IND 2.2 | 4.5 | S | BB is fully capacitated on Web based M&E system by Dec 2015 |  |  | A2.2 | Capacity Building of BB
[6 empty] | A2.2.1 | Internal Monitoring and Evaluation of PSDP | M&E system has been established and is running smoothly at BB. The Particip final report has been submitted and approved. |  |  |  |  | . | 4.5 | S
IND 2.3 | NA | NA | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs – October 2016. |  |  | A2.3 | Establishment of Web-based Market Intelligence System
[6 empty] | A2.3.1 | Recruitment of an International Expert to work with BB to Develop the MIS | ToRs have been developed but activity to be launched in February. Process currently delayed by adaptation to EDF rules. |  |  |  |  | . | NA | NA
IND 2.4 | NA | NA | Curriculum on export development promotion is developed for BITC by June 2016. |  |  | A2.4 | Export Development Curriculum
[6 empty] | A2.4.1 | Develop and pilot courses in accordance with the National Qualification Framework prescribed by BQA. | The process has been delayed due to the new EDF rules and its awaiting an expert to be engaged. A meeting has taken place with BITC who is to provide feedback on which approach they will undertake. |  |  |  |  | . | NA | NA
IND 2.5 | NA | NA | BITC and clients with export potential are trained on export to regional and international markets by August 2016. |  |  | A2.5 | Support to BITC on Export Markets
[6 empty] | A2.5.1 | Adapt existing tools or develop new tools for improving service delivery of BITC to its clients (due diligence and audits of SMEs, Botswana export products and services, etc.) | This activity was meant to be undertaken under the same budget as A2.4.1. BITC have expressed that the EUR 35,000 budget is insufficient to undertake both A2.4.1 and A2.5.1 and as such this activity cannot be completed. |  |  |  |  | . | NA | NA
IND 2.6 | NA | NA | At least one (1) MoU with IO is signed by October 2016. |  |  | A.2.6 | MoU signed with IOs
[6 empty] | A2.6.1 | Engage different IOs on how they can partner with PSDP to Assist SMMEs | Bilateral Meeting with IOs pending and are expected to take place in March 2016. |  |  |  |  | . | NA | NA
IND 2.7 | 3.1 | S | Local capacity of at least one (1) community trust to manage a heritage site by October 2016. |  |  | A.2.7 | Capacity Building of community Trusts
[6 empty] | A2.7.1 | Capacity building and skills development for the Tsodilo Community Trust Members | The following courses were examined from 25th to 29th of January 2016: Bookkeeping & Accounting; HR; Employee Relations; FO; Safari Guide; F&B Service; F&B Production; Computer Skills / Excel; Customer Service / Guest Relations. Small Business Management has been completed and graded already as this initiative was carried out on site in Tsodilo during November 2016. What is left is the final report and an article to be produced in 15 February. A total of 11 people undertook the exam, who were doing two to three courses at a time. |  |  |  |  | . | 3.1 | S
IND 2.8 | 3 | MS | At least one (1) new cultural tourism product is developed by June 2016. |  |  | A 2.8 | Development of New Cultural Tourism Products
[6 empty] | A2.8.1 | Branding and Marketing of the Tsodilo World Heritage Site | The following documents have been received and are currently under review: Tsodilo Hills Proposition and Experience; Tsodilo Hills Experience Development Action Plan; Tsodilo Hills Marketing and Communications Plan. The expert is expected to come for a third mission as two have already been completed. The workshop for this mission has been rescheduled to the week of the 15th - 17th Feb . Contract was extended to 28th of February. |  |  |  |  | . | 3 | MS
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
. | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
1 | A2.1.2 Local Expert engaged to work with BB in the implementation of a new governance structure. |  |  | 3 | In this activity, the expert has now been engaged for a shorter period characterised by a more focused scope, with two or three deliverables removed from the ToRs. This has also led to a reduction in the budget for the implementation of this activity.
2 | A2.3.1 Recruitment of an International Expert to work with BB to Develop the MIS |  |  | NA | The rolling out of this activity has been delayed due to adaptation to the new EDF rules.
3 | A2.4.1 Develop and pilot courses in accordance with the National Qualification Framework prescribed by BQA. |  |  | NA | While a meeting has taken place with BITC, the process was delayed by the adaptation to the new EDF rules.
4 | A2.5.1 Adapt existing tools or develop new tools for improving service delivery of BITC to its clients (due diligence and audits of SMEs, Botswana export products and services, etc.) |  |  | NA | BITC have expressed that the EUR 35,000 budget is insufficient to undertake both A2.4.1 and A2.5.1 and as such this activity cannot be completed.