## Result Area 3
Result Area Activity Monitoring Report (Summary) : 12th February 2016
RESULT AREA 3: | [12 empty] | Sub- Activity Score | Score | Rating Code
Information dissemination and awareness for trade agreements enhanced | [12 empty] | . | . | .
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 3.1 | NA | NA | At least ten (10) NSA is trained in implementation of trade agreement by June 2016 |  |  | A3.1 | Training of NSAs in implementation of Trade Agreements
[6 empty] | A3.1.1 | Capacity building of NSAs on trade issues including the implementation of Economic Partnership Agreement | Activity is expected to be initiated in April 2016. |  |  |  |  | . | NA | NA
IND 3.2 | NA | NA | Two (2) workshops are conducted on international trade opportunities by June 2016 |  |  | A3.2 | Workshops on International Trade Opportunities
[6 empty] | A.3.2.1 | Capacity building of NSAs on the implementation of Economic Partnership Agreement | Activity is expected to be initiated in April 2016. |  |  |  |  | . | NA | NA
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
3 | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
. | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
. | . |  |  | . | .