## Overall Summary
Monitoring and Evaluation Report (Summary) : 31st March 2016
Result Area / Component | [5 empty] | Rating | Rating Code | Remarks on Significant Achievements
RESULT AREA 1: CAPACITY AND COMPETITIVENESS OF SMME’S AND COMMUNITY BASED ORGANISATION (CBOS) INCLUDING VALUE CHAINS IS STRENGTHENED | [5 empty] | 2.6 | MS | This Result Area is starting to pick up in terms of activities being rolled out. It was possible to rate the overall activity, despite the fact that some of the activities, particularly relating to the strengthening of SMMEs in management operations, are still awaiting commencement. A number of activities have been rolled out and are going according to schedule. Some activities however were rated moderately unsatisfactory which affected the final score. Thus for example, with the upgrading service of companies in the Hospitality industry, the service provider identified by the programme did not sit well with HATAB (whose members are the main beneficiaries of the intervention), and as such, the procurement process here experienced delays. Another example is the Mentoring of micro enterprises in Finance and Accounting (A1.7.1), in which the activity had not been committed on time and in goign forward, procedures for informing the tender committee about evaluation sittings will have to be formalised in order to avoid delays. The same observation is also made for A1.5.3 (Individual training and Coaching to improve market access by SMMEs).
RESULT AREA 2: SERVICE DELIVERY OF TARGETED INTERMEDIARY ORGANISATIONS (IOs) AND BUSINESS DEVELOPMENT SERVICE PROVIDERS (BDSPs) IS ENHANCED | [5 empty] | 3.1 | S | Under this result area, there have been a number of improvements in a number of activities under the various indicators. Under A2.1.1 (Engagement of International Experts and local consultants who will collaborate on developing BB as an Apex body structure), the international experts have been procured and have begun their work. These experts are working hand in hand with the local expert under activity A2.1.2 (Local Expert engaged to work with BB in the implementation of a new governance structure). As well, it is noted that Business Botswana Public Relations Unit will be implementing the activity to develop the Market Intelligence Information System so as to promote the sustainability of the intervention within the organisation. The activities relating to the capacity building and skills development for the Tsodilo Community Trust Members (A2.7.1) and the Branding and marketing of the Tsodilo World Heritage Site, A2.8.1, have both been completed. With regard to A2.4.1, (Adapt existing tools or develop new tools for improving service delivery of BITC to its clients), having initially expressed that there EUR 35,000 budget was not enough to implement both this activity and A2.4.1 (Develop and pilot courses in accordance with the National Qualification Framework prescribed by BQA), BITC are preparing an official note to seek further assistance from the programme, following a budget review.
RESULT AREA 3: INFORMATION DISSEMINATION AND AWARENESS FOR TRADE AGREEMENTS ENHANCED | [5 empty] | 3 | MS | The Activities in this result area are expected to be initiated in May 2016. The service provider has been identified before the 31st of March and the contract is set to be signed within the first week of April.Following a meeting with MTI Trade Department and EU delegation, three workshops on International Trade opportunities are foreseen. The emphasis will be on the EPA. Training is foreseen to take place in Gaborone, Francistown and Maun. This is in preparation for the signing of the EPA in June 2016.
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY | [5 empty] | 5 | HS | No Change visible as compared to previous report
4< HS <=5 | . | 3< S <=4 | . | 2< MS <=3 | . | 1< MU <=2 | . | 0< U <=1 | . | HU =0 | . | .