## Progressive
Performance of each Log Frame Indicator Progressive Quarter Wise (Summary) 31st March 2016
.
Result Area One :Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Feb 2016 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016
Ind 1.1 | Seven (7) Value Chains with respective action plans in seven (7) sub sectors are validated and realization of opportunities identified with lead organizations by October 2016 | S | S | . | . | . | Activities in this indicator have been completed.
Ind 1.2 | Capacity of beef farmers associations in two (2) regions is strengthened in order to be more competitive in the local, regional and international market by October 2016. | NA | MS | . | . | . | Only one activity has been completed which relates to the Upgrading Capacity of Beef farmers Associations. With the Benchmarking mission to UK, a service provider has been identified who has already started some antecedent work leading up to the visit to the UK. The other two activities are yet to begin. Communication is on-going with the Ministry of Agriculture to ascertain if they are still interested in collaborating with the PSDP Coordination unit, with respect to the assistance to the Botswana National Beef Producers Union (activity A1.2.3).
Ind 1.3 | Capacity of at least one (1) honey and morula association is strengthened and at least four (4) beekeeping experts are trained by June 2016. | S | S | . | . | . | The indicator has one activity in which the final report has been submitted and final payments are being processed.
Ind 1.4 | Two (2) raw material supply chain study are carried out with respective action plans for honey and morula CBOs and SMMEs are developed and validated by October 2016. | NA | NA* | . | . | . | The sole activity in this indicator is yet to commence and has been moved to a later date due to the fact that the identified expert is still winding down another activity (Assistance to Associations and experts to enable them to become more structured).
Ind 1.5 | At least 70 SMMEs are strengthened on management, operations in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by October 2016. | NA | NA* | . | . | . | There are eight activities under this indicator. Preparatory work has begun in four of them, which attracted moderately satisfactory ratings in A1.5.1 and A1.5.2 and moderately unsatisfactory ratings with respect to A1.5.3 - where procedures for informing the tender committee about evaluation sittings will have to be formalised in order to avoid delays - and A1.5.8. where progress in the activity was stalled due to the fact that HATAB were not happy with the chose service provider.
Ind 1.6 | At least four (4) SMMEs are assisted in quality standards and certification is obtained by August 2016. | NA | NA* | . | . | . | There are two activities in this indicator. One activity has already commenced: Training and mentoring of SMMEs on Standards and Certification Processes (A1.6.1). The other activity is yet to commence.
Ind 1.7 | Thirty (30) micro-enterprises and Community Based Organizations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance and mentoring by October 2016. | NA | MS | . | . | . | There are two activities in this indicator. The group training in business plans is going according to plan, however, the Mentoring of micro enterprises in Finance and Accounting did not roll out according to plan, due to the fact that procedures for informing the tender committee about evaluation sittings will have to be formalised in order to avoid delays
Ind 1.8 | Forty (40) SMMEs and CBOs have participated in environmental awareness activities by September 2015. | NA | NA | . | . | . | The sole activity in this indicator was subsumed under Indicator 1.5 and it is therefore suggested that this indicator is dispensed with.
Ind 1.9 | Five (5) interns are placed at enterprises by March 2016. | MS | MS | . | . | . | There is one activity under this indicator which is on-going. The National Internship office has been contacted and the various beneficiary enterprises are also to be contacted.
Result Area Two: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced.
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Feb 2016 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016
Ind 2.1 | BB is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 5%. | MS | MS | . | . | . | An international expert has been procured and has started working with the local one.
Ind 2.2 | BB is fully capacitated on Web based M&E system by Dec 2015. | S | S | . | . | . | M&E system has been established and is running smoothly at BB.
Ind 2.3 | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs – October 2016. | NA | MS | . | . | . | The sole activity in this indicator is on-going. A note received from BB has indicated that BB Public Relations department will implement activity which also promotes sustainability.
Ind 2.4 | Curriculum on export development promotion is developed for BITC by June 2016. | NA | NA | . | . | . | The tender dossier is under preparation for a competitive bid.
Ind 2.5 | BITC and clients with export potential are trained on export to regional and international markets by August 2016. | NA | NA | . | . | . | BITC have expressed that the EUR 35,000 which was set aside to undertake activities in both Ind 2.4 and Ind 2.5 was not enough. BITC are to prepare an official note to seek additional assistance.
Ind 2.6 | At least one (1) MoU with IO is signed by October 2016. | NA | MU | . | . | . | Bilateral Meeting with IOs are pending and were expected to take place in March 2016. This has not yet occurred.
Ind 2.7 | Local capacity of at least one (1) community trust to manage a heritage site by October 2016. | S | S | . | . | . | The sole activity in this indicator has been completed. The final report has been submitted and payment is being processed.
Ind 2.8 | At least one (1) new cultural tourism product is developed by June 2016. | MS | S | . | . | . | There is an improvement from the last report in that the Final report for the sole activity in this indicator has been submitted, reviewed and has been approved. Final payment is being processed.
Result Area Three: Information Dissemination and Awareness For Trade Agreements Enhanced
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Feb 2016 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016
Ind 3.1 | At least ten (10) NSA is trained in implementation of trade agreement by June 2016 | NA | MS | . | . | . | With this Indicator, the service provider has been identified before the 31st of March and the contract is set to be signed within the first week of April.
Ind 3.2 | Two (2) workshops are conducted on international trade opportunities by June 2016 | NA | MS | . | . | . | With this Indicator, the service provider has been identified before the 31st of March and the contract is set to be signed within the first week of April.
Component Four: Management and Communications
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Feb 2016 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016
NA | Performance Management and Communications | HS | HS | . | . | . | Dialogue Sachi and Sachi contract extended to June 2016. M&E system established and running smoothly. Indicator doing well for this quarter.
NA | Not Applicable | . | . | . | . | . | . | . | NA | Not Due to Start
HS | 4< HS <=5 | S | 3< S <=4 |  |  | MS | 2< MS <=3 |  | MU | 1< MU <=2
U | 0< U <=1 | HU | HU =0 |  |  | . | . | . | . | .