## Result Area 1
Result Area Activity Monitoring Report (Summary) : 31st March 2016
RESULT AREA 1: | [12 empty] | Sub- Activity Score | Score | Rating Code
Capacity and competitiveness of SMMEs and Community Based Organisations (CBOs) including value chains is strengthened. | [13 empty] | 2.6 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 1.1 | 3.5 | S | Seven (7) Value Chains with respective action plans in seven (7) sub sectors are validated and realization of opportunities identified with lead organizations by October 2016 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Tourism value chain has been finalised with the Report completed. Technical guides have been developed and are completed, although this goes beyond the deliverables of the contract. |  |  |  |  | . | 3.5 | S
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | This activity has been completed and payment is being processed. Technical guides have been developed and are completed, although this goes beyond the deliverables of the contract. |  |  |  |  | . | 3.5 | S
IND 1.2 | 2.75 | MS | Capacity of beef farmers associations in two (2) regions is strengthened in order to be more competitive in the local, regional and international market by October 2016. |  |  | A 1.2 | Capacity Building of Beef Farmers Associations
[6 empty] | A 1.2.1 | Upgrading Capacity of Beef farmers Associations | The regions in question are Ghazi and Ngami land. The Farmers association invited an Irish association (ICSA) to capacitate them under an activity financed by PSDP. The assistance was geared at making the local associations run their operations more effectively. These associations are in operation and lobbying for their members. The activity and payment have completed and the activity has now been closed. |  |  |  |  | . | 4 | S
[6 empty] | A1.2.2 | A select number of commercial beef farmers will be taken on a benchmarking mission to UK | There is an agricultural Show to the UK entitled "Royal III Counties" expected to commence from the 17th to the 19th of June. ToRs have been developed and a single offer made to service provider. |  |  |  |  | . | NA | NA
[6 empty] | A1.2.3 | Assistance to the Botswana National Beef Producers Union | Activity had not yet begun due to the fact that the Ministry of Agriculture had not yet provided information that is pertinent to its commencement. While the ToRs have been received, the PSDP Coordination Unit has raised concerns about the sustainability of some of the terms. A letter has been drafted to the Ministry of Agriculture to see if they are still interested in undertaking the activity with PSDP. This comes against the backdrop of a change of personnel at the Ministry of Agriculture. |  |  |  |  | . | 1.5 | MU
IND 1.3 | 4 | S | Capacity of at least one (1) honey and morula association is strengthened and at least four (4) beekeeping experts are trained by June 2016. |  |  | A1.3 | Wild / Natural Product Capacity Building
[6 empty] | A1.3.1 | Assistance to Associations and experts to enable them to become more structured | The activity was carried over from CDE. The consultant has forwarded the final report and copies of the business plan have been worked on with the beekeeping associations, as well as draft article for news letter. The Honey technical guides are now being finalised with the beekeeping expert. Final payment is being processed. |  |  |  |  | . | 4 | S
IND 1.4 | NA | NA | Two (2) raw material supply chain study are carried out with respective action plans for honey and morula CBOs and SMMEs are developed and validated by October 2016. |  |  | A1.4 | Raw Material Supply Chain Studies
[6 empty] | A1.4.1 | Development of action plans for honey and morula CBOs and SMMEs | Tender is to be launched during April. The expert who was to be engaged was winding down another activity (Assistance to Associations and experts to enable them to become more structured). As such an updated work plan is needed on this activity. |  |  |  |  | . | NA | NA
IND 1.5 | NA | NA | At least 70 SMMEs are strengthened on management, operations in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by October 2016. |  |  | A 1.5 | Strengthening of SMMEs on Management Operations
[6 empty] | A1.5.1 | Business Plan Preparation (Quality Control) |  |  | The Expert expected to have been procured by March 2016, however, this tender had not yet been launched by 1st April 2016 as per the work plan. The Coordination Unit explained that this activity has to follow the workshop on business planning which has been deferred to accommodate the availability of beneficiaries. |  |  | . | NA | NA
[6 empty] | A1.5.2 | Provisions of finance and management coaching by Local Experts SMMEs and CBOs - North |  |  | Contractor has been awarded the tender for this activity. The file has now been committed. The Activity is expected to have began by 1st April to 30th June. The budget is 31,100 to include workshops in the course of the training. |  |  | . | 2.5 | MS
[6 empty] | A1.5.3 | Individual training and Coaching to improve market access by SMMEs |  |  | ToR were revised so as to combine 5 days market strategy activity with the 5 days sales and distribution strategy. The new budget is now EUR 45,000 for 24 beneficiaries. This file has not yet been committed due to the fact that the tender evaluation committee members were informed about the sitting but the nominated institutions requested official nomination request letters, and this has delayed the process. |  |  | . | 1.5 | MU
[6 empty] | A1.5.4 | Mentoring in Agro to support SMMEs |  |  | Tender being prepared. Expert expected to have been procured in April 2016. Activity to begin in May and run until August. ToRs have been finalised. |  |  | . | NA | NA
[6 empty] | A1.5.5 | Individual coaching and mentoring of SMMEs and CBOs in Tourism sector |  |  | ToRs ready and tender being prepared. Expert expected to have been procured from mid-February to early March 2016. Activity to begin in mid April and run until August. |  |  | . | NA | NA
[6 empty] | A1.5.6 | Site visits to SMMEs to evaluate progress made |  |  | PSDP Coordination Unit to commence site visits towards the end of April. |  |  | . | NA | NA
[6 empty] | A1.5.7 | Human Resource Management, Including Productivity enhancement systems |  |  | This is to be combined with a workshop on environmental awareness. Budget is to be a maximum of EUR 30,000. The Combined terms of reference are still being developed. The start up date will be around mid-May to end of July. |  |  | . | NA | NA
[6 empty] | A1.5.8 | Upgrading service of companies in the Hospitality industry |  |  | One contractor has sent in a submission on 26.02.15. one service provider has withdrawn from the process from the original three. Evaluation meeting to be set for 10th March 2016. This activity was targeting HATAB members. At the moment, HATAB not happy with service provider. A meeting is to be carried out with HATAB by the Coordinating Unit and an update to be obtained there after. |  |  | . | 1.5 | MU
IND 1.6 | NA | NA | At least four (4) SMMEs are assisted in quality standards and certification is obtained by August 2016 |  |  | A 1.6 | Capacity Building of SMME's for Quality Standards and Certification
[6 empty] | A1.6.1 | Training and mentoring of SMMEs on Standards and Certification Processes | This activity is expected to commence from March to July 2016. A proposal from the consultant has been received and preparations for rolling out the intervention are underway. Meeting with consultant held and a start up and planning workshop has been scheduled with the beneficiaries. File has been committed and activity has begun. A project commencement letter was dispensed dated 10th March and on the 15th March 2016, a project initiation workshop was held. The activity is on-going. |  |  |  |  | . | 2.5 | MS
[6 empty] | A1.6.2 | Facilitation of SMMEs to acquire BoBs Certification | The activity is expected to start on 1st July to 30th September 2016. The budget is still to be determined because it is going to be a contributory budget : SMMEs will pay half. |  |  |  |  | . | NA | NA
IND 1.7 | 1.75 | MU | Thirty (30) micro-enterprises and Community Based Organizations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance and mentoring by October 2016. |  |  | A.1.7 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A.1.7.1 | Strengthening of SMME’s and CBOs through the development of competent Human Resources and facilitating access to markets through information and communication. | Group training in Business Plan |  | One Contract has been signed with service provider on the 5th of February. Tentative dates for training beneficiaries from the south are: 11/04/16-15/04/16 and for beneficiaries from the north, the training is from: 04/04/16-08/04/16 . Initial payment has been processed. |  |  | 2.9 | 2.2 | MS
[8 empty] | Mentoring of micro enterprises in Finance and Accounting |  | This will also include Group training in Management Finance. The maximum budget is 40,000. Tender was expected to be evaluated by 30th March 2016. This file has not yet been committed due to the fact that the tender evaluation committee members were informed about the sitting but the nominated institutions requested official nomination request letter, and this has delayed the process. This had not been undertaken in an official manner. |  |  | 1.5
IND 1.8 | NA | NA | Forty (40) SMMEs and CBOs have participated in environmental awareness activities by September 2015. |  |  | A.1.8 | Participation of SMMEs in Environmental Awareness
[6 empty] | A1.8.1 | A workshop to be conducted on Environmental awareness. | One day workshop to be incorporated with human resources training. |  |  |  |  | . | NA | NA
IND 1.9 | 2.1 | MS | Five (5) interns are placed at enterprises by March 2016. |  |  | A1.9 | Placement of Interns
[6 empty] | A1.9.1 | Collaborate with the National Internship Department on the provision of Interns to PSDP Beneficiaries | ToRs prepared. National Internship office has been contacted and were supportive of the idea. Enterprise are to be contacted. Activity on-going. |  |  |  |  | . | 2.1 | MS
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
. | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
1 | A 1.1.1Seven (7) Value Chains with respective action plans in seven (7) sub sectors are validated and realization of opportunities identified with lead organizations by October 201 |  |  | 3.5 | It is noted that the technical guides, while related to the activity, actually go beyond the scope of the experts deliverables. This activity was effectively completed under CDE and is now undergoing the final stages before the file can be decommited. This is the same for activity A1.1.2.
2 | A 1.2.3 Assistance to the Botswana National Beef Producers Union |  |  | 1.5 | This activity is rated as moderately unsatisfactory due to the fact that there has been a persistent delay brought about by the cumbersome communication between the PSDP Coordinating Unit and the Ministry of Agriculture. As well, there is still no work plan that has been provided to show when this activity is expected to be rolled out. In the mean time, the PSDP Coordination Unit has drafted a letter to the Ministry seeking clarity on whether they will be interested in collaborating on rolling out this activity.
3 | A 1.4.1 Development of action plans for honey and morula CBOs and SMMEs |  |  | NA | The expert who was to be engaged was winding down another activity (Assistance to Associations and experts to enable them to become more structured). As such an alert is issued that an updated work plan is needed on this activity.
3 | A1.5.2 Provisions of finance and management coaching by Local Experts SMMEs and CBOs - North, |  |  | 2.5 | This activity attracts a score of moderately satisfactory. Contractor has been awarded the tender for this activity. The file has now been committed. The Activity is expected to have began by 1st April to 30th June.
4 | A1.5.3 Individual training and Coaching to improve market access by SMMEs, |  |  | 1.5 | This file has not yet been committed due to the fact that the tender evaluation committee members were informed about the sitting but the nominated institutions requested official nomination request letter. It seems that there has hitherto been no formal request accompanying the selection of the tender committee, resulting in a delay of the process. As such, the activity attracts a score of moderately unsatisfactory. In going forward, it is recommended that these formal procedures should be adopted between the PSDP Coordinating Unit and the Tender Committee.
5 | A1.5.7 Human Resource Management, Including Productivity enhancement systems |  |  | NA | This activity is to incorporate the workshop on environmental awareness (under A1.8.1), with a maximum budget of EUR 30,000. In going forward it may be beneficial to ensure that the Management Committee gives a formal approval for the merging of activities and budgets, because this has implications on the planning of the activity and the monitoring aspect of it as well.
6 | A1.5.8 Upgrading service of companies in the Hospitality industry |  |  | 1.5 | This activity has been rated as moderately unsatisfactory because the tender evaluation committee were meant to meet by on 10th March 2016. However, owing to a dissatisfaction of HATAB members with the chosen Service provider, there has been a delay in the process. When the issue is resolved. the rating will change.
6 | A1.6.2 Facilitation of SMMEs to acquire BoBs Certification |  |  | NA | The budget for this activity is still to be determined because it will be a contributory budget in which the SMMEs pay half.
7 | A1.7.1 Strengthening of SMME’s and CBOs through the development of competent Human Resources and facilitating access to markets through information and communication. |  |  | 1.75 | In terms of Group Training in Business Plan, it is to be noted that only one contract out of multiple trainings has been signed, and on this basis, it is more appropriate to award a score of NA. In terms of Mentoring of micro enterprises in Finance and Accounting, the activity is now to be combined with Group Training in Management Finance. The new maximum budget is now EUR 40,000. The activity was rated moderately unsatisfactory because the file had not been committed by 30th March 2016. It seems that there has hitherto been no formal request accompanying the selection of the tender committee, resulting in a delay of the process. In going forward, it is recommended that these formal procedures should be adopted between the PSDP Coordinating Unit and the Tender Committee.
8 | A1.8.1 A workshop to be conducted on Environmental awareness. |  |  | NA | This Indicator ought to be removed as it has been subsumed under another activity elsewhere.