## Result Area 3
Result Area Activity Monitoring Report (Summary) : 31st March 2016
RESULT AREA 3: | [12 empty] | Sub- Activity Score | Score | Rating Code
Information dissemination and awareness for trade agreements enhanced | [12 empty] | . | 3 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 3.1 | 3 | MS | At least ten (10) NSA is trained in implementation of trade agreement by June 2016 |  |  | A3.1 | Training of NSAs in implementation of Trade Agreements
[6 empty] | A3.1.1 | Capacity building of NSAs on trade issues including the implementation of Economic Partnership Agreement | Activity is expected to be initiated in April 2016. Following a meeting with MTI trade department and EU delegation, three workshops on International Trade opportunities are foreseen. Emphasis will be on the EPA. EU delegation has proposed dates between 23 and 24 May in Gaborone. other trainings foreseen in Francistown and Maun. This is in preparation for the signing of the EPA in June 2016. Tender dossier now under preparation. |  |  |  |  | . | 3 | MS
IND 3.2 | 3 | MS | Two (2) workshops are conducted on international trade opportunities by June 2016 |  |  | A3.2 | Workshops on International Trade Opportunities
[6 empty] | A.3.2.1 | Capacity building of NSAs on the implementation of Economic Partnership Agreement | Activity is expected to be initiated in April 2016. Following a meeting with MTI trade department and EU delegation, three workshops on International Trade opportunities are foreseen. Emphasis will be on the EPA. EU delegation has proposed dates between 23 and 24 May in Gaborone. other trainings foreseen in Francistown and Maun. This is in preparation for the signing of the EPA in June 2016. Tender dossier now under preparation. |  |  |  |  | . | 3 | MS
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
3 | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
. | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
. | . |  |  | . | .