## Overall Summary
Monitoring and Evaluation Report (Summary) : 23rd May 2016
Result Area / Component | [5 empty] | Rating | Rating Code | Remarks on Significant Achievements
RESULT AREA 1: CAPACITY AND COMPETITIVENESS OF SMME’S AND COMMUNITY BASED ORGANISATION (CBOS) INCLUDING VALUE CHAINS IS STRENGTHENED | [5 empty] | 2.5 | MS | The overall rating for this Result Area dropped by 1 point from the last Quarter. More activities have begun to show some progress and have improved to MU. These include the following: i) the Assistance to the Botswana Beef Producers Union – in which a focal person within the MoA has been identified and MoA is now cooperating; ii) Provisions of finance and management coaching by Local Experts SMMEs and CBOs – North, Individual training and Coaching to improve market access by SMMEs; iii) Group training in Business Plan – where the training for beneficiaries from the North and South have been completed; iv) work has also begun in the Mentoring of micro enterprises in Finance and Accounting with meetings held in Francistown and Maun. There are however concerns related to a number of activities under the indicator to strengthen SMME management operations. Thus for example, the rolling out of Mentoring in Agro to support SMMEs and Individual coaching and mentoring of SMMEs and CBOs in Tourism sector have both been delayed by a month. A delay was also experienced with the Human Resource Management, Including Productivity enhancement systems and this is due to the fact that the MC had reservations about combining the activity with the Environmental awareness workshops.
RESULT AREA 2: SERVICE DELIVERY OF TARGETED INTERMEDIARY ORGANISATIONS (IOs) AND BUSINESS DEVELOPMENT SERVICE PROVIDERS (BDSPs) IS ENHANCED | [5 empty] | 2.7 | MS | The rating for this result area has dropped from a rating of 3.1 (Satisfactory) to a rating of 2.7 (Moderately Satisfactory). This has been primarily caused by a downgrade in the activity to adapt existing tools or develop new tools for improving service delivery of BITC to its clients. The activity is in the logframe, but yet there is no budget to implement it. On the other hand, there has been some excellent work conducted with respect to the activity to restructure BB and an interim report has been produced. The local expert will continue to work towards the final product. There has also been progress on the activity relating to the market intelligence system, with six service providers identified to tender. In terms of the activity to have an MoU singed with IOs, a stakeholder meeting was to be held 25th May 2016 which shows some progress towards achieving the result. The activities relating to the Tsodilo World Heritage Site and the Trust Members have both been completed satisfactorily.
RESULT AREA 3: INFORMATION DISSEMINATION AND AWARENESS FOR TRADE AGREEMENTS ENHANCED | [5 empty] | 3.1 | S | This Result Area is doing rather well and has improved from Moderately Satisfactory to Satisfactory. Following a meeting with MTI Trade Department and EU Delegation, three workshops on International Trade opportunities were planned. The Emphasis was on the upcoming signing of the EPA in June. Two workshops have been held in Francistown and in Maun. The reports for these are under preparation. Another workshop was also to be held in Gaborone on 24/05/2016.
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY | [5 empty] | 5 | HS | No Change visible as compared to previous report
4< HS <=5 | . | 3< S <=4 | . | 2< MS <=3 | . | 1< MU <=2 | . | 0< U <=1 | . | HU =0 | . | .