## Progressive
Performance of each Log Frame Indicator Progressive Quarter Wise (Summary) 23rd May 2016
.
Result Area One :Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Feb 2016 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016
Ind 1.1 | Seven (7) Value Chains with respective action plans in seven (7) sub sectors are validated and realization of opportunities identified with lead organizations by October 2016 | S | S | S | . | . | Activities in this indicator have been completed.
Ind 1.2 | Capacity of beef farmers associations in two (2) regions is strengthened in order to be more competitive in the local, regional and international market by October 2016. | NA | MS | MS | . | . | Only one activity has been completed which relates to the Upgrading Capacity of Beef farmers Associations. With the Benchmarking mission to UK, a service provider has been identified who has already started some antecedent work leading up to the visit to the UK. With respect to the assistance to the Botswana National Beef Producers Union, the activity has started to show progress.
Ind 1.3 | Capacity of at least one (1) honey and morula association is strengthened and at least four (4) beekeeping experts are trained by June 2016. | S | S | S | . | . | The indicator has one activity in which the final report has been submitted and final payments completed.
Ind 1.4 | Two (2) raw material supply chain study are carried out with respective action plans for honey and morula CBOs and SMMEs are developed and validated by October 2016. | NA | NA* | NA* | . | . | The sole activity in this indicator is yet to commence and has been moved to a later date due to the fact that the identified expert is still winding down another activity (Assistance to Associations and experts to enable them to become more structured).
Ind 1.5 | At least 70 SMMEs are strengthened on management, operations in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by October 2016. | NA | NA* | MU | . | . | There are a number of activities under this indicator. Two activities (Provisions of finance and management coaching and Individual training and Coaching to improve market access) have begun and are now on-going. Site visits to SMMEs have been conducted, however there were some delays in rolling out activities, for example with the Mentoring in Agro to support SMMEs; Human Resource Management, Including Productivity enhancement systems; and Individual coaching and mentoring in the Tourism sector.
Ind 1.6 | At least four (4) SMMEs are assisted in quality standards and certification is obtained by August 2016. | NA | NA* | NA* | . | . | There are two activities in this indicator. One activity has already commenced: Training and mentoring of SMMEs on Standards and Certification Processes (A1.6.1). The other activity is yet to commence.
Ind 1.7 | Thirty (30) micro-enterprises and Community Based Organizations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance and mentoring by October 2016. | NA | MS | MS | . | . | There are two activities in this indicator. The group training in business plans has been completed. The Mentoring of micro enterprises in Finance and Accounting has also begun and is now an on-going activity.
Ind 1.8 | Forty (40) SMMEs and CBOs have participated in environmental awareness activities by September 2015. | NA | NA | NA | . | . | The sole activity under this indicator is yet to commence.
Ind 1.9 | Five (5) interns are placed at enterprises by March 2016. | MS | MS | MS | . | . | There is one activity under this indicator. There has been official contact between the CU and Internship office. There is an indication that special dispensation might be given to BB because they are an NGO.
Result Area Two: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced.
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Feb 2016 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016
Ind 2.1 | BB is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 5%. | MS | MS | S | . | . | International expert were procured and they worked with the local expert and an Interim report has been produced.
Ind 2.2 | BB is fully capacitated on Web based M&E system by Dec 2015. | S | S | S | . | . | M&E system has been established and is running smoothly at BB.
Ind 2.3 | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs – October 2016. | NA | MS | MS | . | . | The sole activity in this indicator is on-going. A note received from BB has indicated that BB Public Relations department will implement activity which also promotes sustainability. Service providers have been identified invtied to tender
Ind 2.4 | Curriculum on export development promotion is developed for BITC by June 2016. | NA | NA | NA | . | . | The tender for the activity in this indicator was launced. Service providers invited to tender.
Ind 2.5 | BITC and clients with export potential are trained on export to regional and international markets by August 2016. | NA | NA | U | . | . | No progress has been made on this indicator. The activity is in the programme logframe but there is no budget to implement it.
Ind 2.6 | At least one (1) MoU with IO is signed by October 2016. | NA | MU | MS | . | . | Stakeholder meeting with IOs to take place on 25/05/2016.
Ind 2.7 | Local capacity of at least one (1) community trust to manage a heritage site by October 2016. | S | S | S | . | . | The sole activity in this indicator has been completed and the file closed.
Ind 2.8 | At least one (1) new cultural tourism product is developed by June 2016. | MS | S | S | . | . | The sole activity in this indicator has been completed and the file closed.
Result Area Three: Information Dissemination and Awareness For Trade Agreements Enhanced
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Feb 2016 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016
Ind 3.1 | At least ten (10) NSA is trained in implementation of trade agreement by June 2016 | NA | MS | S | . | . | Two workshops have taken place in Francistown and Maun. One workshop pending in Gaborone
Ind 3.2 | Two (2) workshops are conducted on international trade opportunities by June 2016 | NA | MS | S | . | . | Two workshops have taken place in Francistown and Maun. One workshop pending in Gaborone
Component Four: Management and Communications
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes |  |  |  |  | Remarks
|  | Feb 2016 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016
NA | Performance Management and Communications | HS | HS | HS | . | . | Dialogue Sachi and Sachi contract extended to June 2016. M&E system established and running smoothly. Indicator doing well for this quarter.
NA | Not Applicable | . | . | . | . | . | . | . | NA | Not Due to Start
HS | 4< HS <=5 | S | 3< S <=4 |  |  | MS | 2< MS <=3 |  | MU | 1< MU <=2
U | 0< U <=1 | HU | HU =0 |  |  | . | . | . | . | .