## Result Area 2
Result Area Activity Monitoring Report (Summary) : 23rd May 2016
RESULT AREA 2: | [12 empty] | Sub- Activity Score | Score | Rating Code
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced. | [12 empty] | . | 2.6875 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 2.1 | 3.1 | S | BB is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 5%. |  |  | A 2.1 | Restructuring of BB
[6 empty] | A 2.1.1 | Engagement of International Experts and local consultants who will collaborate on developing BB as an Apex body structure | Contract has been signed by expert and the inception report submitted to BB Secretariat for adoption. The mission dates were from 3rd to 6th May 2016. There were two experts procured with experience of chambers of commerce having worked at Paris Chambers and Belgium Chambers. The experts work on a subscription model for BB and also met with BB Staff and Associaitons. Their report has been completed and they are expected to return in August after the local expert's engagment has been completed. |  |  |  |  | . | 3.1 | S
[6 empty] | A2 .1.2 | Local Expert engaged to work with BB in the implementation of a new governance structure. | This activity is linked to the above one. An international expert worked with a local one, but activities are separated because it is a separate contract. The inception report and interim reports have been submited. The local expert has also held meetings with associations (HATAB, Chambers of Commerce and other associations for BB). Expert has updated the BB Constitution for comments such that it can be registered. The activity is on-going. |  |  |  |  | . | 3.1 | S
IND 2.2 | 3.5 | S | BB is fully capacitated on Web based M&E system by Dec 2015 |  |  | A2.2 | Capacity Building of BB
[6 empty] | A2.2.1 | Internal Monitoring and Evaluation of PSDP | M&E system has been established and is running smoothly at BB. The Particip final report has been submitted and approved. |  |  |  |  | . | 3.5 | S
IND 2.3 | 2.1 | MS | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs – October 2016. |  |  | A2.3 | Establishment of Web-based Market Intelligence System
[6 empty] | A2.3.1 | Recruitment of an International Expert to work with BB to Develop the MIS | This activity is on-going. A note received from BB has indicated that BB Public Relations department will implement activity which also promotes sustainability. The market intellignece tender was launced, and the deadline is 3rd June 2016. 6 service providers were invited to tender. |  |  |  |  | . | 2.1 | MS
IND 2.4 | NA | NA | Curriculum on export development promotion is developed for BITC by June 2016. |  |  | A2.4 | Export Development Curriculum
[6 empty] | A2.4.1 | Develop and pilot courses in accordance with the National Qualification Framework prescribed by BQA. | The tender for this activity (competitive bid) was launced. 3 service providers invited to tender. |  |  |  |  | . | NA | NA
IND 2.5 | 1 | U | BITC and clients with export potential are trained on export to regional and international markets by August 2016. |  |  | A2.5 | Support to BITC on Export Markets
[6 empty] | A2.5.1 | Adapt existing tools or develop new tools for improving service delivery of BITC to its clients (due diligence and audits of SMEs, Botswana export products and services, etc.) | This activity was meant to be undertaken under the same budget as A2.4.1. BITC have expressed that the EUR 35,000 budget is insufficient to undertake both A2.4.1 and A2.5.1 and as such this activity cannot be completed. BITC were meant to prepare an official note to seek additional assistance from the programme. No progress has been made as we head into the last month of the second qaurter of the year. |  |  |  |  | . | 1 | U
IND 2.6 | 2.1 | MS | At least one (1) MoU with IO is signed by October 2016. |  |  | A.2.6 | MoU signed with IOs
[6 empty] | A2.6.1 | Engage different IOs on how they can partner with PSDP to Assist SMMEs | Bilateral Meeting with IOs pending and were expected to take place in March 2016. Stakeholder meeting is to be held 25th May 2016 which will involve a discussion of the MoU which should culminate in those interested parties signing, |  |  |  |  | . | 2.1 | MS
IND 2.7 | 3.1 | S | Local capacity of at least one (1) community trust to manage a heritage site by October 2016. |  |  | A.2.7 | Capacity Building of community Trusts
[6 empty] | A2.7.1 | Capacity building and skills development for the Tsodilo Community Trust Members | The following courses were examined from 25th to 29th of January 2016: Bookkeeping & Accounting; HR; Employee Relations; FO; Safari Guide; F&B Service; F&B Production; Computer Skills / Excel; Customer Service / Guest Relations. Small Business Management has been completed and graded already as this initiative was carried out on site in Tsodilo during November 2016. What is left is the final report and an article to be produced in 15 February. A total of 11 people undertook the exam, who were doing two to three courses at a time. Second draft of the final report received and approved. Final payment finalised and file closed. |  |  |  |  | . | 3.1 | S
IND 2.8 | 3.5 | S | At least one (1) new cultural tourism product is developed by June 2016. |  |  | A 2.8 | Development of New Cultural Tourism Products
[6 empty] | A2.8.1 | Branding and Marketing of the Tsodilo World Heritage Site | Final reports been submitted, reviewed and has been approved. Final payment has been completed and file has been closed. |  |  |  |  | . | 3.5 | S
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
. | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
1 | A2.1.1 Engagement of International Experts and local consultants who will collaborate on developing BB as an Apex body structure |  |  | 3.1 | Two internartional experts with experience of chambers of commerce having worked at Paris Chambers and Belgium Chambers were procured and worked with the local expert. This phase of the activity was completed and an interim report was submited. As such, the activity attracted a score of Satisfactory.
2 | A2.1.2 Local Expert engaged to work with BB in the implementation of a new governance structure. |  |  | 3.1 | This activity is linked to the above one. International experts worked with a local one, but activities are separated because it is a separate contract. The inception report and interim reports have been submited. The local expert has also held meetings with associations (HATAB, Chambers of Commerce and other associations for BB). Expert has updated the BB Constitution for comments such that it can be registered. The activity is on-going. The activity is ongoing and has attracted a satisfactory score for the quarter.
3 | A2.3.1 Recruitment of an International Expert to work with BB to Develop the MIS |  |  | 2.1 | This activity is on-going. A note received from BB has indicated that BB Public Relations department will implement the activity which will also promote sustainability. An alert is issued to the effect that 6 service providers have been invited to tender for this activity. The activity attracts a rating of moderately satisfactory.
4 | A2.3.1 Recruitment of an International Expert to work with BB to Develop the MIS |  |  | NA | The tender for this activity (competitive bid) was launced. 3 service providers invited to tender. As soon as a contractor is identified and the acitivity commences, the score will be adjusted accordingly.
5 | A2.5.1 Adapt existing tools or develop new tools for improving service delivery of BITC to its clients (due diligence and audits of SMEs, Botswana export products and services, etc.) |  |  | 1 | This activity was meant to be undertaken under the same budget as A2.4.1. BITC have expressed that the EUR 35,000 budget is insufficient to undertake both A2.4.1 and A2.5.1 and as such this activity cannot be completed. BITC were meant to prepare an official note to seek additional assistance from the programme. The activity has made no progress since the last quarter and is now rated as unsatisfactory. The activity is in the logframe yet therre is no budget for it.
6 | A2.6.1 Engage different IOs on how they can partner with PSDP to Assist SMMEs |  |  | 2.1 | The activity is now moderately satisfactory. Stakeholder meeting is to be held 25th May 2016 which will involve a discussion of the MoU which should culminate in those interested parties signing it. When the stakeholder meetigns have been completed, and the MoU has been signed, the score will accordingly be adjusted.