## Result Area 3
Result Area Activity Monitoring Report (Summary) : 23rd May 2016
RESULT AREA 3: | [12 empty] | Sub- Activity Score | Score | Rating Code
Information dissemination and awareness for trade agreements enhanced | [12 empty] | . | 3.1 | S
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 3.1 | 3.1 | S | At least ten (10) NSA is trained in implementation of trade agreement by June 2016 |  |  | A3.1 | Training of NSAs in implementation of Trade Agreements
[6 empty] | A3.1.1 | Capacity building of NSAs on trade issues including the implementation of Economic Partnership Agreement | Following a meeting with MTI Trade Department and EU Delegation, three workshops on International Trade opportunities were planned. The Emphasis was on the upcoming signing of the EPA in June. Two workshops have been held in Francistown (09/05/2016) with over 40 participants and in Maun (17/05/16) with over 50 participants. The reports for these are under preparation. |  |  |  |  | . | 3.1 | S
IND 3.2 | 3.1 | S | Two (2) workshops are conducted on international trade opportunities by June 2016 |  |  | A3.2 | Workshops on International Trade Opportunities
[6 empty] | A.3.2.1 | Capacity building of NSAs on the implementation of Economic Partnership Agreement | Following a meeting with MTI Trade Department and EU Delegation, three workshops on International Trade opportunities were planned. The Emphasis was on the upcoming signing of the EPA in June. Two workshops have been held in Francistown (09/05/2016) with over 40 participants and in Maun (17/05/16) with over 50 participants. The reports for these are under preparation. |  |  |  |  | . | 3.1 | S
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
3 | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
. | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
1 | A3.1.1 Capacity building of NSAs on trade issues including the implementation of Economic Partnership Agreement |  |  | 3.1 | The Emphasis odf these workshops was on the upcoming signing of the EPA in June. Two workshops have been held in Francistown (09/05/2016) with over 40 participants and in Maun (17/05/16) with over 50 participants. The reports for these are under preparation. A workshop in Gaborone was still to take place on 24/05/2016. When all the workshops are complete and the reports are all available, then the score will accordingly be adjusted.
2 | A3.2.1 Capacity building of NSAs on the implementation of Economic Partnership Agreemen |  |  | 3.1 | The Emphasis odf these workshops was on the upcoming signing of the EPA in June. Two workshops have been held in Francistown (09/05/2016) with over 40 participants and in Maun (17/05/16) with over 50 participants. The reports for these are under preparation. A workshop in Gaborone was still to take place on 24/05/2016. When all the workshops are complete and the reports are all available, then the score will accordingly be adjusted.