## Result Area 1
Result Area Activity Monitoring Report (Summary) : Quarter Ending 30 June 2015
RESULT AREA 1: | [8 empty] | Sub- Activity Score | Score | Rating Code
CAPACITY AND COMPETITIVENESS OF SMMEs AND COMMUNITY BASED ORGANISATION (CBO'S) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [8 empty] | . | 2.96 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  | . | Score | Rating Code
IND 1.1 | 3 | MS | Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 |  | A 1.1 | Value Chains Analysis and Development
[5 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Projects on Beef Completed and the final VC report submitted October 2014. Pursuant to the action plans of the report and the recommendations made, three action items are being implemented. (1) Management tools for Commercial Farmers (2) Upgrading capacity of Farmers Association. (3) Technical Tools of graduating communal Farmers. Horticulture and tourism in progress. The Horticulture report has been received and is now under review (18 June 2015). Tourism VCAD: received and currently under review (26 June 2015). Reports have been distributed to the stakeholders. |  | . | 3 | MS
[5 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | All Five Final reports submitted by the consultant and have been reviewed by CDE as of 25 February 2015. Reformatted final report received by PSDP for comments to the consultants by 5 April 2015. Feedback on new report format submitted to HCL, 10 April 2015. Follow up to be made on final submission of all reports. Comments provided to HCL by 22 April 2015. An organisation for implementing action plans will be identified in October 2015. |  | . | 3 | MS
IND 1.2 | 2 | MU | Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014. |  | A 1.2 | Value Added wild / Natural Product Opportunity Study
[5 empty] | A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | Action plan for Honey submitted and Morula being finalised. Reports received and approved. Final Payment being processed. Honey Technical Guide under evaluation (follow up actions). Secondary actions based on recommendations to be elaborated. Recruitment of Honey Expert to assist SMMEs and CBOs under review. No progress on Morula. Field missions have been completed. Recruitment of Honey Expert to assist SMMEs and CBOs under review. Contract submitted for approval. It is expected that capacity building and implementation of action plans from the report will begin in September 2015. |  | . | 2 | MU
IND 1.3 | 4 | S | At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015. |  | A 1.3 | SME's Diagnostics (Baseline studies)
[5 empty] | A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | Team for the Diagnosis of SMMEs (BWP 1410/01) | Team leader final report complete and submitted. What remains are administrative actions by the PSDP unit. | 4 | 4 | S
[7 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) | Local Consultants completed 22 SMMEs out of a total of ___22_SMME's. What remains is administrative work to be completed by PSDP. | 4
[7 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) | BNPC completed 28 out of _28 SMMEs. What remains is administrative work to be completed by PSDP. | 4
[7 empty] | SMME Diagnosis by BIH (BWP/1417/01)) | BIH Completed 15 out of 15 SMME's. What remains is administrative work to be completed by PSDP. | 4
[7 empty] | SMME Diagnostics by LEA (BWP/1430/01) | LEA completed 9 SMME's including 2 CBO's. What remains is administrative work to be completed by PSDP. | 4
[7 empty] | SMME Diagnostics by CEDA (BWP/1430/01) | CEDA Completed 10/10 SMME's by 31st January 2015. What remains is administrative work to be completed by PSDP. | 4
[7 empty] | Monitoring the SMME Audit Process (BWP/1439/01) | Capacity Building of local staff on SMME Diagnostics File completed and closed | 4
[7 empty] | PSDP Mission Logistics (BWP/1404/01 | This entailed a provisional budget to cover SMME site visits by the PSDP team. The site visit reports have been completed and made available . This will then be able to trigger an evaluation from the M&E team. | 4
[7 empty] | SMME Diagnostics for Micros (File Number Requested) | These were completed. Interventions have started in which they will be attending workshops and they will also get mentors. | 4
IND 1.3 Cont.. | 4 Cont.. | S | Cont… |  | A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[5 empty] | A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | Support to poultry sector (BWP 1444/01) | File de-committed due to the fact that the action was cancelled. No clear explanation as to why this was the case has been forthcoming. However, the poultry companies are being assisted with some attending Occupational Safety and Health Training, Business Management Training and TBT Certification (work in progress). | . | 2.25 | MS
[7 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) | Progress made in that all consultants have begun their missions and the activity is on-going. Arrangements under way for ICT, Bakery and Poultry expert trips, foreseen in June-July Time frame. ICT expert expected 2 July 2015 – 25 July. | 3
IND 1.4 | 2.25 | MS | At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015 |  |  |  | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) | Progress made: Consultants have begun their missions and the activity is on-going. Economarkets to commence local support, following introduction meetings. Contracting on-going for local consultant support. Third expert identified, with possible start-up of October 2015. The first such intervention began in March and a number of similar interventions are on-going. Any evaluation on impact could reasonably be done from September. | 3
[7 empty] | Group training in management Finance (BWP 1446/01) | TOR and budget finalized. Selection and PA to be finalised. It is difficult to measure the extent of progress in the absence of a definite date for the group training. | 2
[7 empty] | Management training for Micros and CBOs | First training has been completed from 15th to 26th june 2015 and the next is scheduled for August 2015 | 2
[7 empty] | Group training in Business Planning for SMEs | TOR and budget finalized. Follow up PA. Budget approved. Contract being drafted for approval and signature. It is difficult to measure the extent of the progress in the absence of a definite date for the group training. ? | 2
[7 empty] | ?a?r?t?i?c?i?p?a?t?i?o?n? ?o?f? ?S?M?M?E?s? ?t?o? ?t?r?a?d?e? ?m?i?s?s?i?o?n?s? ?&? ?t?r?a?i?n?i?n?g?s?.? ?I?n? ?t?e?r?m?s? ?o?f? ?t?r?a?d?e? ?m?i?s?s?i?o?n?s? ?a?n?d? ?t?r?a?i?n?i?n?g? ?t?h?e? ?f?i?l?e? ?n?u?m?b?e?r? ?h?a?s? ?s?t?i?l?l? ?n?o?t? ?b?e?e?n? | b?t?a?i?n?e?d? ?s?i?n?c?e? ?t?h?e? ?l?a?s?t? ?r?e?p?o?r?t??T?O?R? ?a?n?d? ?b?u?d?g?e?t? ?t?o? ?b?e? ?p?r?e?p?a?r?e?d?.? ?A?g?a?i?n?,? ?i?t? ?i?s? ?d?i?f?f?i?c?u?l?t? ?t?o? ?m?e?a?s?u?r?e? ?t?h?e? ?e?x?t?e?n?t? ?o?f? ?t?h?e? ?p?r?o?g?r?e?s?s? ?i?n? ?t?h?e? ?a?b?s?e?n?c?e? ?o?f? ?a? ?d?e?f?i?n?i?t?e? ?d?a?t?e? ?f?o?r? ?t?h?e? ?g?r?o?u?p? ?t?r?a?i?n?i?n?g?.? ?I?n?d?i?v?i?d?u?a?l? ?C?o?a?c?h?i?n?g? ?o?f? ?S?M?M?E?s? ? A?c?t?i?v?i?t?y? ?u?n?d?e?r? ?p?r?e?p?a?r?a?t?i?o?n?.? ?R?e?q?u?e?s?t? ?f?i?l?e? ?n?u?m?b?e?r?.? ?F?i?n?a?n?c?i?a?l? ?o?f?f?e?r? ?a?n?d? ?d?o?c?u?m?e?n?t?a?t?i?o?n? ?t?o? ?b?e? ?s?u?b?m?i?t?t?e?d? ?1?3?t?h? ?A?p?r?i?l? ?2?0?1?5? ?f?o?r? ?c?o?m?m?i?t?m?e?n?t?.? ?T?h?e?r?e? ?i?s? ?a? ?r?e?l?a?t?i?o?n?s?h?i?p? ?t?h?a?t? ?h?a?s? ?b?e?e?n? ?e?s?t?a?b?l?i?s?h?e?d? ?w?i?t?h? ?a? ?f?e?w? ?o?r?g?a?n?i?s?a?t?i?o?n?s? ?t?h?a?t? ?o?f?f?e?r? ?e?x?p?e?r?t? ?s?e?r?v?i?c?e?s?.? ?T?h?e? ?d?e?l?a?y?s? ?a?r?e? ?d?u?e? ?t?o? ?a?d?m?i?n?i?s?t?r?a?t?i?v?e? ?c?o?n?s?t?r?a?i?n?t?s?.? ??S?M?E? ?D?e?v?e?l?o?p?m?e?n?t? ?E?x?p?e?r?t?s? ?<?A?c?t?i?v?i?t?y? ?u?n?d?e?r? ?p?r?e?p?a?r?a?t?i?o?n?.? ?F?i?l?e? ?n?u?m?b?e?r? ?r?e?q?u?e?s?t? ?i?s? ?o?n?-?g?o?i?n?g? ??I?N?D? ?1?.?5?[?6?0? ?S?M?M?E?s? ?a?n?d? ?C?B?O?s? ?h?a?v?e? ?p?a?r?t?i?c?i?p?a?t?e?d? ?i?n? ?e?n?v?i?r?o?n?m?e?n?t?a?l? ?a?w?a?r?e?n?e?s?s? ?a?c?t?i?v?i?t?i?e?s? ?b?y? ?D?e?c?e?m?b?e?r? ?2?0?1?5?.??A?1?.?5?*?T?e?c?h?n?i?c?a?l? ?A?d?v?i?s?o?r?s? ?a?n?d? ?s?h?o?r?t? ?t?e?r?m? ?E?x?p?e?r?t?s? ??A?.?1?.?5?.?1?1?T?e?c?h?n?i?c?a?l? ?a?d?v?i?s?o?r? ?i?n? ?A?g?r?o? ?i?n?d?u?s?t?r?y? ?(?B?O?T?/?1?4?0?1?/?0?1?)? ??F?i?n?a?l? ?r?e?p?o?r?t? ?s?u?b?m?i?t?t?e?d?.? ?F?i?l?e? ?c?l?o?s?e?d?.? ?T?h?i?s? ?a?d?v?i?s?o?r? ?i?s? ?i?n? ?r?e?l?a?t?i?o?n? ?t?o? ?A?1?.?1?.?1? ? ?w?h?i?c?h? ?a?c?t?i?o?n? ?i?s? ?t?a?k?i?n?g? ?p?l?a?c?e? ?o?n? ?t?h?e? ?r?e?c?o?m?m?e?n?d?a?t?i?o?n?s? ?o?f? ?t?h?i?s? ?r?e?p?o?r?t?.? ?M?S?e?r?v?i?c?e? ?P?r?o?v?i?d?e?r? ?f?o?r? ?a?s?s?i?s?t?a?n?c?e? ?i?n? ?c?o?n?s?t?r?u?c?t?i?o?n? ?a?n?d? ?p?u?b?l?i?c? ?w?o?r?k?s? ?(?B?W?P?1?4?3?1?/?0?1?)?:I?n?c?e?p?t?i?o?n? ?R?e?p?o?r?t? ?s?u?b?m?i?t?t?e?d?.? ?F?i?l?e? ?n?u?m?b?e?r? ?r?e?q?u?e?s?t?e?d?,? ?a?w?a?i?t?i?n?g? ?p?r?o?f?i?l?e? ?o?f? ?s?e?r?v?i?c?e? ?p?r?o?v?i?d?e?r?.? ? ?M?o?d?u?l?e?s? ?f?o?r? ?w?o?r?k?s?h?o?p? ?s?e?s?s?i?o?n?s? ?h?a?v?e? ?b?e?e?n? ?a?p?p?r?o?v?e?d?,? ?w?o?r?k?s?h?o?p? ?c?o?m?p?l?e?t?e?d? ?f?r?o?m? ?1?5?t?h? ?J?u?n?e? ?t?o? ?1?9?t?h? ?J?u?n?e? ?2?0?1?5?.? ?W?o?r?k?s?h?o?p? ?r?e?p?o?r?t? ?a?n?d? ?S?u?n?d?a?y? ?S?t?a?n?d?a?r?d? ?a?r?t?i?c?l?e? ?u?n?d?e?r? ?p?r?e?p?a?r?a?t?i?o?n?.? ?A? ?t?r?a?i?n?i?n?g? ?r?e?p?o?r?t? ?i?s? ?e?x?p?e?c?t?e?d? ?b?e?f?o?r?e? ?t?h?e? ?e?n?d? ?o?f? ?J?u?l?y? ?2?0?1?5?.?G?S?e?r?v?i?c?e? ?P?r?o?v?i?d?e?r? ?f?o?r? ?a?s?s?i?s?t?a?n?c?e? ?t?o? ?c?l?e?a?n? ?e?n?e?r?g?y? ?c?o?m?p?a?n?i?e?s? ?(?B?W?P?/?1?4?2?6?/?0?1?)?dF?i?n?a?l? ?r?e?p?o?r?t? ?w?a?s? ?s?u?b?m?i?t?t?e?d? ?i?n? ?M?a?r?c?h? ?2?0?1?5?a?n?d? ?t?h?e? ?f?i?l?e? ?h?a?s? ?b?e?e?n? ?c?l?o?s?e?d? ?w?e?l?l? ?b?e?f?o?r?e? ?t?h?e? ?c?o?n?t?r?a?c?t? ?d?a?t?e? ?l?a?p?s?e?d?.? ?T?h?e? ?s?e?r?v?i?c?e? ?c?o?n?s?i?s?t?e?d? ?o?f? ?t?h?r?e?e? ?m?i?s?s?i?o?n?s?:? ?1?)? ?C?a?p?a?c?i?t?y? ?n?e?e?d?s? ?a?s?s?e?s?s?m?e?n?t? ?o?f? ?8? ?S?M?M?E?s?,? ?2?)? ?P?l?a?n?t? ?A?s?s?e?s?s?m?e?n?t?s? ?a?n?d? ?B?u?s?i?n?e?s?s? ?P?l?a?n?s?,? ?3?)? ?F?e?e?d?b?a?c?k? ?M?e?e?t?i?n?g?s? ?a?n?d? ?A?c?t?i?o?n? ?P?l?a?n?s?.? ?A?n? ?a?w?a?r?e?n?e?s?s? ?t?r?a?i?n?i?n?g? ?w?o?r?k?s?h?o?p? ?w?a?s? ?a?l?s?o? ?c?o?n?d?u?c?t?e?d? ?f?o?r? ?1?9? ?e?n?t?e?r?p?r?i?s?e?s? ?o?n? ?5?t?h? ?M?a?r?c?h? ?2?0?1?5?.?\?S?h?o?r?t?-?t?e?r?m? ?E?x?p?e?r?t?s? ?(?P?S?D?P? ?s?u?p?p?o?r?t? ?s?t?a?f?f?)? ?B?W?P?/?1?3?0?5?/?0?1?,? ? ?B?W?P?/?1?4?0?7?/?0?1?,? ?B?W?P?/?1?3?1?1?/?0?1?,? ?B?W?P?/?1?4?4?2?/?0?1? ?Ð?S?u?p?p?o?r?t? ?t?o? ?P?S?D?P? ?j?u?n?i?o?r? ?e?x?p?e?r?t?s? ?a?n?d? ?i?n?t?e?r?n?s?.? ?T?h?e? ?f?o?l?l?o?w?i?n?g? ?f?i?l?e?s? ?h?a?v?e? ?b?e?e?n? ?c?l?o?s?e?d? ?(?B?W?P?/?1?3?0?5?/?0?1?,? ?B?W?P?/?1?4?0?7?/?0?1?,? ?B?W?P?/?1?3?1?1?/?0?1?)?.? ?T?h?e? ?o?n?l?y? ?a?c?t?i?v?e? ?f?i?l?e? ?i?s? ?B?W?P?/?1?4?4?2?/?0?1? ?w?h?i?c?h? ?i?s? ?t?h?e? ?p?a?y?m?e?n?t? ?o?f? ?P?S?D?P? ?e?x?p?e?r?t?s? ?a?n?d? ?I?n?t?e?r?n?s?.? ??H?S? ? ?4?<? ?H?S? ?<?=?5??3?<? ?S? ?<?=?4? ?2?<? ?M? ?S?<?=?3? ?1?<? ?M?U? ?<?=?2??U??0?<? ?U? ?<?=?1??H?U??H?U? ?=?0??N?A??N?o?t? ?D?u?e? ?t?o? ?S?t?a?r?t?P?J?u?s?t?i?f?i?c?a?t?i?o?n? ?F?o?r? ?A?c?t?i?v?i?t?i?e?s? ?G?r?a?d?e?d? ?H?i?g?h?l?y? ?S?a?t?i?s?f?a?c?t?o?r?y? ?o?r? ?H?i?g?h?l?y? ?U?n?s?a?t?i?s?f?a?c?t?o?r?y??S?.? ?N?o?!?N?a?m?e? ?o?f? ?A?c?t?i?v?i?t?y? ?A?w?a?r?d?e?d? ?H?S? ?o?r? ?H?U??R?a?t?i?n?g? ?J?u?s?t?i?f?i?c?a?t?i?o?n? ?f?o?r? ?E?x?t?r?e?m?e? ?S?c?o?r?e??N?a?m?e? ?o?f? ?A?c?t?i?v?i?t?y? ?6?A?l?e?r?t? ?/? ?L?e?s?s?o?n?s? ?L?e?a?r?n?t? ?a?n?d? ?S?u?g?g?e?s?t?i?o?n?s? ?f?o?r? ?w?a?y? ?f?o?r?w?a?r?d?[?A?1?.?1?.?1? ? ?S?t?r?u?c?t?u?r?e?d? ?v?a?l?u?e? ?c?h?a?i?n?s? ?a?n?a?l?y?s?i?s? ?a?n?d? ?p?r?e?p?a?r?a?t?i?o?n? ?o?f? ?c?a?p?a?c?i?t?y? ?b?u?i?l?d?i?n?g? ?A?c?t?i?o?n? ?p?l?a?n?s? ? T?h?e? ?c?o?n?t?r?a?c?t? ?e?x?p?i?r?e?s? ?i?n? ?A?u?g?u?s?t? ?2?0?1?5? ?a?n?d? ?i?t? ?w?a?s? ?e?x?p?e?c?t?e?d? ?t?h?a?t? ?t?h?i?s? ?a?c?t?i?v?i?t?y? ?s?h?o?u?l?d? ?h?a?v?e? ?b?e?e?n? ?c?o?m?p?l?e?t?e?d? ?t?w?o? ?m?o?n?t?h?s? ?b?e?f?o?r?e?,? ?w?h?i?c?h? ?i?s? ?i?n? ?J?u?n?e?.? ?T?h?e? ?a?c?t?i?v?i?t?y? ?i?s? ?t?h?u?s? ?r?u?n?n?i?n?g? ?b?e?h?i?n?d? ?s?c?h?e?d?u?l?e? ?b?e?c?a?u?s?e? ?a?c?t?i?o?n? ?i?t?e?m?s? ?a?r?e? ?s?t?i?l?l? ?b?e?i?n?g? ?i?m?p?l?e?m?e?n?t?e?d? ?a?n?d? ?r?e?v?i?e?w?s? ?f?o?r? ?t?h?e? ?r?e?p?o?r?t?s? ?o?n? ?H?o?r?t?i?c?u?l?t?u?r?e? ?a?n?d? ?T?o?u?r?i?s?m? ?V?C?s? ?s?t?i?l?l? ?t?a?k?i?n?g? ?p?l?a?c?e? ?w?i?t?h? ?n?o? ?d?e?a?d?l?i?n?e?s? ?w?h?e?n? ?t?h?e?y? ?w?o?u?l?d? ?b?e? ?c?o?m?p?l?e?t?e?.? ?I?n? ?t?h?e? ?a?b?s?e?n?c?e? ?o?f? ?w?o?r?k?-?p?l?a?n?s?,? ?p?r?o?j?e?c?t?i?n?g? ?t?a?r?g?e?t?s? ?h?a?s? ?p?r?e?s?e?n?t?e?d? ?c?h?a?l?l?e?n?g?e?s? ?f?o?r? ?t?h?e? ?p?r?o?g?r?e?s?s? ?o?f? ?t?h?e? ?a?c?t?i?v?i?t?y? ?a?n?d? ?t?h?e?s?e? ?s?h?o?u?l?d? ?b?e? ?d?e?v?e?l?o?p?e?d? ?a?s? ?a? ?m?a?t?t?e?r? ?o?f? ?p?r?i?o?r?i?t?y?.? ? ?d?A?1?.?1?.?2? ?E?m?e?r?g?i?n?g? ?v?a?l?u?e? ?c?h?a?i?n?s? ?a?n?a?l?y?s?i?s? ?a?n?d? ?p?r?e?p?a?r?a?t?i?o?n? ?o?f? ?c?a?p?a?c?i?t?y? ?b?u?i?l?d?i?n?g? ?A?c?t?i?o?n? ?p?l?a?n?s? ?(?B?W?P?1?3?1?4?/?0?1?)?_T?h?e? ?i?n?t?e?r?n?a?l? ?r?e?v?i?e?w? ?o?f? ?t?h?e? ?r?e?p?o?r?t?s? ?i?s? ?o?n? ?g?o?i?n?g? ?a?n?d? ?t?h?e? ?d?a?t?e?s? ?h?a?v?e? ?b?e?e?n? ?c?h?a?n?g?e?d? ?f?r?o?m? ?M?a?r?c?h? ?t?o? ?A?u?g?u?s?t? ?2?0?1?5?,? ?a?s? ?a? ?r?e?s?u?l?t? ?o?f? ?t?h?e? ?p?o?o?r? ?q?u?a?l?i?t?y? ?o?f? ?t?h?e? ?i?n?i?t?i?a?l? ?r?e?p?o?r?t?.? ?T?h?e? ?p?r?o?j?e?c?t? ?t?o?o?l?s? ?t?h?a?t? ? ?s?h?o?w? ?t?h?e? ?e?x?t?e?n?s?i?o?n?,? ?e?n?d? ?a?n?d? ?c?h?a?n?g?e? ?o?f? ?p?r?o?j?e?c?t? ?a?c?t?i?v?i?t?i?e?s? ?a?n?d? ?p?l?a?n?s? ?s?h?o?u?l?d? ?b?e? ?s?h?a?r?e?d? ?w?i?t?h? ?t?h?e? ?t?e?a?m? ?a?s? ?a? ?w?h?o?l?e? ?s?o? ?a?s? ?t?o? ?a?l?l?o?w? ?f?o?r? ?t?h?e?i?r? ?u?s?e? ?b?y? ?a?l?l? ?r?e?l?e?v?a?n?t? ?P?S?D?P? ?s?t?a?f?f?.? ?T?A?1?.?2?.?1? ?D?e?v?e?l?o?p?m?e?n?t? ?o?f? ?a?c?t?i?o?n? ?p?l?a?n?s? ?f?o?r? ?h?o?n?e?y? ?a?n?d? ?m?o?r?u?l?a? ?C?B?O?s? ?a?n?d? ?S?M?M?E?s? ?(?B?W?P? ?1?4?1?4?/?0?1?)?½?S?o?m?e? ?p?r?o?g?r?e?s?s? ?m?a?d?e?,? ?h?o?w?e?v?e?r? ?t?h?e? ?i?n?d?i?c?a?t?o?r? ?s?c?o?r?e? ?m?u?s?t? ?b?e? ?d?o?w?n?g?r?a?d?e?d? ?t?o? ?M?o?d?e?r?a?t?e?l?y? ?U?n?s?a?t?i?s?f?a?c?t?o?r?y? ?b?e?c?a?u?s?e? ?t?h?e? ?a?c?t?i?v?i?t?y? ?w?a?s? ?m?e?a?n?t? ?t?o? ?b?e? ?c?o?m?p?l?e?t?e?d? ?o?n? ?2?8? ?F?e?b?r?u?a?r?y? ?b?u?t? ?h?a?s? ?n?o?t? ?b?e?e?n? ?c?o?m?p?l?e?t?e?d? ?y?e?t?.?<?A? ?1?.?3?.?1? ? ?D?i?a?g?n?o?s?t?i?c?s? ?o?f? ?S?M?M?E?s? ?(?B?N?P?C?,? ?B?I?H?,? ?L?o?c?a?l? ?c?o?n?s?u?l?t?a?n?t?s?)?î?T?h?e? ?i?n?d?i?c?a?t?o?r? ?s?h?o?u?l?d? ?b?e? ?u?p?g?r?a?d?e?d? ?t?o? ?4? ?d?u?e? ?t?o? ?t?h?e? ?f?a?c?t? ?t?h?a?t? ?r?e?p?o?r?t?s? ?h?a?v?e? ?a?l?l? ?b?e?e?n? ?s?u?b?m?i?t?t?e?d?.? ?A?s? ?w?e?l?l?,? ?a?l?l? ?t?h?e? ?a?u?d?i?t?s? ?h?a?v?e? ?b?e?e?n? ?c?o?m?p?l?e?t?e?d? ?a?n?d? ?t?h?e? ?t?e?a?m? ?l?e?a?d?e?r? ?f?i?l?e? ?h?a?s? ?b?e?e?n closed. Payments for SMMEs (Interim and Final) to be followed up on.P䄁 ㄀⸀㐀⸀㄀ 䌀愀瀀愀挀椀琀礀 䈀甀椀氀搀椀渀最 漀昀 匀䴀䴀䔀✀猀 愀渀搀 䌀䈀伀✀猀 昀漀爀 甀瀀最爀愀搀椀渀最 琀栀攀椀爀 䌀漀洀瀀攀琀椀瘀攀渀攀猀猀嬀ऄWith regards to support to the SMEs by senior experts in service, expert missions have begun and are still on-going. The first such intervention began in March 2015 and a number of similar interventions are on-going. Any evaluation on impact could reasonably be done from September 2015. The score for these sub activity is thus upgraded. With regard to the Technical Support to SMMEs by Managers Without Boarders, the consultants have also begun their missions and the activity is on-going. The sub activity score is thus upgraded. In terms of the group training in management finance, Management training for Micros and CBOs, Group training in Business Planning for SMEs and Participation of SMMEs to trade missions & trainings, it is difficult to measure the extent of the progress in the absence of a definite date for the group training. ??ĠŔ1䄁㄀⸀㔀⸀㄀ 吀攀挀栀渀椀挀愀氀 䄀搀瘀椀猀漀爀猀 愀渀搀 猀栀漀爀琀 琀攀爀洀 䔀砀瀀攀爀琀猀 ਀ăWith the lack of a work-plan specifying the time frame for which the advisory services in the agro industry were to be conducted, it is difficult to assess whether such services were delivered on time. Until such clarity is resolved, then a scoring of satisfactory is appropriate. In terms of the activity pertaining to the Service provider for assistance in Construction and Public Works, the Workshop has taken place on time and the sub activity indicator should be upgraded. With respect to the short term experts support to PSDP staff, payments for BWP/1442/01 are still to be followed up on from the last quarterly report. The sub-activity score should thus receive a moderately satisfactory rating, even though the overall score of the Activity as a whole is satisfactory. | 2
2
2
| 3.5 | S
[9 empty] | 4 | 3.5 | S
3.5
3.5
3
|  | S |  | MS | MU
1 |  |  |  | 3
2 |  |  |  | 3
3 |  |  |  | 3
4 |  |  |  | 4
5 |  |  |  | 2.25
6 |  |  |  | 3.5