## Result Area 3
Result Area Activity Monitoring Report (Summary) :30th June 2015
RESULT AREA 3: | [12 empty] | Score | Rating Code
Business environment (reduction of red tape and pilot on accessing finance) for enterprises is enhanced. | [12 empty] | 4 | S
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity |  |  | Remarks on Significant Achievements |  |  | Score | Rating Code
IND 3.1 | 4 | S | Capacity building conducted on trade and specific negotiation skills • Recommendations submitted by PSDP to MTI on the reduction of; the cost of doing business; and the cost and time required for registration and operationalization of SMMEs in Botswana by June 2015. • Members of the Trade Facilitation and Advisory Group (TFAG) and National Committee on Trade Policy and Negotiations (NCTPN) are trained on MTI Trade Capacity Building Strategy by June 2015. • At least 10 IO staff members are trained in EPA implementation by September 2015 |  |  | A 3.1 | Capacity Building on Trade and Specific Negotiation Skills
[6 empty] | A 3.1.1 | Establish trade facilitation group and provide capacity building (BWP/1314/02) |  |  | Completed and final report submitted |  |  | 4 | S
[6 empty] | A 3.1.2 | Training of TFAG and NTCPN on negotiation and trade facilitation (BWP/1314/02) |  |  | Contract has been awarded for the expert to begin his work. Activity can now be monitored. |  |  | 3.5 | S
[6 empty] | A 3.1.3 | Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation |  |  | Contract has been awarded for the expert to begin his work. Activity can now be monitored. |  |  | 3.5 | S
IND 3.2 | 5 | HS | Improved Policy Framework to access finance • At least 1 new financial product (post loan support mechanism) targeting SMMEs is introduced by commercial banks and or other financial institutions supporting SMME financing by December 2015 • 30 SMME’s under PSDP are assisted to prepare their business plans for submission to commercial banks and other financial institutions by December 2015. • At least 5 PSDP SMMEs assisted are accessing finance by February 2016. • Micro finance policy framework is established and presented to Government for adoption by September 2014. • A microfinance Act is drafted and submitted to government by September 2014. |  |  | A 3.2 | Policy Framework to Improve Access to Finance
[6 empty] | A 3.2.1 | Draft a microfinance policy framework (BWP/1403/01), (BWP/1418/01), (BWP/1415/01) |  |  | Activity completed. Submitted to the Competent Authority in the Government of Botswana |  |  | 5 | HS
[6 empty] | A 3.2.2 | Draft a micro-finance Act for Botswana (BWP/1422/01) |  |  | Legal Expert for Micro Finance Act- Activity pending approval of the framework policy. |  |  | NA | NA
IND 3.3 | 4 | S | Improved Business Environment (Ease of Doing Business) • A compilation of recommendations submitted to MTI by December 2015 to simplify tax registration with a view to improve tax compliance by SMMEs. • A compilation of labour laws affecting SMMEs with recommendations for reforms submitted to MTI by December 2015. |  |  | A 3.3 | Improving Business Environment (Ease of Doing Business)
[6 empty] | A 3.3.1 | Review the registration process and tax compliance |  |  | Contract has been awarded 26 January 2015 to 30 August 2015. Consultants had their first mission between 17-19 March 2015. Having met with key stakeholders, their inception report is expected on 19 April 2015 (Work in Progress). |  |  | 4 | S
[6 empty] | A 3.3.2 | Review of labour laws and recommend labour productivity improvement strategies (BWP/1433/01) |  |  | First mission complete. Activity still awaiting confirmation of dates for the 2nd mission (work in progress). |  |  | 4 | S
. | . | . | . |  |  | . | . |  |  | . |  |  | . | .
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA | NOT APPLICABLE
| Progress or change since last report |  |  | . | .
|  |  | . | . | . | . | . | . | . | . | . | . | . | .
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | A 3.2.1 Draft a microfinance policy framework |  |  | 5 | The draft Policy completed in time and submitted to the relevant authority.
S. No | Name of Activity |  |  | Rating | Alert / Observations, Lessons Learnt and Suggestions for way forward
1 | A 3.1.1. Establish trade facilitation group and provide capacity building. |  |  | 4 | Although the weekly report indicate that the report is completed and final report is submitted, the score should still remain the same due to the fact that there is no indication that the evidence from the report has been accepted by PSDP.
2 | A 3.1.2 Training of TFAG and NTCPN on negotiation and trade facilitation |  |  | 3.5 | There has been some achievement in that the contract has been awarded for the expert to begin his work. Activity can now be monitored.
3 | A 3.1.3 Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation |  |  | 3.5 | There has been some achievement in that the contract has been awarded for the expert to begin his work. Activity can now be monitored.
4 | A 3.2.2. Draft a micro-finance Act for Botswana |  |  | NA | This particular intervention was dropped from the list of activities. This was a decision taken by the MC as it did with the Micro Finance Policy.
6 | A 3.3.2 Review of labour laws and recommend labour productivity improvement strategies. |  |  | 4 | (Work in progress).