## Overall Objective
Overall Pbjective
To contribute to economic growth, employment creation and diversification Resulting in the Reduction of Poverty
INDICATOR | BASELINE | TARGET | STATUS | TIME (YEARS) | OVERALL OBJECTIVE ASSESSMENT | RATING INDICATOR
Annual GDP Growth | 5 | 7 | 6 | 1 | HIGHLY SATISFACTORY | HS
Employment creation | 20000 | 50000 | 25000 | 1 | MODERATELY UNSATISFACTORY | MU
Gross capital formation, private sector (% of GDP) | 35 | 40 | 39 | 1 | HIGHLY SATISFACTORY | HS

## Overall Summary
Monitoring and Evaluation Report (Summary) : 1st January to 28th February
Result Area / Component |  |  | Rating | Rating Code | Remarks on Significant Achievements
RESULT AREA 1: CAPACITY AND COMPETITIVENESS OF SMME’S AND COMMUNITY BASED ORGANISATION (CBOS) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS |  |  | 1.6 | MU | There has not been much change in this resuly area. There are alerts and observations that have been made which if not attended to, might affect the rating.
RESULT AREA 2: SERVICE DELIVERY OF TARGETED INTERMEDIARY ORGANISATIONS (IOs) AND BUSINESS DEVELOPMENT SERVICE PROVIDERS (BDSP) IS ENHANCED |  |  | 2.6 | MS | Very Little change has beenseen in this area, hence the rating remains as it was last year
RESULT AREA 3: BUSINESS ENVIRONMENT FOR ENTERPRISES IS IMPROVED (REDUCTION OF RED TAPE AND PILOT ON IMPROVED ACCESS TO FINANCE BY SMMEs) |  |  | 3.2 | S | No Change from the last report.
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY |  |  | 5 | HS | No Change visible as compared to previous report
4< HS <=5 | 3< S <=4 | 2< MS <=3 | 1< MU <=2 |  | 0< U <=1 | HU =0

## Progressive
Performance of each Log Frame Indicator Progressive Quarter Wise (Summary) December 2014 with Interin Report for 28th February 2015
Result Area One :Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 1.1 | Action plans to support SMMEs and IOs are developed foe eight valuchains and eight sub sectors by February 2015 | NA | S | S | . | . | . | . | . | .
Ind 1.2 | Studies are carried out for development of Honey and Morula Value Chains by September 2014. | HU | MU | MS | . | . | . | . | . | .
Ind 1.3 | At least 70 SMMEs are strengthened on management, operations by December 2015. | MS | MS | MU | . | . | . | . | . | Some activities that are now due to start have not done so well hence the grading has gone down
Ind 1.4 | 30 CBO’s are trained on management, marketing, quality standards and accounting by December 2015 | NA | NA | HU | . | . | . | . | . | Some activities that are now due to start have not done so well hence the grading has gone down In This case A 1.4.1 which contributes partly to this Log Frame Indicator has fallen to 0 from NA
Ind 1.5 | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. | NA | NA | HU | . | . | . | . | . | same as above
Result Area Two: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Log Frame Indicator Number | Description of the Log frame Indicator | HU: Progressive Rating codes; .: Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 2.1 | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana and M&E is Operational by December 2014 | MU | S | S | . | . | . | . | . | .
Ind 2.2 | A web based market intelligence information system is developed for use by SMMEs - June 2015. | U | MS | MS | . | . | . | . | . | .
Ind 2.3 | Capacity building of BITC is conducted by December 2015 | NA | NA | U | . | . | . | . | . | Activity A 2.2.1 and A 2.2.2 should have started by now but have not so well and they fell from NA to 1 and this caused Log Frame Indicator 2.3 to fall from NA to 1
Ind 2.4 | Capacity building of CBO's and IO's is conducted by December 2015 | NA | MS | MS | . | . | . | . |  | .
Ind 2.5 | Capacity building of BOBS is conducted by December 2015 | bar: HU to .
Result Area Three: Business environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Log Frame Indicator Number | Description of the Log frame Indicator | HU: Progressive Rating codes; .: Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 3.1 | Capacity building conducted on trade and specific negotiation skills | NA | S | S | . | . | . | . | . | .
Ind 3.2 | Improved Policy Framework to access finance | NA | HS | MS | . | . | . | . | . | This Log frame indicator has two contributors A 3.2.1 and A 3.2.2 where as the first is over the second is now due and has not moved as planned thus this was downgraded to 0 Hence the fall in the Rating for Ind 3.2
Ind 3.3 | Improved Business Environment (Ease of Doing Business) | NA | NA | MS | . | . | . | . | . | The contributors to this log frame Indicator are A 3.3.1 and are now due to start and are at MS level hence this fall in rating
Component Four: Management and Communications
Log Frame Indicator Number | Description of the Log frame Indicator | NA: Progressive Rating codes | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
NOTA | Performance Management and Communications | MS | HS | HS | . | . | . | . | . | .
. | bar: HS to .
NOTA | Not Applicable | [8 empty] | Not Due to Start | bar: NA to .
HS | 4< HS <=5 | S | 3< S <=4 |  |  | MS | 2< MS <=3 |  | MU | 1< MU <=2
U | 0< U <=1 | HU | HU =0 |  |  | . | . | . | . | .

## Evaluation
Results of Assesment of Completed Activities
S. No | Result Area | Activity | Feedback / Remrks on Completed Activities |  |  | Recommendations on Action to be taken
1 | . | . | . |  |  | .
2 | . | . | . |  |  | .
3 | . | . | . |  |  | .
4 | . | . | . |  |  | .
5 | . | . | . |  |  | .
6 | . | . | . |  |  | .
7 | . | . | . |  |  | .
8 | . | . | . |  |  | .
9 | . | . | . |  |  | .
Results of Assesment of Completed ActivityGroups Indicator Wise
S. No | Result Area | Log Frame Indicator | Contributing Activities Completed | Feedback / Remarks on Assesment Log Frame Indicator Wise |  |  | Recommendations on Action to be taken
1 | . | . | . | . |  | . | .
2 | . | . | . | . |  | . | .
3 | . | . | . | . |  | . | .
4 | . | . | . | . |  | . | .
5 | . | . | . | . |  | . | .
6 | . | . | . | . |  | . | .
7 | . | . | . | . |  | . | .
8 | . | . | . | . |  | . | .
9 | . | . | . | . |  | . | .
Lessons Learnt and Way forward Result Area and Activity Wise
S. No | Result Area | Activity | Lessons learnt in Execution |  | Remedial Action / Improvements Possible |  |  | Remarks
1 | . | . | . |  | . |  |  | .
2 | . | . | . |  | . |  |  | .
3 | . | . | . |  | . |  |  | .
4 | . | . | . |  | . |  |  | .
5 | . | . | . |  | . |  |  | .
6 | . | . | . |  | . |  |  | .
7 | . | . | . |  | . |  |  | .
8 | . | . | . |  | . |  |  | .

## Project Purpose
PROJECT PURPOSE
To improve the business environment in Botswana and stimulate economic diversification in the private sector. Develop and increase the role of SMMEs in the economy.
INDICATOR | BASELINE | TARGET | STATUS | TIME LAPSED (YEARS) | PROJECT PURPOSE ASSESSMENT | RATING INDICATOR
World Bank doing business ranking | 134 | 120 | 125 | 1 | MODERATELY SATISFACTORY | MS
Economic Diversification | 120 | 134 | 125 | 1 | MODERATELY SATISFACTORY | MS
Number of SMMEs | 40000 | 50000 | 47000 | 1 | HIGHLY SATISFACTORY | HS
Value and volume of exports | 650 | 750 | 600 | 1 | HIGHLY UNSATISFACTORY | HU

## Result Area 1
Result Area Activity Monitoring Report (Summary) : 28th February 2015
RESULT AREA 1: | [12 empty] | Score | Rating Code
CAPACITY AND COMPETITIVENESS OF SMMEs AND COMMUNITY BASED ORGANISATION (CBO'S) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [12 empty] | 1.6 | MU
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | Score | Rating Code
IND 1.1 | 3.5 | S | Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Projects on Beef Completed, Three action items are being implemented. (1) Management for Commercial Farmers (2) Upgrading capacity of Farmers Association. (3) Technical Tools of graduating communal Farmers. Horticulture and tourism in progress. No report submitted yet |  |  |  |  | 4 | S
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | Final report submitted for review by CDE but still pending since 02 February 2015, contract extended to 28th February 2015. |  |  |  |  | 3 | MS
IND 1.2 | 3 | MS | Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014. |  |  | A 1.2 | Value Added wild / Natural Product Opportunity Study
[6 empty] | A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | Action plan for Honey Submitted and Morula being finalised, contract extended till 28 February 2015. |  |  |  |  | 3 | MS
IND 1.3 | 2.5 | MU | At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015. |  |  | A 1.3 | SME's Diagnostics (Baseline studies)
[6 empty] | A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | Team for the Diagnosis of SMMEs (BWP 1414/01) |  | Team Leader preparing final report not yet complete |  |  | 5 | HS
[8 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Local Consultants completed 22 SMMEs out of a total of ____SMME's
[8 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | BNPC completed 28 out of __ SMMEs
[8 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | BIH Completed 14 out of 15 SMME's
[8 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | LEA completed 9 SMME's including 2 CBO's
[8 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | CEDA to Complrte 10 SMME's by 31st January 2015
[8 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Capacity Building of local staff on SMMe Diagnostics File Completed and closed
[8 empty] | PSDP Mission Logistics (BWP/1404/01 |  | No Data
[8 empty] | SMME Diagnostics for Micros (File Number Requested) |  | Yet to start
[6 empty] | A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | Support to poultry sector (BWP 1444/01) |  | (1)funds committed and contract to be signed by 30 January 2015 (2)Consultant first mission begins 2 February 2015 |  |  | 0 | HU
[8 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | file at commitment level- commitment of funds by 20th February 2015
IND 1.4 | 0 | HU | At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015 |  |  |  |  | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | file at commitment level- commitment of funds by 20th February 2015
[8 empty] | SMEs trade missions-Result Area1 (BWP 1313/01) |  | Three SMEs from the Diary sector participated at the 9th African Diary Conference and Exhibition held in Harare, Zimbabwe from the 24 to 26 September, 2013.
[8 empty] | Group training in management Finance (BWP 1446/01) |  | TOR and budget finalized. Follow up PA
[8 empty] | Management training for Micros and CBOs |  | selection of service provider done. Follow up Commitment
[8 empty] | Group training in Business Planning for SMEs |  | TOR and budget finalized. Follow up PA
[8 empty] | Participation of SMMEs to trade missions & trainings |  | TOR and budget to be prepared. Request file number
[8 empty] | Individual Coaching of SMMEs |  | Activity under preparation. Request file number
IND 1.5 | 0 | HU | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. |  |  |  |  | SME Development Experts |  | Activity under preparation. Request file number
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | A 1.3.1 Diagnostics for 70 SMMe's |  |  | 5 | The task was successfully completed in time
2 | . |  |  | . | .
3 | . |  |  | . | .
4 | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt abd Suggestions for way forward
1 | A 1.1.1 Structured value chains analysis and preparation of capacity building Action plans |  |  | 4 | Though the contract ends in August 2015 as shown in the weekly report The contract stipulates that all deliverables must be complete two months before that date or in June 2015. Further no progress is reported after 31st December 2014 if this continues the rating may need to be down graded
2 | A1.1.2 Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) |  |  | 3 | The contract has been extended to 28th Feb 2015 (The report does not specify if the MC has been taken in confidence or approval of the competent authourity has been taken for this extension. Also, as per the weekly report the consultant has submitted the final report before the 2nd February weekly meeting; yet as per subsequent reports the report is pending review by CDE till the date of this report.
3 | A1.2.1 Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) |  |  | 3 | As per the completion dates in the weekly report the second part of this activity (Morula Study and Action Report) will becone due on 1st March; consequently the rating will fall.
4 | A 1.3.1 Diagnostics of SMMEs (BNPC, BIH, Local consultants) |  |  | 3 | This subactivity had been graded HS in the last report as on 31st December 2014 the number of SMME audits completed were more than 70 out of 100 when 70 was the target. The progress during 1st January 2015 to 28 February 2015 has been below expectations and major tasks like the team leaders report and outstanding Audits have not neen completed
5 | A 1.4.1 Capacity Building of SMME's and CBO's for upgrading their Competiveness |  |  | 0 | As of 28th Feb all these sub activities should have started but the latest weekly report indicated no progress or action in hand. The pending actions need to be done and if necessary approval of the compitent authourity needs to be taken and completion dates revised

## Result Area 1(D)
Monitoring and Evaluation Interim Report for the period 1st January 2015 to 28 Feb 2015
Result Area 1: Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors
Contributing Activity Number | Description of Activity | BASELINE | TARGET | OUTPUT / SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievements |  |  |  |  | Score | Rating Code | Rating | Reporting Responsibility and Method
A 1.1 | Value Chains Analysis and Development
A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Previous studies and proposals | Three value chains identified that show potential to be strengthened in a published study | M & E Output Verification http://www.webtestopq.co.bw/documents/3QUtDc.pdf | 2018-08-19 | 2019-03-01 | Projects on Beef Completed, Three action items are being implemented. (1) Management for Commercial Farmers (2) Upgrading capacity of Farmers Association. (3) Technical Tools of graduating communal Farmers. Horticulture and tourism in progress. No report submitted yet |  |  |  |  | 4 | Satisfactory | S | BOCCIM Staff – direct system update
A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | No action plan exists | Five value chains in eight sub-sector capacity building actions plans to support SMMEs and IOs are developed and validated by February 2015 | PSDP M&E Report; Analysis and Development Study report and SMMEs Audit reports | 2018-07-31 | 2019-03-01 | Final report submitted for review by CDE but still pending since 02 February 2015, contract extended to 28th February 2015. |  |  |  |  | 3 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
A 1.2 | Value Added wild / Natural Product Opportunity Study
A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | No opportunity study exists | Honey and Morula Action Plan opportunity studies conducted and action plans for honey and morula in place by September 2014 | PSDP M&E Reports; Contracts Awarded and Reports Tracking the Contract; Action plans Completed | 2018-06-17 | 2018-10-01 | Action plan for Honey Submitted and Morula being finalised, contract extended till 28 February 2015. |  |  |  |  | 3 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
A 1.3 | SME's Diagnostics (Baseline studies)
A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | No PSDP audit and need assessment | 100 SMME’s are audited | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2018-07-15 | 2018-11-08 | Team for the Diagnosis of SMMEs (BWP 1414/01) |  | Team Leader preparing final report not yet complete |  |  | 5 | Highly Satisfactory | HS | BOCCIM Staff – direct system update
[7 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Local Consultants completed 22 SMMEs out of a total of ____SMME's
[7 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | BNPC completed 28 out of __ SMMEs
[7 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | BIH Completed 14 out of 15 SMME's
[7 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | LEA completed 9 SMME's including 2 CBO's
[7 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | CEDA to Complrte 10 SMME's by 31st January 2015
[7 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Capacity Building of local staff on SMMe Diagnostics File Completed and closed
[7 empty] | PSDP Mission Logistics (BWP/1404/01 |  | No Data
[7 empty] | SMME Diagnostics for Micros (File Number Requested) |  | Yet to start
A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | No PSDP tailored capacity training done | 70 SMMe's and 30 Micro enterprises as well as CBOs are audited and an Action Plan for Capacity Building developed and implemented by Dec 2015 ; 10 SMMEs are implementing environmental protection plans | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2019-01-06 | 2019-12-31 | Support to poultry sector (BWP 1444/01) |  | (1)funds committed and contract to be signed by 30 January 2015 (2)Consultant first mission begins 2 February 2015 |  |  | 0 | Highly Unsatisfactory | HU | BOCCIM Staff – direct system update
[7 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | file at commitment level- commitment of funds by 20th February 2015
[7 empty] | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | file at commitment level- commitment of funds by 20th February 2015
[7 empty] | SMEs trade missions-Result Area1 (BWP 1313/01) |  | Three SMEs from the Diary sector participated at the 9th African Diary Conference and Exhibition held in Harare, Zimbabwe from the 24 to 26 September, 2013.
[7 empty] | Group training in management Finance (BWP 1446/01) |  | TOR and budget finalized. Follow up PA
[7 empty] | Management training for Micros and CBOs |  | selection of service provider done. Follow up Commitment
[7 empty] | Group training in Business Planning for SMEs |  | TOR and budget finalized. Follow up PA
[7 empty] | Participation of SMMEs to trade missions & trainings |  | TOR and budget to be prepared. Request file number
[7 empty] | Individual Coaching of SMMEs |  | Activity under preparation. Request file number
[7 empty] | SME Development Experts |  | Activity under preparation. Request file number
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | . | . | .

## Result Area 2
Result Area Activity Monitoring Report (Summary) : 28th February 2015
RESULT AREA 2: | [12 empty] | Score | Rating Code
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced. | [12 empty] | 2.5833 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | Score | Rating Code
IND 2.1 | 3.3333 | S | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 10% by December 2015. • PSDP Web based M&E system is operational by December 2014. |  |  | A 2.1 | Capiciyty Building of BOCCIM
[6 empty] | A 2.1.1 | Internal Monitoring and Evaluation of PSDP | final report submitted and training schedule for 3rd to 5th March 2015 |  |  |  |  | 4 | S
[6 empty] | A 2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | Review of the mandates and establish BOCCIM as an Apex body (BOT/1402/01) |  | The final report ith recommendations to establish BOCCIM as an apex body has been submitted. |  |  | 4 | S
[8 empty] | Review of BOCCIM Constitution (BWP/1401/01 ) |  | Reports of the work done received for uploading by M&E team but Progress not given in Weekly report
[8 empty] | BOCCIM Membership Model (BWP/1402/01 ) |  | Reports of the work done received for uploading by M&E team but Progress not given in Weekly report
[8 empty] | Consultative Workshops for BOCCIM (BWP/1416/01 ) |  | Reports of the work done received for uploading by M&E team but Progress not given in Weekly report
[8 empty] | BOCCIM NBC (BWP/1438/01 ) |  | Reports of the work done received for uploading by M&E team but Progress not given in Weekly report
[6 empty] | A 2.1.3 | BOCCIM capacity building to render better services to its members (BWP/1437/01) | Inception Report Submitted |  |  |  |  | 2 | MU
[6 empty] | A 2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | TOR and Budget and budget to be prepared and start by March 2015 |  |  |  |  | NA | NA
IND 2.2 | 3 | MS | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs - June 2015. |  |  | A 2.1.4 | Assistance to the establishment of market intelligence information system/web based platform for networking and information / Public and private dialogue, etc… (BWP/1434/01) | Benchmarking BOCCIM web Portal (BWP/1434/01) |  | Mission for the market intelligence completed in November 2014 |  |  | 3 | MS
[8 empty] | Feasibility study for the market intelligence being done under Value chain analysis for beef, tourism, and horticulture sectors (BWP/1310/01 ). |  | Web based platform for networking and information dissemination will be established under Result Area 2. The first mission was undertaken in December 2014. Mission report has been submitted and approved.
[8 empty] | Assistance to the establishment of market intelligence information |  | TOR and Budget to be prepared
Ind 2.3 | 1 | U | Capacity building of BITC is conducted • An export strategy with respective action plan is adopted and implementation of the action plan starts in December 2015. • Three partnerships are established with external trading partners by December 2015. • At least 10 of the PSDP targeted SMMEs are qualified for export by BITC by December 2015. |  |  | A 2.2 | Capacity Building of BITC
[6 empty] | A 2.2.1 | Assistance to BITC in Export Development and Promotion (BWP/1406/01) | Assistance to BITC in Export Development and Promotion – contract signed, first mission for the consultant starts on the 13 February 2015. |  |  |  |  | 1 | U
[6 empty] | A 2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | Participation of IOs to trade missions & trainings – (BWP/1307/01) |  | WTO International Trade & Development course, Geneva, Switzerland. Completed |  |  | 1 | U
[8 empty] | Participation of IOs to trade missions & trainings – (BWP/1308/01) |  | support for training on Exports and Investment Promotion Programme –report submitted, Dublin Ireland.
[8 empty] | BITC sector association experts- .(BWP/1503/01) |  | contract signed and deskwork has started
Ind 2.4 | 3 | MS | Capacity building of Intermediary Organisations and sector associations is conducted. • Number of private firms using TSIs and BDSPs services increased by 10% by December 2015. • At least 70% of SMMEs and CBOs benefiting from PSDP intervention are satisfied with the quality of service provided by IOs and BDSPs. • Recommendations developed and submitted to MTI by December 2015 for improving competitiveness and export of Botswana Beef. • At least three new products and/or services introduced by IOs by December 2015. |  |  | A 2.3 | Capacity Building of Intermediart Organisations and Sector Associations
[6 empty] | A 2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) (BWP/1420/01) | 62 local staff from Intermediary Organisation were trained- the activity has been completed and closed. |  |  |  |  | 3 | MS
[6 empty] | A 2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | PPD Meeting on Beef Value Chain (BWP/1428/01) |  | Successfully Completed |  |  | 3 | MS
[8 empty] | Management Tools for Commercial farmers (BWP/1508/01) |  | PA preparation.
[8 empty] | Technical Tools for Graduating communal farmers (BWP/1510/01) |  | PA preparation.
[8 empty] | Upgrading Capacity of farmers Associations (BWP/1511/01) |  | PA preparation.
[6 empty] | A 2.3 3 | Assistance to the tourism sector in partnership with BTO and HATAB | Assistance to the tourism sector in partnership with BTO and HATAB |  | TOR and Budget to be prepared. to start in March 2015 |  |  | NA | NA
[8 empty] | HATAB Tourism conference (BWP/1443/01) |  | Activity to take place in April 2015.
[6 empty] | A 2.3.4 | Assistance to honey sector associations | TOR and Budget to be prepared to start April 2015. |  |  |  |  | NA | NA
IND 2.5 | NA | NA | Capacity building conducted for BOBS on Quality Certification • Draft National Quality Policy is developed and submitted to MTI by June 2015. • BOBS staff members are trained in audit and inspection services and ten service providers are capacitated in auditing and certification of agro-industry (horticulture, diary, beef) and manufacturing by December 2015. • SMME certification system is in place by September 2015. |  |  | A 2.4 | Capacity Building for BOBS on Quality and Certification
[6 empty] | A 2.4.1 | Support the development of a National Quality Policy | Not Started |  |  |  |  | NA | NA
[6 empty] | A 2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | Not Started |  |  |  |  | NA | NA
[6 empty] | A 2.4.3 | Support the process of certification for SMEs | Due to start in April 2015 |  |  |  |  | NA | NA
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0 | NA | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
NIL | NIL |  |  | NIL | NIL
. | . |  |  | . | .
S. No | Name of Activity |  |  | Rating | Alert / Observations, Lessons Learnt abd Suggestions for way forward
1 | A 2.1.1 Internal Monitoring and Evaluation of PSDP |  |  | 4 | There is an inprovement in the alighment of the weekly progress report and the inputs requred for the M&E framework. Further efforts required
2 | A 2.1.2 Review of the mandates and establish BOCCIM as an Apex body |  |  | 4 | The first part of five parts is complete and no report is available for the remaining 4 parts . If no reports are available by the next report the score will be down graded
3 | A 2.1.5 Training BOCCIM and other IOs in policy research, lobbying & advocacy |  |  | NA | The activity is due in March and the TOR and other firmalities are yet to be done. May be down graded if not started
4 | A 2.1.4 Assistance to the establishment of market intelligence information |  |  | 3 | This is due to start in march and may be down graded if not started in March as per this report TOR and Budgets are to be prepared
5 | A 2.2.1 Assistance to BITC in Export Development and Promotion (BWP/1406/01) |  |  | 1 | The report does not clarify if the consultant has started and they are on on schedule
6 | A 2.2.2 Assistance to BITC for implementation of its new strategy (sector approach) |  |  | 1 | The report does not clarify if the work and projects has started and work is on schedule
7 | A 2.3.1 Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) (BWP/1420/01) |  |  | 1 | Training feedback and evaluation reports not submitted hence the low score
8 | A 2.3.2 Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export |  |  | 3 | Score low as only the Beef Sector PPD is complete and no progrerss reported on other sectors and the Start date is reported to be February 2015. Thus if there is no progress this rating will fall further
9 | A 2.3.3 Assistance to the tourism sector in partnership with BTO and HATAB |  |  | NA | These are to start in March and April and even the file numbers and approval is not done the scores may fall to HU if not started.
10 | A 2.4 Capacity Building for BOBS on Quality and Certification and all sub activities |  |  | NA | These are to start in April and even the file numbers and approval is not done the scores may fall to HU if not started.

## Result Area 2 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 2: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Contributing Activity Number | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievement |  | Score | RATING CODE | RATING | Reporting Responsibility
A 2.1 | Capacity Building of BOCCIM
A 2.1.1 | Internal Monitoring and Evaluation of PSDP | Web based M&E system is not available | Web based M&E system is fully operational | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | final report submitted and training schedule for 3rd to 5th March 2015 |  | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
A 2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | Review of Mandates not taken place | BOCCIM established as Apex Body for Private Sector in Botswana | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | Review of the mandates and establish BOCCIM as an Apex body (BOT/1402/01) | The final report ith recommendations to establish BOCCIM as an apex body has been submitted. | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
[7 empty] | review of BOCCIM Constitution (BWP/140/01) | Reports of the work done reieved for uploading by M&E team but Progress not given in weekly report
[7 empty] | BOCCIM Membership model (BWP/1402/01) | Reports of the work done reieved for uploading by M&E team but Progress not given in weekly report
[7 empty] | Consultative Workshop for BOCCIM (BWP/1416/01) | Reports of the work done reieved for uploading by M&E team but Progress not given in weekly report
[7 empty] | BOCCIM NBC (BWP /1438/01) | Reports of the work done reieved for uploading by M&E team but Progress not given in weekly report
A 2.1.3 | BOCCIM capacity building to render better services to its members | No Membership satisfaction survey carried out | BOCCIM Membership increases by 10% by December 2015 | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | Inception Report Submitted |  | 2 | MODERATELY UNSATISFACTORY | MU | CDE / BOCCIM Staff – direct system update;
A 2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | DNA | DNA | PSDP M&E Reports; | DNA | 2015-12-01 | TOR and Budget and budget to be prepared and start by March 2015 |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
A 2.1.4 | Assistance to the establishment of market intelligence information system/web based platform | No MIIS | An operational MIIS | PSDP M&E Reports; Hits on website | 2014-10-01 | 2015-06-30 | Benchmarking Boccim Web Portal (BWP/1434/01) | Mission for the market intelligence completed in November 2014 | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
[7 empty] | Feasibility study for the market intelligence being done under Value chain analysis for beef, tourism, and horticulture sectors | Web based platform for networking and information dissemination will be established under Result Area 2. The First mission was undertaken in december 2014. Mission report has been submitted and approved
[7 empty] | Assistance to the establishment of market intelligence information | TOR and Budget to be prepared
A 2.2 | Capacity Building of BITC
A 2.2.1 | Assistance to BITC in Export Development and Promotion | No Export Strategy is in place at BITC. The PSDP identified SMMES are not exporting. | One export strategy implemented, 3 partnerships are established with external trading partners outside Botswana’s borders. Ten SMMEs are export ready. | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2015-01-05 | 2015-12-30 | Assistance to BITC in Export Development and Promotion – contract signed, first mission for the consultant starts on the 13 February 2015. |  | 1 |  | U | CDE / BOCCIM Staff – direct system update;
A 2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2015-01-05 | 2015-12-30 | Participation of Ios to trade missions & trainings - (BWP/1307/01) | WTO International Trade & Development course, Geneva, Switzerland. Completed | 1 | UNSATISFACTORY | U | CDE / BOCCIM Staff – direct system update;
[7 empty] | participation of Ios to trade missions & trainings - (BWP/1307/01) | support for training on Exports and Investment Promotion Programme –report submitted, Dublin Ireland.
[7 empty] | BITC sector association experts - (BWP/1503/01) | contract signed and deskwork has started.
A 2.3 | Capacity Building of Intermediary Organisations and Sector Associations
A 2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | 62 local staff from Intermediary Organisation were trained- the activity has been completed and closed. |  | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
A 2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | PPD Meeting on Beef Value Chain (BWP/1428/01) | Succesfully Completed | 2 | MODERATELY UNSATISFACTORY | MU | CDE / BOCCIM Staff – direct system update;
[7 empty] | Management Tools for Commercial farmers (BWP/1508/01) | PA preparation.
[7 empty] | Technical Tools for Graduating communal farmers (BWP/1510/01) | PA preparation.
[7 empty] | upgrading Capacity of farmers Associations (BWP/1511/01) | PA preparation.
2.3.3 | Assistance to the tourism sector in partnership with BTO and HATAB | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Assistance to the tourism sector in partnership with BTO and HATAB | TOR and Budget to be prepared. to start in March 2015 | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
[7 empty] | HATAB Tourism Conference(BWP/1443/01) | Activity to take place in April 2015.
A 2.3.4 | Assistance to honey sector associations | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | TOR and Budget to be prepared to start April 2015. |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
A 2.4 | Capacity Building for BOBS on Quality and Certification
A 2.4.1 | Support the development of a National Quality Policy | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
A 2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
.
A 2.4.3 | Support the process of certification for SMEs | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 |  | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . |  | . | . | . | . | .

## Result Area 3
Result Area Activity Monitoring Report (Summary) : December 2014
RESULT AREA 3: | [6 empty] | Score | Rating Code
Business environment (reduction of red tape and pilot on accessing finance) for enterprises is enhanced. | [6 empty] | 3.25 | S
Log Frame Indicator Number | Score | Rating Code | Description of Indicator | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements | Score | Rating Code
IND 3.1 | 4 | S | Capacity building conducted on trade and specific negotiation skills • Recommendations submitted by PSDP to MTI on the reduction of; the cost of doing business; and the cost and time required for registration and operationalization of SMMEs in Botswana by June 2015. • Members of the Trade Facilitation and Advisory Group (TFAG) and National Committee on Trade Policy and Negotiations (NCTPN) are trained on MTI Trade Capacity Building Strategy by June 2015. • At least 10 IO staff members are trained in EPA implementation by September 2015 | A 3.1 | Capacity Building on Trade and Specific Negotiation Skills
|  |  |  | A 3.1.1 | Establish trade facilitation group and provide capacity building | Trade Facilitation Advisory Group and NTCPN needs assesment Developed | 4 | S
|  |  |  | A 3.1.2 | Training of TFAG and NTCPN on negotiation and trade facilitation | Yet to start | NA | NA
|  |  |  | A 3.1.3 | Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation | Yet to start | NA | NA
IND 3.2 | 2.5 | MS | Improved Policy Framework to access finance • At least 1 new financial product (post loan support mechanism) targeting SMMEs is introduced by commercial banks and or other financial institutions supporting SMME financing by December 2015 • 30 SMME’s under PSDP are assisted to prepare their business plans for submission to commercial banks and other financial institutions by December 2015. • At least 5 PSDP SMMEs assisted are accessing finance by February 2016. • Micro finance policy framework is established and presented to Government for adoption by September 2014. • A microfinance Act is drafted and submitted to government by September 2014. | A 3.2 | Policy Framework to Improve Access to Finance
|  |  |  | A 3.2.1 | Draft a microfinance policy framework | Draft Microfinance Policy Developed and submitted to MTI and MFDP | 5 | HS
|  |  |  | A 3.2.2 | Draft a micro-finance Act for Botswana | Yet to start | NA | NA
IND 3.3 | NA | NA | Improved Business Environment (Ease of Doing Business) • A compilation of recommendations submitted to MTI by December 2015 to simplify tax registration with a view to improve tax compliance by SMMEs. • A compilation of labour laws affecting SMMEs with recommendations for reforms submitted to MTI by December 2015. | A 3.3 | Improving Business Environment (Ease of Doing Business)
|  |  |  | A 3.3.1 | Review the registration process and tax compliance | Yet to start | NA | NA
|  |  |  | A 3.3.2 | Review of labour laws and recommend labour productivity improvement strategies | Yet to start | NA | NA

## Result Area 3 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 3: Business Environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Contributing Activity Number | DESCRIPTION OF ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Signifcant Achievements | Score | RATING CODE | RATING | Reporting Responsibility
A 3.1 | Capacity building on Trade and Specific Negotiation Skills
3.1.1 | Establish trade facilitation group and provide capacity building | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Completed and final report submitted | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
3.1.2 | Training of TFAG and NTCPN on negotiation and trade facilitation | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
3.1.3 | Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
A 3.2 | Policy Framework to Improve Access to Finance
3.2.1 | Draft a microfinance policy framework | No Policy | DNA | Activity Progress Reports | DNA | DNA | Activity completed. Submitted to the Competent Authourity in the Government of Botswana | 5 | HIGHLY SATISFACTORY | HS | CDE / BOCCIM Staff – direct system update;
3.2.2 | Draft a micro-finance Act for Botswana | No Act | DNA | Activity Progress Reports | DNA | Dec 154 | Legal Expert for Micro Finance Act- Activity pending approval of the framework policy | 0 | HIGHLY UNSATISFACTORY | HU | CDE / BOCCIM Staff – direct system update;
A 3.3 | Improving Business Environment (Ease of Doing Business)
3.3.1 | Review the registration process and tax compliance | No Review | DNA | Activity Progress Reports | DNA | 2019-12-31 | contract has been awarded 26 January 2015 to 30 August 2015 | 3 | MODERATELY SATISFACTORTY | MS | CDE / BOCCIM Staff – direct system update;
3.3.2 | Review of labour laws and recommend labour productivity improvement strategies | DNA | DNA | Activity Progress Reports | DNA | 2019-12-31 | contract has been awarded 26 January 2015 to 30 August 2015 | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | . | . | .

## Component 4
Monitoring and Evaluation Report for Quarter Ending December 2014
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY
Activity No. | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Status / Achievements | Score | RATING CODE | RATING | Reporting Responsibility
4.1 | Recruitment of a service provider for the design of PSDP Monitoring and Evaluation (M&E) System | No M&E System | Online M&E System operational | Consultants engaged and system developed | 28-05-14 | 31-01-16 | Activity A 4.1 Completed Service Provider in place since June 2014 and M&E Progress Reporting shifted to Result Area 2 A 2.1.1 | 5 | NA | NA | CDE / BOCCIM Staff – direct system update;
4.2 | Design and implement PSDP Communication and Visibility Plan | No Communication and Visibility Plan | Effective implementation of the Communicaiton and Visibility Plan | Plan is developed | 14/05/2014 | 14-01-16 | Communication and visibility plan approved; PSDP News letter launched; 4 press releaseds of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced. | 5 | NA | NA | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | .

## Component 4 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY
Contributing Activity Number | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievement | Score | RATING CODE | RATING | Reporting Responsibility
A 4.1 | Recruitment of a service provider for the design of PSDP Monitoring and Evaluation (M&E) System | No M&E System | Online M&E System operational | Consultants engaged and system developed | 28-05-14 | 31-01-16 | Activity A 4.1 Completed Service Provider in place since June 2014 and M&E Progress Reporting shifted to Result Area 2 A 2.1.1 | 5 | HIGHLY SATISFACTORY | HS | CDE / BOCCIM Staff – direct system update;
A 4.2 | Design and implement PSDP Communication and Visibility Plan | No Communication and Visibility Plan | Effective implementation of the Communicaiton and Visibility Plan | Plan is developed | 14/05/2014 | 14-01-16 | Communication and visibility plan approved; PSDP News letter launched; 4 press releaseds of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced. | 5 | HIGHLY SATISFACTORY | HS | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | .

## Logframe
PSDP LOGICAL FRAME
Intervention Logic | Objectively Verifiable Indicators | Source of Verification
OVERALL OBJECTIVE | Botswana maintains positive economic growth, with increased contribution from the private sector. | National economic statistics
To contribute to economic growth, employment creation and diversification resulting in the reduction of poverty |  | Reports by UN, IMF, World Bank, OECD and AU
PROJECT PURPOSE | Ease of doing business in Botswana improved | Doing Business indicators WB (access to credit, trading across borders)
To improve the business environment in Botswana and stimulate economic diversification in the private sector. Develop and increase the role of SMMEs in the economy. | Increased number of SMMEs in economic production, exports and employment | Botswana Business surveys
| Increased contribution by the private sector to the GDP | Central Bureau of Statistics indicators
Result Area 1: | Ind.1.1 Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 | Contracts Awarded and Reports Tracking the PSDP Monitoring and evaluation (M&E) Reports SMMEs Audit reports Capacity building workshop reports BOBS’s SMME quality improvement report
Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Ind. 1.2: Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014.
Ind.1.3: At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015.
Ind.1.4: At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015.
Ind.1.5: 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015.
Result Area 2: | Ind.2.1: BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 10% by December 2015. • PSDP Web based M&E system is operational by December 2014. | PSDP M&E Reports BOCCIM new Constitution BOCCIM Strategy Plan 2014-2016 BOCCIM Annual Reports BOCCIM membership satisfaction survey report PSDP M&E Web portal
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
| Ind.2.2: A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs - June 2015 | PSDP M&E Reports TSIs and BDSPs annual reports
| Ind.2.3: Capacity building of BITC is conducted • An export strategy with respective action plan is adopted and implementation of the action plan starts in December 2015. • Three partnerships are established with external trading partners by December 2015. • At least 10 of the PSDP targeted SMMEs are qualified for export by BITC by December 2015. | Contracts Awarded and Reports Tracking the Contract PSDP M&E Reports SMME annual reports BITC annual reports MTI annual reports
| Ind 2.4: Capacity building of Intermediary Organisations and sector associations is conducted. • Number of private firms using TSIs and BDSPs services increased by 10% by December 2015. • At least 70% of SMMEs and CBOs benefiting from PSDP intervention are satisfied with the quality of service provided by IOs and BDSPs. • Recommendations developed and submitted to MTI by December 2015 for improving competitiveness and export of Botswana Beef. • At least three new products and/or services introduced by IOs by December 2015. | Contracts Awarded and Reports Tracking the Contract PSDP M&E Reports TSI and BSDPs annual reports SMME survey reports Tourism industry reports
| Ind 2.5: Capacity building conducted for BOBS on Quality Certification • Draft National Quality Policy is developed and submitted to MTI by June 2015. • BOBS staff members are trained in audit and inspection services and ten service providers are capacitated in auditing and certification of agro-industry (horticulture, diary, beef) and manufacturing by December 2015. • SMME certification system is in place by September 2015. • Draft National Quality Policy is developed and submitted to MTI by June 2015. • BOBS staff members are trained in audit and inspection services and ten service providers are capacitated in auditing and certification of agro-industry (horticulture, diary, beef) and manufacturing by December 2015. • SMME certification system is in place by September 2015. | PSDP M&E Reports BOBs annual reports
Result Area 3 | Ind.3.1: Capacity building conducted on trade and specific negotiation skills • Recommendations submitted by PSDP to MTI on the reduction of; the cost of doing business; and the cost and time required for registration and operationalization of SMMEs in Botswana by June 2015. • Members of the Trade Facilitation and Advisory Group (TFAG) and National Committee on Trade Policy and Negotiations (NCTPN) are trained on MTI Trade Capacity Building Strategy by June 2015. • At least 10 IO staff members are trained in EPA implementation by September 2015. | Willingness and availability of MTI staff to participate Trade Facilitation Advisory Group is operational and effective Willingness and availability of banking sector to pparticipate. Willingness of SMMEs to register for taxes
Business environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
| Ind.3.2: Improved Policy Framework to access finance • At least 1 new financial product (post loan support mechanism) targeting SMMEs is introduced by commercial banks and or other financial institutions supporting SMME financing by December 2015. • 30 SMME’s under PSDP are assisted to prepare their business plans for submission to commercial banks and other financial institutions by December 2015. • At least 5 PSDP SMMEs assisted are accessing finance by February 2016. • Micro finance policy framework is established and presented to Government for adoption by September 2014. • A microfinance Act is drafted and submitted to government by September 2014. | Contracts Awarded and Reports Tracking the Contract PSDP M&E Reports MFDP annual reports SMME reports Banks/financial institutions annual reports
| Ind.3.3: Improved Business Environment (Ease of Doing Business) • A compilation of recommendations submitted to MTI by December 2015 to simplify tax registration with a view to improve tax compliance by SMMEs. • A compilation of labour laws affecting SMMEs with recommendations for reforms submitted to MTI by December 2015 | PSDP M&E reports SMME audit reports World Bank Doing Business Report MTI reports