## Overall Objective
Overall Objective
To contribute to economic growth, employment creation and diversification Resulting in the Reduction of Poverty
INDICATOR | BASELINE | TARGET | STATUS | TIME (YEARS) | OVERALL OBJECTIVE ASSESSMENT | RATING INDICATOR
Annual GDP Growth | 5 | 7 | 6 | 1 | HIGHLY SATISFACTORY | HS
Employment creation | 20000 | 50000 | 25000 | 1 | MODERATELY UNSATISFACTORY | MU
Gross capital formation, private sector (% of GDP) | 35 | 40 | 39 | 1 | HIGHLY SATISFACTORY | HS

## Overall Summary
Monitoring and Evaluation Report (Summary) : December 2014
Overall Summary
Result Area / Component | [5 empty] | Rating | Rating Code | Remarks on Significant Achievements
RESULT AREA 1: CAPACITY AND COMPETITIVENESS OF SMME’S AND COMMUNITY BASED ORGANISATION (CBOS) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [5 empty] | 2.66 | MS | • 70 SMMEs Audited Training and Capacity building yet to start in 2015. • Report and Action Plans for Beef Value chain completed and Public Private Dialogue conducted, Work in progress in 2 other structured value chains, • 5 Emerging value chains and Morula and Honey Opportunity studies in progress. Final reports expected in early 2015.
RESULT AREA 2: SERVICE DELIVERY OF TARGETED INTERMEDIARY ORGANISATIONS (IOs) AND BUSINESS DEVELOPMENT SERVICE PROVIDERS (BDSP) IS ENHANCED | [5 empty] | 3 | MS | • BOCCIM Action Plan as an apex Body elaborated; • Monitoring and Evaluation System Portal has gone live, pending training of staff and transfer of Portal to BOCCIM server; • Other capacity building actions have not yet started and some are in progress.
RESULT AREA 3: BUSINESS ENVIRONMENT FOR ENTERPRISES IS IMPROVED (REDUCTION OF RED TAPE AND PILOT ON IMPROVED ACCESS TO FINANCE BY SMMEs) | [5 empty] | 3.25 | S | • Trade Facilitation Advisory Group and NTCPN needs assesment developed; • Micro Finance Policy Framework developed and submitted to MTI and MFDP; • MTI supported on Monitoring and Evaluation.
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY | [5 empty] | 5 | HS | • Service Provider to develop and maintain M&E System and Portal recruited and in place since June 2014 • Communication and visibility plan approved; PSDP News letter launched; 4 press releaseds of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced
4 <HS< =5 | HS | 3 <S< =4 | S | 2<MS<=3 | 2 <MS< =3 | MS | 1 <MU< =2 | MU | 0 <U< =1 | U | HU =0 | HU
Justification for Result Areas Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Result Area Awarded HS ou HU |  |  | Rating |  | Justification for Extreme score
1 | Component 4 |  |  | 5 |  | The two service providers for M&E system and Communications are in place and delivering as expected. Their presence is felt and seen by a number of stakeholders
2 | . |  |  | . |  | .
3 | . |  |  | . |  | .
4 | . |  |  | . |  | .
2.5

## Progressive sheet
Performance of each Log Frame Indicator Progressive Quarter Wise
Monitoring and Evaluation Report (Summary) : December 2014
Result Area One :Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Log Frame Ind | Description of the Log frame Indicator | Progressive Rating codes | [6 empty] | Remarks
|  | Q3 2014 | Q4 2014 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 1.1 | Action plans to support SMMEs and IOs are developed for eight valuchains and eight sub sectors by February 2015 | NA | S | .. | .. | .. | .. | .. | ..
Ind 1.2 | Studies are carried out for development of Honey and Morula Value Chains by September 2014. | HU | MU | .. | .. | .. | .. | .. | ..
Ind 1.3 | At least 70 SMMEs are strengthened on management, operations by December 2015. | MS | MS | .. | .. | .. | .. | .. | ..
Ind 1.4 | 30 CBO’s are trained on management, marketing, quality standards and accounting by December 2015 | NA | NA | .. | .. | .. | .. | .. | ..
Ind 1.5 | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. | NA | NA | .. | .. | .. | .. | .. | ..
Result Area Two: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Log Frame Ind | Description of the Log frame Indicator | Progressive Rating codes | [6 empty] | Remarks
|  | Q3 2014 | Q4 2014 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 2.1 | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana and M&E is Operational by December 2014 | MU | S | .. | .. | .. | .. | .. | ..
Ind 2.2 | A web based market intelligence information system is developed for use by SMMEs - June 2015. | U | MS | .. | .. | .. | .. | .. | ..
Ind 2.3 | Capacity building of BITC is conducted by December 2015 | NA | NA | .. | .. | .. | .. | .. | ..
Ind 2.4 | Capacity building of CBO's and IO's is conducted by December 2015 | NA | MS | .. | .. | .. | .. | .. | ..
Ind 2.5 | Capacity building of BOBS is conducted by December 2015 | NA | NA | .. | .. | .. | .. | .. | ..
Result Area Three: Business environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Log Frame Ind | Description of the Log frame Indicator | Progressive Rating codes | [6 empty] | Remarks
|  | Q3 2014 | Q4 2014 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 3.1 | Capacity building conducted on trade and specific negotiation skills | NA | S | .. | .. | .. | .. | .. | ..
Ind 3.2 | Improved Policy Framework to access finance | NA | HS | .. | .. | .. | .. | .. | ..
Ind 3.3 | Improved Business Environment (Ease of Doing Business) | NA | NA | .. | .. | .. | .. | .. | ..
Component Four: Management and Communications
Log Frame Ind | Description of the Log frame Indicator | Progressive Rating codes | [6 empty] | Remarks
|  | Q3 2014 | Q4 2014 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
NOTA | Performance Management and Communications | MS | HS | .. | .. | .. | .. | .. | ..
NOTA | Not Applicable | .. | .. | .. | .. | .. | .. | NA | Not Due to Start
HS | 4< HS <=5 | S | 3< S <=4 |  | MS | 2< MS <=3 |  | MU | 1< MU <=2
U | 0< U <=1 | HU | HU =0 |  | .. | .. | .. | .. | ..

## Evaluation
Results of Assesment of Completed Activities
S. No | Result Area | Activity | Feedback / Remrks on Completed Activities |  |  | Recommendations on Action to be taken
1 | . | . | . |  |  | .
2 | . | . | . |  |  | .
3 | . | . | . |  |  | .
4 | . | . | . |  |  | .
5 | . | . | . |  |  | .
6 | . | . | . |  |  | .
7 | . | . | . |  |  | .
8 | . | . | . |  |  | .
9 | . | . | . |  |  | .
Results of Assesment of Completed ActivityGroups Indicator Wise
S. No | Result Area | Log Frame Indicator | Contributing Activities Completed | Feedback / Remarks on Assesment Log Frame Indicator Wise |  |  | Recommendations on Action to be taken
1 | . | . | . | . |  | . | .
2 | . | . | . | . |  | . | .
3 | . | . | . | . |  | . | .
4 | . | . | . | . |  | . | .
5 | . | . | . | . |  | . | .
6 | . | . | . | . |  | . | .
7 | . | . | . | . |  | . | .
8 | . | . | . | . |  | . | .
9 | . | . | . | . |  | . | .
Lessons Learnt and Way forward Result Area and Activity Wise
S. No | Result Area | Activity | Lessons learnt in Execution |  | Remedial Action / Improvements Possible |  |  | Remarks
1 | . | . | . |  | . |  |  | .
2 | . | . | . |  | . |  |  | .
3 | . | . | . |  | . |  |  | .
4 | . | . | . |  | . |  |  | .
5 | . | . | . |  | . |  |  | .
6 | . | . | . |  | . |  |  | .
7 | . | . | . |  | . |  |  | .
8 | . | . | . |  | . |  |  | .

## Project Purpose
PROJECT PURPOSE
To improve the business environment in Botswana and stimulate economic diversification in the private sector. Develop and increase the role of SMMEs in the economy.
INDICATOR | BASELINE | TARGET | STATUS | TIME LAPSED (YEARS) | PROJECT PURPOSE ASSESSMENT | RATING INDICATOR
World Bank doing business ranking | 134 | 120 | 125 | 1 | MODERATELY SATISFACTORY | MS
Economic Diversification | 120 | 134 | 125 | 1 | MODERATELY SATISFACTORY | MS
Number of SMMEs | 40000 | 50000 | 47000 | 1 | HIGHLY SATISFACTORY | HS
Value and volume of exports | 650 | 750 | 600 | 1 | HIGHLY UNSATISFACTORY | HU

## Result Area 1
Result Area Activity Monitoring Report (Summary) : December 2014
RESULT AREA 1: | [8 empty] | Score | Rating Code
CAPACITY AND COMPETITIVENESS OF SMMEs AND COMMUNITY BASED ORGANISATION (CBO'S) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [8 empty] | 2.66 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements | Score | Rating Code
IND 1.1 | 3.5 | S | Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans | Projects on Beef Completed, Horticulture and tourism in progress | 4 | S
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans | Projects on Dairy, Leather, Piggery, Poultry and Goats in progress | 3 | MS
IND 1.2 | 2 | MU | Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014. |  |  | A 1.2 | Value Added wild / Natural Product Opportunity Study
[6 empty] | A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs | Study started and in progress | 2 | MU
IND 1.3 | 2.5 | MS | At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015. |  |  | A 1.3 | SME's Diagnostics (Baseline studies)
[6 empty] | A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | Auditof 70 SMME's out of 100 complete | 5 | HS
[6 empty] | A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | Activity yet to start | NA | NA
IND 1.4 | NA | NA | At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015
IND 1.5 | NA | NA | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015.
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | A 1.3.1 Diagnostics for 70 SMMe's |  |  | 5 | The task was successfully completed in time
2 | . |  |  | . | .
3 | . |  |  | . | .
4 | . |  |  | . | .

## Result Area 1 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 1: Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors
Activity No. | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Status / Achievements | Score |  | RATING | Reporting Responsibility and Method
1.1.1 | Structured value chains analysis and preparation of capacity building action plans | Previous studies and proposals | Three value chains identified that show potential to be strengthened in a published study | M & E Output Verification http://www.webtestopq.co.bw/documents/3QUtDc.pdf | 2014-08-18 | 2015-02-28 | Projects on Beef Completed, Horticulture and tourism in progress | 4 | SATISFACTORY | S | BOCCIM Staff – direct system update
1.1.2 | Emerging value chains analysis and preparation of capacity building action plans | No action plan exists | Five value chains in eight sub-sector capacity building actions plans to support SMMEs and IOs are developed and validated by February 2015 | PSDP M&E Report; Analysis and Development Study report and SMMEs Audit reports | 2014-07-30 | 2015-02-28 | Projects on Dairy, Leather, Piggery, Poultry and Goats in progress | 3 | MODERATELY SATISFACTORY | MS | BOCCIM Staff – direct system update
1.2.1 | Development of action plans for honey and morula CBOs and SMMEs | No opportunity study exists | Honey and Morula Action Plan opportunity studies conducted and action plans for honey and morula in place by September 2014 | PSDP M&E Reports; Contracts Awarded and Reports Tracking the Contract; Action plans Completed | 2014-06-16 | 2014-09-30 | Study started and in progress | 2 | MODERATELY UNSATISFACTORY | MU | BOCCIM Staff – direct system update
1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | No PSDP audit and need assessment | 100 SMME’s are audited | PSDP M&E Reports; SMME diagnostic report | 2014-07-14 | 2014-11-07 | Audit of 70 SMMEs out of 100 complete | 5 | HIGHLY SATISFACTORY | HS | BOCCIM Staff – direct system update
1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, public works including energy efficiency | No PSDP tailored capacity training done | 70 SMMe's and 30 Micro enterprises as well as CBOs are audited and an Action Plan for Capacity Building developed and implemented by Dec 2015 ; 10 SMMEs are implementing environmental protection plans | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2015-01-05 | 2015-12-30 | The activity has not started as it is planned for Jan 2015, hence the number of SMME’S & CBO’s to be trained is yet to be determined. | NA | NA | NA | BOCCIM Staff – direct system update
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | . | . | .
Note on H7: Kabita: As per the December 11 report to MC 70 SME's havew been audited so the score of 0 is too low.

## Result Area 2
Result Area Activity Monitoring Report (Summary) : December 2014
RESULT AREA 2: | [8 empty] | Score | Rating Code
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced. | [8 empty] | 2.9 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements | Score | Rating Code
IND 2.1 | 3.33 | S | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 10% by December 2015. • PSDP Web based M&E system is operational by December 2014. |  |  | A 2.1 | Capiciyty Building of BOCCIM
[6 empty] | A 2.1.1 | Internal Monitoring and Evaluation of PSDP | Monitoring and Evaluation Portal is operational to be followed by training | 4 | S
[6 empty] | A 2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | BOCCIM action plan as an apex body elaborated | 4 | S
[6 empty] | A 2.1.3 | BOCCIM capacity building to render better services to its members | In Progress | 2 | MU
[6 empty] | A 2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | Not Started | NA | NA
IND 2.2 | 3 | MS | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs - June 2015. |  |  | A 2.1.4 | Assistance to the establishment of market intelligence information system/web based platform for networking and information / Public and private dialogue, etc… | In Progress | 3 | MS
Ind 2.3 | NA | NA | Capacity building of BITC is conducted • An export strategy with respective action plan is adopted and implementation of the action plan starts in December 2015. • Three partnerships are established with external trading partners by December 2015. • At least 10 of the PSDP targeted SMMEs are qualified for export by BITC by December 2015. |  |  | A 2.2 | Capacity Building of BITC
[6 empty] | A 2.2.1 | Assistance to BITC in Export Development and Promotion | Not Started | NA | NA
[6 empty] | A 2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | Not Started | NA | NA
Ind 2.4 | 2.5 | MS | Capacity building of Intermediary Organisations and sector associations is conducted. • Number of private firms using TSIs and BDSPs services increased by 10% by December 2015. • At least 70% of SMMEs and CBOs benefiting from PSDP intervention are satisfied with the quality of service provided by IOs and BDSPs. • Recommendations developed and submitted to MTI by December 2015 for improving competitiveness and export of Botswana Beef. • At least three new products and/or services introduced by IOs by December 2015. |  |  | A 2.3 | Capacity Building of Intermediart Organisations and Sector Associations
[6 empty] | A 2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) | Only three training programmes done | 3 | MS
| 0 |  |  |  |  | A 2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | Only Beef PPD is done | 2 | MU
[6 empty] | A 2.3 3 | Assistance to the tourism sector in partnership with BTO and HATAB | Not Started | NA | NA
[6 empty] | A 2.3.4 | Assistance to honey sector associations | Not Started | NA | NA
IND 2.5 | NA | NA | Capacity building conducted for BOBS on Quality Certification • Draft National Quality Policy is developed and submitted to MTI by June 2015. • BOBS staff members are trained in audit and inspection services and ten service providers are capacitated in auditing and certification of agro-industry (horticulture, diary, beef) and manufacturing by December 2015. • SMME certification system is in place by September 2015. |  |  | A 2.4 | Capacity Building for BOBS on Quality and Certification
[6 empty] | A 2.4.1 | Support the development of a National Quality Policy | Not Started | NA | NA
[6 empty] | A 2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | Not Started | NA | NA
[6 empty] | A 2.4.3 | Support the process of certification for SMEs | Not Started | NA | NA
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | . |  |  | . | .
2 | . |  |  | . | .
3 | . |  |  | . | .
4 | . |  |  | . | .

## Result Area 2 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 2: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Activity No. | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Status / Achievements | Score | RATING CODE | RATING | Reporting Responsibility
2.1.1 | Internal Monitoring and Evaluation of PSDP | Web based M&E system is not available | Web based M&E system is fully operational | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | Monitoring and Evaluation Portal is operational to be followed by training | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | Review of Mandates not taken place | BOCCIM established as Apex Body for Private Sector in Botswana | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | BOCCIM action plan as an apex body elaborated | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
2.1.3 | BOCCIM capacity building to render better services to its members | No Membership satisfaction survey carried out | BOCCIM Membership increases by 10% by December 2015 | PSDP M&E Reports; | 2014-03-28 | 2015-12-01 | In Progress | 2 | MODERATELY UNSATISFACTORY | MU | CDE / BOCCIM Staff – direct system update;
2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | DNA | DNA | PSDP M&E Reports; | DNA | 2015-12-01 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.1.4 | Assistance to the establishment of market intelligence information system/web based platform | No MIIS | An operational MIIS | PSDP M&E Reports; Hits on website | 2014-10-01 | 2015-06-30 | In progress (One visit by Consultant) | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
2.2.1 | Assistance to BITC in Export Development and Promotion | No Export Strategy is in place at BITC. The PSDP identified SMMES are not exporting. | One export strategy implemented, 3 partnerships are established with external trading partners outside Botswana’s borders. Ten SMMEs are export ready. | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Only three training programmes done | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Only Beef PPD is done | 2 | MODERATELY UNSATISFACTORY | MU | CDE / BOCCIM Staff – direct system update;
2.3.3 | Assistance to the tourism sector in partnership with BTO and HATAB | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.3.4 | Assistance to honey sector associations | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.4.1 | Support the development of a National Quality Policy | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
2.4.3 | Support the process of certification for SMEs | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2015-01-05 | 2015-12-30 | Not Started | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | . | . | .

## Result Area 3
Result Area Activity Monitoring Report (Summary) : December 2014
RESULT AREA 3: | [6 empty] | Score | Rating Code
Business environment (reduction of red tape and pilot on accessing finance) for enterprises is enhanced. | [6 empty] | 3.25 | S
Log Frame Indicator Number | Score | Rating Code | Description of Indicator | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements | Score | Rating Code
IND 3.1 | 4 | S | Capacity building conducted on trade and specific negotiation skills • Recommendations submitted by PSDP to MTI on the reduction of; the cost of doing business; and the cost and time required for registration and operationalization of SMMEs in Botswana by June 2015. • Members of the Trade Facilitation and Advisory Group (TFAG) and National Committee on Trade Policy and Negotiations (NCTPN) are trained on MTI Trade Capacity Building Strategy by June 2015. • At least 10 IO staff members are trained in EPA implementation by September 2015 | A 3.1 | Capacity Building on Trade and Specific Negotiation Skills
|  |  |  | A 3.1.1 | Establish trade facilitation group and provide capacity building | Trade Facilitation Advisory Group and NTCPN needs assesment Developed | 4 | S
|  |  |  | A 3.1.2 | Training of TFAG and NTCPN on negotiation and trade facilitation | Yet to start | NA | NA
|  |  |  | A 3.1.3 | Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation | Yet to start | NA | NA
IND 3.2 | 2.5 | MS | Improved Policy Framework to access finance • At least 1 new financial product (post loan support mechanism) targeting SMMEs is introduced by commercial banks and or other financial institutions supporting SMME financing by December 2015 • 30 SMME’s under PSDP are assisted to prepare their business plans for submission to commercial banks and other financial institutions by December 2015. • At least 5 PSDP SMMEs assisted are accessing finance by February 2016. • Micro finance policy framework is established and presented to Government for adoption by September 2014. • A microfinance Act is drafted and submitted to government by September 2014. | A 3.2 | Policy Framework to Improve Access to Finance
|  |  |  | A 3.2.1 | Draft a microfinance policy framework | Draft Microfinance Policy Developed and submitted to MTI and MFDP | 5 | HS
|  |  |  | A 3.2.2 | Draft a micro-finance Act for Botswana | Yet to start | NA | NA
IND 3.3 | NA | NA | Improved Business Environment (Ease of Doing Business) • A compilation of recommendations submitted to MTI by December 2015 to simplify tax registration with a view to improve tax compliance by SMMEs. • A compilation of labour laws affecting SMMEs with recommendations for reforms submitted to MTI by December 2015. | A 3.3 | Improving Business Environment (Ease of Doing Business)
|  |  |  | A 3.3.1 | Review the registration process and tax compliance | Yet to start | NA | NA
|  |  |  | A 3.3.2 | Review of labour laws and recommend labour productivity improvement strategies | Yet to start | NA | NA

## Result Area 3 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 3: Business Environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Activity No. | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Status / Achievements | Score | RATING CODE | RATING | Reporting Responsibility
3.1.1 | Establish trade facilitation group and provide capacity building | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Trade Facilitation Advisory Group and NTCPN needs assesment developed | 4 | Satisfactory | S | CDE / BOCCIM Staff – direct system update;
3.1.2 | Training of TFAG and NTCPN on negotiation and trade facilitation | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
3.1.3 | Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
3.2.1 | Draft a microfinance policy framework | No Policy | DNA | Activity Progress Reports | DNA | DNA | Draft Microfinance Policy Developed and submitted to MTI and MFDP | 5 | Highly Satisfactory | HS | CDE / BOCCIM Staff – direct system update;
3.2.2 | Draft a micro-finance Act for Botswana | No Act | DNA | Activity Progress Reports | DNA | Dec 154 | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
3.3.1 | Review the registration process and tax compliance | No Review | DNA | Activity Progress Reports | DNA | 2015-12-30 | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
3.3.2 | Review of labour laws and recommend labour productivity improvement strategies | DNA | DNA | Activity Progress Reports | DNA | 2015-12-30 | Yet to start | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | . | . | .

## Component 4
Monitoring and Evaluation Report for Quarter Ending December 2014
Component 4 | [8 empty] | Score | Rating Code
Common Activities Management and Communications | [8 empty] | 5 | HS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements | Score | Rating Code
NA | NA | NA | NA |  |  | A 4.1 | Recruitment of a service provider to develop the Monitoring and evaluation System | Activity A 4.1 Completed Service Provider in place since June 2014 and M&E Progress Reporting shifted to Result Area 2 A 2.1.1 | 5 | HS
[6 empty] | A 4.2 | Design and Imnplementation of a PSDP Communication and Visibilituy Plan | Communication and visibility plan approved; PSDP News letter launched; 4 press releaseds of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced | 5 | HS
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | A 4.1 Recruitment of a service provider for Development of M&E System |  |  | 5 | Service Provider recruited by May 2014 and is on the job since then
2 | A 4.2 Implementation Agency for Communications Plan |  |  | 5 | Service Provider recruited by May 2014 and is on the job since then
3 | . |  |  | . | .
4 | . |  |  | . | .

## Component 4(D)
Monitoring and Evaluation Report for Quarter Ending December 2014
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY
Activity No. | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Status / Achievements | Score | RATING CODE | RATING | Reporting Responsibility
4.1 | Recruitment of a service provider for the design of PSDP Monitoring and Evaluation (M&E) System | No M&E System | Online M&E System operational | Consultants engaged and system developed | 28-05-14 | 31-01-16 | Activity A 4.1 Completed Service Provider in place since June 2014 and M&E Progress Reporting shifted to Result Area 2 A 2.1.1 | 5 | NA | NA | CDE / BOCCIM Staff – direct system update;
4.2 | Design and implement PSDP Communication and Visibility Plan | No Communication and Visibility Plan | Effective implementation of the Communicaiton and Visibility Plan | Plan is developed | 14/05/2014 | 14-01-16 | Communication and visibility plan approved; PSDP News letter launched; 4 press releaseds of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced. | 5 | NA | NA | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Due to Start |  | DNA | Data Not Avatlable |  | . | . | . | .

## Logframe
PSDP LOGICAL FRAME
Intervention Logic | Objectively Verifiable Indicators | Source of Verification
OVERALL OBJECTIVE | Botswana maintains positive economic growth, with increased contribution from the private sector. | National economic statistics
To contribute to economic growth, employment creation and diversification resulting in the reduction of poverty |  | Reports by UN, IMF, World Bank, OECD and AU
PROJECT PURPOSE | Ease of doing business in Botswana improved | Doing Business indicators WB (access to credit, trading across borders)
To improve the business environment in Botswana and stimulate economic diversification in the private sector. Develop and increase the role of SMMEs in the economy. | Increased number of SMMEs in economic production, exports and employment | Botswana Business surveys
| Increased contribution by the private sector to the GDP | Central Bureau of Statistics indicators
Result Area 1: | Ind.1.1 Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 | Contracts Awarded and Reports Tracking the PSDP Monitoring and evaluation (M&E) Reports SMMEs Audit reports Capacity building workshop reports BOBS’s SMME quality improvement report
Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Ind. 1.2: Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014.
Ind.1.3: At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015.
Ind.1.4: At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015.
Ind.1.5: 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015.
Result Area 2: | Ind.2.1: BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 10% by December 2015. • PSDP Web based M&E system is operational by December 2014. | PSDP M&E Reports BOCCIM new Constitution BOCCIM Strategy Plan 2014-2016 BOCCIM Annual Reports BOCCIM membership satisfaction survey report PSDP M&E Web portal
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
| Ind.2.2: A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs - June 2015 | PSDP M&E Reports TSIs and BDSPs annual reports
| Ind.2.3: Capacity building of BITC is conducted • An export strategy with respective action plan is adopted and implementation of the action plan starts in December 2015. • Three partnerships are established with external trading partners by December 2015. • At least 10 of the PSDP targeted SMMEs are qualified for export by BITC by December 2015. | Contracts Awarded and Reports Tracking the Contract PSDP M&E Reports SMME annual reports BITC annual reports MTI annual reports
| Ind 2.4: Capacity building of Intermediary Organisations and sector associations is conducted. • Number of private firms using TSIs and BDSPs services increased by 10% by December 2015. • At least 70% of SMMEs and CBOs benefiting from PSDP intervention are satisfied with the quality of service provided by IOs and BDSPs. • Recommendations developed and submitted to MTI by December 2015 for improving competitiveness and export of Botswana Beef. • At least three new products and/or services introduced by IOs by December 2015. | Contracts Awarded and Reports Tracking the Contract PSDP M&E Reports TSI and BSDPs annual reports SMME survey reports Tourism industry reports
| Ind 2.5: Capacity building conducted for BOBS on Quality Certification • Draft National Quality Policy is developed and submitted to MTI by June 2015. • BOBS staff members are trained in audit and inspection services and ten service providers are capacitated in auditing and certification of agro-industry (horticulture, diary, beef) and manufacturing by December 2015. • SMME certification system is in place by September 2015. • Draft National Quality Policy is developed and submitted to MTI by June 2015. • BOBS staff members are trained in audit and inspection services and ten service providers are capacitated in auditing and certification of agro-industry (horticulture, diary, beef) and manufacturing by December 2015. • SMME certification system is in place by September 2015. | PSDP M&E Reports BOBs annual reports
Result Area 3 | Ind.3.1: Capacity building conducted on trade and specific negotiation skills • Recommendations submitted by PSDP to MTI on the reduction of; the cost of doing business; and the cost and time required for registration and operationalization of SMMEs in Botswana by June 2015. • Members of the Trade Facilitation and Advisory Group (TFAG) and National Committee on Trade Policy and Negotiations (NCTPN) are trained on MTI Trade Capacity Building Strategy by June 2015. • At least 10 IO staff members are trained in EPA implementation by September 2015. | Willingness and availability of MTI staff to participate Trade Facilitation Advisory Group is operational and effective Willingness and availability of banking sector to pparticipate. Willingness of SMMEs to register for taxes
Business environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
| Ind.3.2: Improved Policy Framework to access finance • At least 1 new financial product (post loan support mechanism) targeting SMMEs is introduced by commercial banks and or other financial institutions supporting SMME financing by December 2015. • 30 SMME’s under PSDP are assisted to prepare their business plans for submission to commercial banks and other financial institutions by December 2015. • At least 5 PSDP SMMEs assisted are accessing finance by February 2016. • Micro finance policy framework is established and presented to Government for adoption by September 2014. • A microfinance Act is drafted and submitted to government by September 2014. | Contracts Awarded and Reports Tracking the Contract PSDP M&E Reports MFDP annual reports SMME reports Banks/financial institutions annual reports
| Ind.3.3: Improved Business Environment (Ease of Doing Business) • A compilation of recommendations submitted to MTI by December 2015 to simplify tax registration with a view to improve tax compliance by SMMEs. • A compilation of labour laws affecting SMMEs with recommendations for reforms submitted to MTI by December 2015 | PSDP M&E reports SMME audit reports World Bank Doing Business Report MTI reports