## Logframe
PSDP LOGICAL FRAME
Intervention Logic | Objectively Verifiable Indicators | Source of Verification
OVERALL OBJECTIVE | Botswana maintains positive economic growth, with increased contribution from the private sector. | National economic statistics
To contribute to economic growth, employment creation and diversification resulting in the reduction of poverty |  | Reports by UN, IMF, World Bank, OECD and AU
PROJECT PURPOSE | Ease of doing business in Botswana improved | Doing Business indicators WB (access to credit, trading across borders)
To improve the business environment in Botswana and stimulate economic diversification in the private sector. Develop and increase the role of SMMEs in the economy. | Increased number of SMMEs in economic production, exports and employment | Botswana Business surveys
| Increased contribution by the private sector to the GDP | Central Bureau of Statistics indicators
Result Area 1: | Ind.1.1 Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 | Contracts Awarded and Reports Tracking the PSDP Monitoring and evaluation (M&E) Reports SMMEs Audit reports Capacity building workshop reports BOBS’s SMME quality improvement report
Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Ind. 1.2: Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014.
Ind.1.3: At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015.
Ind.1.4: At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015.
Ind.1.5: 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015.
Result Area 2: | Ind.2.1: BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 10% by December 2015. • PSDP Web based M&E system is operational by December 2014. | PSDP M&E Reports BOCCIM new Constitution BOCCIM Strategy Plan 2014-2016 BOCCIM Annual Reports BOCCIM membership satisfaction survey report PSDP M&E Web portal
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
| Ind.2.2: A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs - June 2015 | PSDP M&E Reports TSIs and BDSPs annual reports
| Ind.2.3: Capacity building of BITC is conducted • An export strategy with respective action plan is adopted and implementation of the action plan starts in December 2015. • Three partnerships are established with external trading partners by December 2015. • At least 10 of the PSDP targeted SMMEs are qualified for export by BITC by December 2015. | Contracts Awarded and Reports Tracking the Contract PSDP M&E Reports SMME annual reports BITC annual reports MTI annual reports
| Ind 2.4: Capacity building of Intermediary Organisations and sector associations is conducted. • Number of private firms using TSIs and BDSPs services increased by 10% by December 2015. • At least 70% of SMMEs and CBOs benefiting from PSDP intervention are satisfied with the quality of service provided by IOs and BDSPs. • Recommendations developed and submitted to MTI by December 2015 for improving competitiveness and export of Botswana Beef. • At least three new products and/or services introduced by IOs by December 2015. | Contracts Awarded and Reports Tracking the Contract PSDP M&E Reports TSI and BSDPs annual reports SMME survey reports Tourism industry reports
| Ind 2.5: Capacity building conducted for BOBS on Quality Certification • Draft National Quality Policy is developed and submitted to MTI by June 2015. • BOBS staff members are trained in audit and inspection services and ten service providers are capacitated in auditing and certification of agro-industry (horticulture, diary, beef) and manufacturing by December 2015. • SMME certification system is in place by September 2015. • Draft National Quality Policy is developed and submitted to MTI by June 2015. • BOBS staff members are trained in audit and inspection services and ten service providers are capacitated in auditing and certification of agro-industry (horticulture, diary, beef) and manufacturing by December 2015. • SMME certification system is in place by September 2015. | PSDP M&E Reports BOBs annual reports
Result Area 3 | Ind.3.1: Capacity building conducted on trade and specific negotiation skills • Recommendations submitted by PSDP to MTI on the reduction of; the cost of doing business; and the cost and time required for registration and operationalization of SMMEs in Botswana by June 2015. • Members of the Trade Facilitation and Advisory Group (TFAG) and National Committee on Trade Policy and Negotiations (NCTPN) are trained on MTI Trade Capacity Building Strategy by June 2015. • At least 10 IO staff members are trained in EPA implementation by September 2015. | Willingness and availability of MTI staff to participate Trade Facilitation Advisory Group is operational and effective Willingness and availability of banking sector to pparticipate. Willingness of SMMEs to register for taxes
Business environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
| Ind.3.2: Improved Policy Framework to access finance • At least 1 new financial product (post loan support mechanism) targeting SMMEs is introduced by commercial banks and or other financial institutions supporting SMME financing by December 2015. • 30 SMME’s under PSDP are assisted to prepare their business plans for submission to commercial banks and other financial institutions by December 2015. • At least 5 PSDP SMMEs assisted are accessing finance by February 2016. • Micro finance policy framework is established and presented to Government for adoption by September 2014. • A microfinance Act is drafted and submitted to government by September 2014. | Contracts Awarded and Reports Tracking the Contract PSDP M&E Reports MFDP annual reports SMME reports Banks/financial institutions annual reports
| Ind.3.3: Improved Business Environment (Ease of Doing Business) • A compilation of recommendations submitted to MTI by December 2015 to simplify tax registration with a view to improve tax compliance by SMMEs. • A compilation of labour laws affecting SMMEs with recommendations for reforms submitted to MTI by December 2015 | PSDP M&E reports SMME audit reports World Bank Doing Business Report MTI reports
Note on B18: Author: This indicator is not showing fully.

## Overall Objective
Overall Objective
To contribute to economic growth, employment creation and diversification Resulting in the Reduction of Poverty
INDICATOR | BASELINE | TARGET | STATUS | TIME (YEARS) | OVERALL OBJECTIVE ASSESSMENT | RATING INDICATOR
Annual GDP Growth | 5 | 7 | 6 | 1 | HIGHLY SATISFACTORY | HS
Employment creation | 20000 | 50000 | 25000 | 1 | MODERATELY UNSATISFACTORY | MU
Gross capital formation, private sector (% of GDP) | 35 | 40 | 39 | 1 | HIGHLY SATISFACTORY | HS
Note on D3: Author: Have we updated these values?

## Project Purpose
PROJECT PURPOSE
To improve the business environment in Botswana and stimulate economic diversification in the private sector. Develop and increase the role of SMMEs in the economy.
INDICATOR | BASELINE | TARGET | STATUS | TIME LAPSED (YEARS) | PROJECT PURPOSE ASSESSMENT | RATING INDICATOR
World Bank doing business ranking | 134 | 120 | 125 | 1 | MODERATELY SATISFACTORY | MS
Economic Diversification | 120 | 134 | 125 | 1 | MODERATELY SATISFACTORY | MS
Number of SMMEs | 40000 | 50000 | 47000 | 1 | HIGHLY SATISFACTORY | HS
Value and volume of exports | 650 | 750 | 600 | 1 | HIGHLY UNSATISFACTORY | HU
Note on A7: Author: Is this a value of it’s the volume of exports?
Note on D3: Author: Have these been updated?

## Overall Summary
Monitoring and Evaluation Report (Summary) : Quarter ending 30 June 2015
Result Area / Component |  |  | Rating | Rating Code | Remarks on Significant Achievements
RESULT AREA 1: CAPACITY AND COMPETITIVENESS OF SMME’S AND COMMUNITY BASED ORGANISATION (CBOS) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS |  |  | 3 | MS | There has been quite an overall improvement from the last quarter particularly in activity A1.4. There are however a number of alerts which must be attended to in order to prevent the rating from being affected negatively.
RESULT AREA 2: SERVICE DELIVERY OF TARGETED INTERMEDIARY ORGANISATIONS (IOs) AND BUSINESS DEVELOPMENT SERVICE PROVIDERS (BDSP) IS ENHANCED |  |  | 3 | MS | There has been a slight improvement in this result area as a result of increased scores in A2.3.1 and A2.3.2 and activities commencing under A2.4. Some alerts have been given which would have to be attended to.
RESULT AREA 3: BUSINESS ENVIRONMENT FOR ENTERPRISES IS IMPROVED (REDUCTION OF RED TAPE AND PILOT ON IMPROVED ACCESS TO FINANCE BY SMMEs) |  |  | 4 | S | Very little change from the last report. The indicator is doing quite well and will be monitored closely in going forward.
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY |  |  | 5 | HS | No Change visible as compared to previous report
4< HS <=5 | 3< S <=4 | 2< MS <=3 | 1< MU <=2 |  | 0< U <=1 | HU =0

## Progressive
Performance of each Log Frame Indicator Progressive Quarter Wise (Summary) Quarter ending 30 June 2015
Result Area One :Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors)
Log Frame Indicator Number | Description of the Log frame Indicator | Progressive Rating codes | [7 empty] | Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 1.1 | Action plans to support SMMEs and IOs are developed foe eight valuchains and eight sub sectors by February 2015 | NA | S | S | S | MS | . | . | . | .
Ind 1.2 | Studies are carried out for development of Honey and Morula Value Chains by September 2014. | HU | MU | MS | MS | MU | . | . | . | .
Ind 1.3 | At least 70 SMMEs are strengthened on management, operations by December 2015. | MS | MS | MU | MU | S | . | . | . | .
Ind 1.4 | 30 CBO’s are trained on management, marketing, quality standards and accounting by December 2015 | NA | NA | HU | HU | MS | . | . | . | .
Ind 1.5 | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. | NA | NA | HU | HU | S | . | . | . | .
Result Area Two: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Log Frame Indicator Number | Description of the Log frame Indicator | NA HU MS NA NA: Progressive Rating codes; . . . . .: Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 2.1 | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana and M&E is Operational by December 2014 | MU | S | S | S | S | . | . | . | .
Ind 2.2 | A web based market intelligence information system is developed for use by SMMEs - June 2015. | U | MS | MS | S | S | . | . | . | .
Ind 2.3 | Capacity building of BITC is conducted by December 2015 | NA | NA | U | MS | MS | . | . | . | .
Ind 2.4 | Capacity building of CBO's and IO's is conducted by December 2015 | NA | MS | MS | MS | S | . | . | . | .
Ind 2.5 | Capacity building of BOBS is conducted by December 2015 | bar: U NA NA to . . .
Result Area Three: Business environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Log Frame Indicator Number | Description of the Log frame Indicator | U NA NA: Progressive Rating codes; . . .: Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
Ind 3.1 | Capacity building conducted on trade and specific negotiation skills | NA | S | S | S | S | . | . | . | .
Ind 3.2 | Improved Policy Framework to access finance | NA | HS | MS | MS | HS | . | . | . | .
Ind 3.3 | Improved Business Environment (Ease of Doing Business) | NA | NA | MS | MU | S | . | . | . | .
Component Four: Management and Communications
Log Frame Indicator Number | Description of the Log frame Indicator | NA NA: Progressive Rating codes; . .: Remarks
|  | Q3 2014 | Q4 2014 | INTERIM 28th Feb 2015 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2016
NA | Performance Management and Communications | MS | HS | HS | HS | HS | . | . | . | .
. | . | bar: NA NA to . .
NA | Not Applicable | . | . | . | . | . | . | . | NA | Not Due to Start
HS | 4< HS <=5 | S | 3< S <=4 |  |  | MS | 2< MS <=3 |  | MU | 1< MU <=2
U | 0< U <=1 | HU | HU =0 |  |  | . | . | . | . | .

## Result Area 1
Result Area Activity Monitoring Report (Summary) : Quarter Ending 30 June 2015
RESULT AREA 1: | [12 empty] | Sub- Activity Score | Score | Rating Code
CAPACITY AND COMPETITIVENESS OF SMMEs AND COMMUNITY BASED ORGANISATION (CBO'S) INCLUDING VALUE CHAINS IS STRENGTHENED, IN A SELECTED NUMBER OF SECTORS | [12 empty] | . | 2.96 | MS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 1.1 | 3 | MS | Eight (8) Value Chains in eight (8) sub sectors are identified and action plans to support SMMEs and IOs developed and validated by February 2015 |  |  | A 1.1 | Value Chains Analysis and Development
[6 empty] | A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Projects on Beef Completed and the final VC report submitted October 2014. Pursuant to the action plans of the report and the recommendations made, three action items are being implemented. (1) Management tools for Commercial Farmers (2) Upgrading capacity of Farmers Association. (3) Technical Tools of graduating communal Farmers. Horticulture and tourism in progress. The Horticulture report has been received and is now under review (18 June 2015). Tourism VCAD: received and currently under review (26 June 2015). Reports have been distributed to the stakeholders. |  |  |  |  | . | 3 | MS
[6 empty] | A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | All Five Final reports submitted by the consultant and have been reviewed by CDE as of 25 February 2015. Reformatted final report received by PSDP for comments to the consultants by 5 April 2015. Feedback on new report format submitted to HCL, 10 April 2015. Follow up to be made on final submission of all reports. Comments provided to HCL by 22 April 2015. An organisation for implementing action plans will be identified in October 2015. |  |  |  |  | . | 3 | MS
IND 1.2 | 2 | MU | Two value added wild / natural product opportunity studies are carried out with respective development and action plans for honey and morula CBOs and SMMEs by September 2014. |  |  | A 1.2 | Value Added wild / Natural Product Opportunity Study
[6 empty] | A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | Action plan for Honey submitted and Morula being finalised. Reports received and approved. Final Payment being processed. Honey Technical Guide under evaluation (follow up actions). Secondary actions based on recommendations to be elaborated. Recruitment of Honey Expert to assist SMMEs and CBOs under review. No progress on Morula. Field missions have been completed. Recruitment of Honey Expert to assist SMMEs and CBOs under review. Contract submitted for approval. It is expected that capacity building and implementation of action plans from the report will begin in September 2015. |  |  |  |  | . | 2 | MU
IND 1.3 | 4 | S | At least 70 SMMEs are strengthened on management, operations (including quality, standards and certification) in order to be more competitive in the local, regional and international market through grouped assistance (training workshops) and individual coaching by December 2015. |  |  | A 1.3 | SME's Diagnostics (Baseline studies)
[6 empty] | A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | Team for the Diagnosis of SMMEs (BWP 1410/01) |  | Team leader final report complete and submitted. What remains are administrative actions by the PSDP unit. |  |  | 4 | 4 | S
[8 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Local Consultants completed 22 SMMEs out of a total of ___22_SMME's. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | BNPC completed 28 out of _28 SMMEs. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | BIH Completed 15 out of 15 SMME's. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | LEA completed 9 SMME's including 2 CBO's. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | CEDA Completed 10/10 SMME's by 31st January 2015. What remains is administrative work to be completed by PSDP. |  |  | 4
[8 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Capacity Building of local staff on SMME Diagnostics File completed and closed |  |  | 4
[8 empty] | PSDP Mission Logistics (BWP/1404/01 |  | This entailed a provisional budget to cover SMME site visits by the PSDP team. The site visit reports have been completed and made available . This will then be able to trigger an evaluation from the M&E team. |  |  | 4
[8 empty] | SMME Diagnostics for Micros (File Number Requested) |  | These were completed. Interventions have started in which they will be attending workshops and they will also get mentors. |  |  | 4
IND 1.3 Cont.. | 4 Cont.. | S | Cont… |  |  | A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
[6 empty] | A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | Support to poultry sector (BWP 1444/01) |  | File de-committed due to the fact that the action was cancelled. No clear explanation as to why this was the case has been forthcoming. However, the poultry companies are being assisted with some attending Occupational Safety and Health Training, Business Management Training and TBT Certification (work in progress). |  |  | . | 2.25 | MS
[8 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | Progress made in that all consultants have begun their missions and the activity is on-going. Arrangements under way for ICT, Bakery and Poultry expert trips, foreseen in June-July Time frame. ICT expert expected 2 July 2015 – 25 July. |  |  | 3
IND 1.4 | 2.25 | MS | At least 30 micro-enterprises and Community Based Organisations (CBO’s) are trained on management, marketing, quality standards and accounting through grouped assistance by December 2015 |  |  |  |  | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | Progress made: Consultants have begun their missions and the activity is on-going. Economarkets to commence local support, following introduction meetings. Contracting on-going for local consultant support. Third expert identified, with possible start-up of October 2015. The first such intervention began in March and a number of similar interventions are on-going. Any evaluation on impact could reasonably be done from September. |  |  | 3
[8 empty] | Group training in management Finance (BWP 1446/01) |  | TOR and budget finalized. Selection and PA to be finalised. It is difficult to measure the extent of progress in the absence of a definite date for the group training. |  |  | 2
[8 empty] | Management training for Micros and CBOs |  | First training has been completed from 15th to 26th june 2015 and the next is scheduled for August 2015 |  |  | 2
[8 empty] | Group training in Business Planning for SMEs |  | TOR and budget finalized. Follow up PA. Budget approved. Contract being drafted for approval and signature. It is difficult to measure the extent of the progress in the absence of a definite date for the group training. |  |  | 2
[8 empty] | Participation of SMMEs to trade missions & trainings. In terms of trade missions and training the file number has still not been obtained since the last report |  | TOR and budget to be prepared. Again, it is difficult to measure the extent of the progress in the absence of a definite date for the group training. |  |  | 2
[8 empty] | Individual Coaching of SMMEs |  | Activity under preparation. Request file number. Financial offer and documentation to be submitted 13th April 2015 for commitment. There is a relationship that has been established with a few organisations that offer expert services. The delays are due to administrative constraints. |  |  | 2
[8 empty] | SME Development Experts |  | Activity under preparation. File number request is on-going |  |  | 2
IND 1.5 | 3.5 | S | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. |  |  | A1.5 | Technical Advisors and short term Experts
[6 empty] | A.1.5.1 |  | Technical advisor in Agro industry (BOT/1401/01) |  | Final report submitted. File closed. This advisor is in relation to A1.1.1 which action is taking place on the recommendations of this report. |  |  | 4 | 3.5 | S
[8 empty] | Service Provider for assistance in construction and public works (BWP1431/01) |  | Inception Report submitted. File number requested, awaiting profile of service provider. Modules for workshop sessions have been approved, workshop completed from 15th June to 19th June 2015. Workshop report and Sunday Standard article under preparation. A training report is expected before the end of July 2015. |  |  | 3.5
[8 empty] | Service Provider for assistance to clean energy companies (BWP/1426/01) |  | Final report was submitted in March 2015and the file has been closed well before the contract date lapsed. The service consisted of three missions: 1) Capacity needs assessment of 8 SMMEs, 2) Plant Assessments and Business Plans, 3) Feedback Meetings and Action Plans. An awareness training workshop was also conducted for 19 enterprises on 5th March 2015. |  |  | 3.5
[8 empty] | Short-term Experts (PSDP support staff) BWP/1305/01, BWP/1407/01, BWP/1311/01, BWP/1442/01 |  | Support to PSDP junior experts and interns. The following files have been closed (BWP/1305/01, BWP/1407/01, BWP/1311/01). The only active file is BWP/1442/01 which is the payment of PSDP experts and Interns. |  |  | 3
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< M S<=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA |  | Not Due to Start
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
S. No | Name of Activity |  |  | Rating | Alert / Lessons Learnt and Suggestions for way forward
1 | A1.1.1 Structured value chains analysis and preparation of capacity building Action plans |  |  | 3 | The contract expires in August 2015 and it was expected that this activity should have been completed two months before, which is in June. The activity is thus running behind schedule because action items are still being implemented and reviews for the reports on Horticulture and Tourism VCs still taking place with no deadlines when they would be complete. In the absence of work-plans, projecting targets has presented challenges for the progress of the activity and these should be developed as a matter of priority.
2 | A1.1.2 Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) |  |  | 3 | The internal review of the reports is on going and the dates have been changed from March to August 2015, as a result of the poor quality of the initial report. The project tools that show the extension, end and change of project activities and plans should be shared with the team as a whole so as to allow for their use by all relevant PSDP staff.
3 | A1.2.1 Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) |  |  | 3 | Some progress made, however the indicator score must be downgraded to Moderately Unsatisfactory because the activity was meant to be completed on 28 February but has not been completed yet.
4 | A 1.3.1 Diagnostics of SMMEs (BNPC, BIH, Local consultants) |  |  | 4 | The indicator should be upgraded to 4 due to the fact that reports have all been submitted. As well, all the audits have been completed and the team leader file has been closed. Payments for SMMEs (Interim and Final) to be followed up on.
5 | A 1.4.1 Capacity Building of SMME's and CBO's for upgrading their Competiveness |  |  | 2.25 | With regards to support to the SMEs by senior experts in service, expert missions have begun and are still on-going. The first such intervention began in March 2015 and a number of similar interventions are on-going. Any evaluation on impact could reasonably be done from September 2015. The score for these sub activity is thus upgraded. With regard to the Technical Support to SMMEs by Managers Without Boarders, the consultants have also begun their missions and the activity is on-going. The sub activity score is thus upgraded. In terms of the group training in management finance, Management training for Micros and CBOs, Group training in Business Planning for SMEs and Participation of SMMEs to trade missions & trainings, it is difficult to measure the extent of the progress in the absence of a definite date for the group training.
6 | A1.5.1 Technical Advisors and short term Experts |  |  | 3.5 | With the lack of a work-plan specifying the time frame for which the advisory services in the agro industry were to be conducted, it is difficult to assess whether such services were delivered on time. Until such clarity is resolved, then a scoring of satisfactory is appropriate. In terms of the activity pertaining to the Service provider for assistance in Construction and Public Works, the Workshop has taken place on time and the sub activity indicator should be upgraded. With respect to the short term experts support to PSDP staff, payments for BWP/1442/01 are still to be followed up on from the last quarterly report. The sub-activity score should thus receive a moderately satisfactory rating, even though the overall score of the Activity as a whole is satisfactory.
Note on F38: Author: I have made some comments in the detailed result area sheet which should be attended to and the responses should be reflected in this section. We really need to pay attention to lessons learnt and suggestions on way forward in order to add value to the process.
Note on F42: Author: What is the outcome of all these baseline studies? What have we learnt?
Note on K23: Author: Did the first intervention start in March 2015?

## Result Area 1 (D)
Monitoring and Evaluation Interim Report for the Quarter Ending 30 June 2015
Result Area 1: Capacity and Competitiveness of SMME’s and Community Based Organisation (CBOs) including value chains is strengthened, in a selected number of sectors
Contributing Activity Number | Description of Activity | BASELINE | TARGET | OUTPUT / SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievements |  |  |  |  | Score | Rating Code | Rating | Reporting Responsibility and Method
A 1.1 | Value Chains Analysis and Development
A 1.1.1 | Structured value chains analysis and preparation of capacity building Action plans (BWP 1310/01) | Previous studies and proposals | Three value chains identified that show potential to be strengthened in a published study | M & E Output Verification http://www.webtestopq.co.bw/documents/3QUtDc.pdf | 2014-08-18 | 2015-02-28 | Projects on Beef Completed and the final VC report submitted October 2014. Pursuant to the action plans of the report and the recommendations made, three action items are being implemented. (1) Management tools for Commercial Farmers (2) Upgrading capacity of Farmers Association. (3) Technical Tools of graduating communal Farmers. Horticulture and tourism in progress. The Horticulture report has been received and is now under review (18 June 2015). Tourism VCAD: received and currently under review (26 June 2015). Reports have been distributed to the stakeholders. |  |  |  |  | 3 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
A1.1.2 | Emerging value chains analysis and preparation of capacity building Action plans (BWP1314/01) | No action plan exists | Five value chains in eight sub-sector capacity building actions plans to support SMMEs and IOs are developed and validated by February 2015 | PSDP M&E Report; Analysis and Development Study report and SMMEs Audit reports | 2014-07-30 | 2015-02-28 | All Five Final reports submitted by the consultant and have been reviewed by CDE as of 25 February 2015. Reformatted final report received by PSDP for comments to the consultants by 5 April 2015. Feedback on new report format submitted to HCL, 10 April 2015. Follow up to be made on final submission of all reports. Comments provided to HCL by 22 April 2015. An organisation for implementing action plans will be identified in October 2015. |  |  |  |  | 3 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
A 1.2 | Value Added wild / Natural Product Opportunity Study
A 1.2.1 | Development of action plans for honey and morula CBOs and SMMEs (BWP 1414/01) | No opportunity study exists | Honey and Morula Action Plan opportunity studies conducted and action plans for honey and morula in place by September 2014 | PSDP M&E Reports; Contracts Awarded and Reports Tracking the Contract; Action plans Completed | 2014-06-16 | 2014-09-30 | Action plan for Honey Submitted and Morula being finalised. Reports received and approved. Final Payment being processed. Honey Technical Guide under evaluation (follow up actions). Secondary actions based on recommendations to be elaborated. Recruitment of Honey Expert to assist SMMEs and CBOs under review. No progress on Morula. Field missions have been completed. Recruitment of Honey Expert to assist SMMEs and CBOs under review. Contract submitted for approval. It is expected that capacity building and implementation of action plans from the report will begin in September 2015. |  |  |  |  | 2 | Moderately Unsatisfactory | MU | BOCCIM Staff – direct system update
A 1.3 | SME's Diagnostics (Baseline studies)
A 1.3.1 | Diagnostics of SMMEs (BNPC, BIH, Local consultants) | No PSDP audit and need assessment | 100 SMME’s are audited | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2014-07-14 | 2014-11-07 | Team for the Diagnosis of SMMEs (BWP 1414/01) |  | Team leader final report complete and submitted. What remains are administrative actions by the PSDP unit. |  |  | 4 | Satisfactory | S | BOCCIM Staff – direct system update
[7 empty] | SMME Diagnostics by Local Consultants (BWP 1412/01) |  | Local Consultants completed 22 SMMEs out of a total of ___22_SMME's. What remains is administrative work to be completed by PSDP.
[7 empty] | SME Diagnosis by BNPC (BWP/1411/01 and 02) |  | BNPC completed 28 out of _28 SMMEs. What remains is administrative work to be completed by PSDP.
[7 empty] | SMME Diagnosis by BIH (BWP/1417/01)) |  | BIH Completed 15 out of 15 SMME's. What remains is administrative work to be completed by PSDP.
[7 empty] | SMME Diagnostics by LEA (BWP/1430/01) |  | LEA completed 9 SMME's including 2 CBO's. What remains is administrative work to be completed by PSDP.
[7 empty] | SMME Diagnostics by CEDA (BWP/1430/01) |  | CEDA to Complete 10 SMME's by 31st January 2015
[7 empty] | Monitoring the SMME Audit Process (BWP/1439/01) |  | Capacity Building of local staff on SMMe Diagnostics File Completed and closed
[7 empty] | PSDP Mission Logistics (BWP/1404/01 |  | This entailed a provisional budget to cover SMME site visits by the PSDP team. The site visit reports have been completed and made available . This will then be able to trigger an evaluation from the M&E team.
[7 empty] | SMME Diagnostics for Micros (File Number Requested) |  | These were completed. Interventions have started in which they will be attending workshops and they will also get mentors.
A 1.4 | Capacity Building of SMME's and CBO's for upgrading their Competiveness
A 1.4.1 | Group training and individual coaching of SMMEs/CBOs in agro-industries, manufacturing, tourism, ICT, Public works including energy efficiency | No PSDP tailored capacity training done | 70 SMMe's and 30 Micro enterprises as well as CBOs are audited and an Action Plan for Capacity Building developed and implemented by Dec 2015 ; 10 SMMEs are implementing environmental protection plans | PSDP M&E Reports, Capacity building workshop reports, Contracts awarded and tracking reports | 2015-01-05 | 2015-12-30 | Support to poultry sector (BWP 1444/01) |  | File de-committed due to the fact that the action was cancelled. No clear explanation as to why this was the case has been forthcoming. However, the poultry companies are being assisted with some attending Occupational Safety and Health Training, Business Management Training and TBT Certification (work in progress). |  |  | 2.25 | Moderately Satisfactory | MS | BOCCIM Staff – direct system update
[7 empty] | Technical Support to SMEs by Senior Expert in Service (BWP/1445/01) |  | Progress made in that all consultant have begun their missions and the activity is on-going. Arrangements under way for ICT, Bakery and Poultry expert trips, foreseen in June-July Time frame. ICT expert expected 2 July 2015 – 25 July.
[7 empty] | Technical support to SMMEs by Managers Without boarders (BWP 1448/01) |  | Progress made: Consultants have begun their missions and the activity is on-going. Economarkets to commence local support, following introduction meetings. Contracting on-going for local consultant support. Third expert identified, with possible start-up of October 2015. The first such intervention began in march and a number of similar interventions are on-going. Any evaluation on impact could reasonably be done from September.
[7 empty] | SMEs trade missions-Result Area1 (BWP 1313/01) |  | Three SMEs from the Diary sector participated at the 9th African Diary Conference and Exhibition held in Harare, Zimbabwe from the 24 to 26 September, 2013.
[7 empty] | Group training in management Finance (BWP 1446/01) |  | TOR and budget finalized. Selection and PA to be finalised. It is difficult to measure the extent of the progress in the absence of a definite date for the group training.
[7 empty] | Management training for Micros and CBOs |  | (1) Selection of service provider done. Follow up on-going. (2) Letters distributed to attendees and follow-up to commence on 27 May 2015. It is difficult to measure the extent of the progress in the absence of a definite date for the group training.
[7 empty] | Group training in Business Planning for SMEs |  | TOR and budget finalized. Follow up PA. Budget approved. Contract being drafted for approval and signature. It is difficult to measure the extent of the progress in the absence of a definite date for the group training.
[7 empty] | Participation of SMMEs to trade missions & trainings. In terms of trade missions and training the file number has still not been obtained since the last report |  | TOR and budget to be prepared. Again, it is difficult to measure the extent of the progress in the absence of a definite date for the group training.
[7 empty] | Individual Coaching of SMMEs |  | Activity under preparation. Request file number. Financial offer and documentation to be submitted 13th April 2015 for commitment. There is a relationship that has been established with a few organisations that offer expert services. The delays are due to administrative constraints.
[7 empty] | SME Development Experts |  | Activity under preparation. File number request is on-going.
A1.5 | Technical Advisors and Short-term Experts
A1.5.1 | Technical Advisors and Short-term Experts | . | 60 SMMEs and CBOs have participated in environmental awareness activities by December 2015. | . | 2014-09-11 | 2015-10-31 | Technical advisor in Agro industry (BOT/1401/01) |  | Final report submitted. File closed. This advisor is in relation to A1.1.1 which action is taking place on the recommendations of this report. |  |  | 3.5 | Satisfactory | S | BOCCIM Staff – direct system update
[7 empty] | Service Provider for assistance in construction and public works (BWP1431/01) |  | Inception Report submitted. File number requested, awaiting profile of service provider. Modules for workshop sessions have been approved, workshop completed from 15th June to 19th June 2015. Workshop report and Sunday Standard article under preparation. A training report is expected before the end of July 2015.
[7 empty] | Service Provider for assistance to clean energy companies (BWP/1426/01) |  | Final report was submitted in March 2015 and the file has been closed well before the contract date lapsed. The service consisted of three missions: 1) Capacity needs assessment of 8 SMMEs, 2) Plant Assessments and Business Plans, 3) Feedback Meetings and Action Plans. An awareness training workshop was also conducted for 19 enterprises on 5th March 2015.
[7 empty] | Short-term Experts (PSDP support staff) BWP/1305/01, BWP/1407/01, BWP/1311/01, BWP/1442/01 |  | Support to PSDP junior experts and interns. The following files have been closed (BWP/1305/01, BWP/1407/01, BWP/1311/01). The only active file is BWP/1442/01 which is the payment of PSDP experts and Interns.
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0 | .
NA | Not Applicable |  | DNA | Data Not Available |  | .
Note on G3: Author: Pse check all the end dates as we have activities that are on going beyond the dates mentioned here.
Note on J15: Author: Has CEDA completed this work?
Note on J20: Author: We need to demand for an explanation on the decommittment.
Note on J21: Author: Update on this as we are now past all these dates.
Note on J24: Author: What does PA stand for?
Note on J25: Author: Has the follow up been done and if so what is the feedback from the attendees?
Note on J26: Author: Meaning of PA?
Note on J27: Author: When is the budget to be prepared?
Note on J28: Author: Has the financial offer been submitted. What are the administrative constraints?
Note on J32: Author: The reports must be available by now and we need to summarise the outcomes here.
Note on J33: Author: Feedback from the workshop?

## Result Area 2
Result Area Activity Monitoring Report (Summary) : 30 June 2015
RESULT AREA 2: | [12 empty] | Sub-Activity Score | Score | Rating Code
Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSPs) is enhanced. | [12 empty] | . | 3.12 | S
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity | Remarks on Significant Achievements |  |  |  |  | . | Score | Rating Code
IND 2.1 | 3.7 | S | BOCCIM is restructured and established as an apex body representing the entire private sector in Botswana; and contributing to policy dialogue; and, membership has increased by 10% by December 2015. • PSDP Web based M&E system is operational by December 2014. |  |  | A 2.1 | Capacity Building of BOCCIM
[6 empty] | A 2.1.1 | Internal Monitoring and Evaluation of PSDP | The final M&E report has been formally accepted by PSDP. Training has been done and completed as planned. Evaluation of the Workshop has been done and the report has been submitted. Particip is working with the M&E until 31st December as per the contract. |  |  |  |  | . | 4 | S
[6 empty] | A 2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | Review of the mandates and establish BOCCIM as an Apex body (BOT/1402/01) |  | The final report with recommendations to establish BOCCIM as an apex body has been submitted. Payment to Particip has been made. BOCCIM is gearing to go onto the implementation stage. |  |  | . | 5 | HS
[8 empty] | Review of BOCCIM Constitution (BWP/1401/01 ) |  | Reports of the work done received for uploading by M&E team . BOCCIM is gearing to go onto the implementation stage. |  |  | .
[8 empty] | BOCCIM Membership Model (BWP/1402/01 ) |  | Reports of the work done received for uploading by M&E team. BOCCIM is gearing to go onto the implementation stage. |  |  | .
[8 empty] | Consultative Workshops for BOCCIM (BWP/1416/01 ) |  | Reports of the work done received for uploading by M&E team. The report says nothing about the workshops. Experts reviewing the mandates, membership model and the constitution all had focus groups that were spoken to as a means of validating the work undertaken. What is significant is that Amendments made to the constitution were approved by a Special General Meeting of BOCCIM. |  |  | .
[6 empty] | A 2.1.3 | BOCCIM capacity building to render better services to its members (BWP/1437/01) | Inception Report submitted for the upgrade of services. ToR and Budget Plan under preparation for the implementation of the BOCCIM Action Plan. With respect to the Exchange Application form, a response has been received and an alternative has since been identified. BOCCIM is now going to be working with Belgian Chambers and Paris Chambers. The interim payment has not been done as the consultant is still to submit his progress report for the upgrading services of BOCCIM activity. |  |  |  |  | . | 2 | MU
[6 empty] | A 2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | TOR and Budget still to be prepared. The activity falls under foreseen projects. |  |  |  |  | . | N/A | N/A
IND 2.2 | 4 | S | A web based market intelligence information system/platform for improving information dissemination and networking is developed for use by SMMEs - June 2015. |  |  | A 2.1.4 | Assistance to the establishment of market intelligence information system/web based platform for networking and information / Public and private dialogue, etc… (BWP/1434/01) | Benchmarking BOCCIM web Portal (BWP/1434/01) |  | Mission for the market intelligence completed in November 2014. Justification has been conducted and approved. The portal is up and running. Site hits reached 2429 visits by 30 June 2015. The portal however is not being used at a frequent rate. |  |  | . | 4 | S
[8 empty] | Feasibility study for the market intelligence being done under Value chain analysis for beef, tourism, and horticulture sectors (BWP/1310/01 ). |  | Web based platform for networking and information dissemination will be established under Result Area 2. The first mission was undertaken in December 2014. Mission report has been submitted and approved. Second mission completed. A project proposal on setting up of the MIIS was presented to BOCCIM and approved in principle. Activity is being paid under ITC budget. Preparation for market consultation dossier underway. 7 companies have been invited to submit profiles. This is likely to start around August or September 2015. |  |  | .
[8 empty] | Assistance to the establishment of market intelligence information |  | CVs shortlisted for market consultation. Next phase is to launch a market consultation for the implementation of the project proposal. |  |  | .
Ind 2.3 | 3 | MU | Capacity building of BITC is conducted • An export strategy with respective action plan is adopted and implementation of the action plan starts in December 2015. • Three partnerships are established with external trading partners by December 2015. • At least 10 of the PSDP targeted SMMEs are qualified for export by BITC by December 2015. |  |  | A 2.2 | Capacity Building of BITC
[6 empty] | A 2.2.1 | Assistance to BITC in Export Development and Promotion (BWP/1406/01) | Comments from BITC on the Inception Report received. The expected project outputs are ; (1) Trade portal complementing BITC website. A manual to be produced on the usage of the portal. (2) Training manuals for BITC staff and exporting firms. (3) Networking (database and contacts to be utilized by BITC). Needs assessment phase started on 20 January 2015 and has now been completed. Feedback meeting was held on the 7th of April. The activity is on-going and the consultant is on site. The Interim report has been submitted. The second mission will begin on the 30th of June 2015. Meetings to be held with BITC, the EU and the World Bank on 2nd July 2015 to discuss avoiding overlaps and repetition. |  |  |  |  | . | 3 | MS
[6 empty] | A 2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | Participation of IOs to trade missions & trainings – (BWP/1307/01) |  | WTO International Trade & Development course, Geneva, Switzerland. Completed?? |  |  | . | 3 | MS
[8 empty] | Participation of IOs to trade missions & trainings – (BWP/1308/01) |  | Support for training on Exports and Investment Promotion Programme –report submitted, Dublin Ireland. |  |  | .
[8 empty] | BITC sector association experts- .(BWP/1503/01) |  | Working with BITC staff to profile 10 companies in the respective sector. Inception report to be submitted. Work began in February 2015 to profile the ICT sector in mining for potential investors. PSDP ICT beneficiaries shared with the sector experts for profiling 5 companies. The activity is on-going. |  |  | .
Ind 2.3 | 3 | MS | Capacity building of Intermediary Organisations and sector associations is conducted. • Number of private firms using TSIs and BDSPs services increased by 10% by December 2015. • At least 70% of SMMEs and CBOs benefiting from PSDP intervention are satisfied with the quality of service provided by IOs and BDSPs. • Recommendations developed and submitted to MTI by December 2015 for improving competitiveness and export of Botswana Beef. • At least three new products and/or services introduced by IOs by December 2015. |  |  | A 2.3 | Capacity Building of Intermediary Organisations and Sector Associations
[6 empty] | A 2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) (BWP/1420/01) | 62 local staff from Intermediary Organisation were trained- the activity has been completed and closed. |  |  |  |  | . | 3 | MS
[6 empty] | A 2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | PPD Meeting on Beef Value Chain (BWP/1428/01) |  | Successfully Completed |  |  | . | 3 | MS
[8 empty] | Management Tools for Commercial farmers (BWP/1508/01) |  | The consultant was in Gaborone for his 2nd and final mission from the 22-30 May 2015. An interim report has been submitted by the Consultants and the interim payment is being processed. |  |  | .
[8 empty] | Technical Tools for Graduating communal farmers (BWP/1510/01) |  | The consultant has submitted his inception report and comments have been submitted to him for consideration. He is also planning for the workshop starting from the 26th June 2015. |  |  | .
[8 empty] | Upgrading Capacity of farmers Associations (BWP/1511/01) |  | The experts were in Gaborone for their first mission from the 23 June to 28 June which covered mainly the needs assessment for the Ghanzi and Ngamiland associations. This is mainly at inception phase and the experts will be continuing with their work. |  |  | .
[8 empty] | SME's Sensitisation on foot and mouth Diseases |  | TOR and Budget have already been prepared. File number to be requested. The file has been committed and the contract will be sent for a signature from the expert. There is no indication of the dates for when this is to be commenced and completed. |  |  | .
[6 empty] | A 2.3 3 | Assistance to the tourism sector in partnership with BTO and HATAB | Assistance to the tourism sector in partnership with BTO and HATAB |  | Actions related to this activity have been rolled out and are going as planned. Experts are currently on the ground. |  |  | . | 3 | MS
[8 empty] | HATAB Tourism conference (BWP/1443/01) |  | Activity completed and file has been de-committed.
[6 empty] | A 2.3.4 | Assistance to honey sector associations | TOR and Budget to be prepared to start April 2015 but as of 30th June 2015, this had not happened yet. |  |  |  |  | . | 0 | HU
IND 2.4 | 3.5 | S | Capacity building conducted for BOBS on Quality Certification Draft National Quality Policy is developed and submitted to MTI by June. |  |  | A 2.4 | Capacity Building for BOBS on Quality and Certification
[6 empty] | A 2.4.1 | Support the development of a National Quality Policy | Validation of report completed. |  |  |  |  | . | 3.5 | S
[6 empty] | A 2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | (Work in progress) |  |  |  |  | . | 3.5 | S
[6 empty] | A 2.4.3 | Support the process of certification for SMEs | TBT Workshop commenced with beneficiaries and service providers at BOBS |  |  |  |  | . | 3.5 | S
IND 2.5 | . | . | Technical Advisors and short term experts |  |  | A.2.5 | Technical Advisors and short term experts
[6 empty] | A2.5.1 | Technical Advisor in Tourism (BWP/1408/01) | Activity has been completed and closed. The file has been de-committed. |  |  |  |  | . | . | .
[6 empty] | A2.5.1 | Anthropologist for Tsodilo Hills | Contract has been signed and a follow-up expert mission is expected in the second half of the year. |  |  |  |  | . | . | .
[6 empty] | A2.5.2 | Short-term Experts (PSDP support staff) BWP/1305/01, BWP/1407/01 ,BWP/1311/01, BWP/1442/01 | Support rendered to PSDP Junior experts and interns |  |  |  |  | . | . | .
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | HATAB and BTO | U | 0< U <=1 | HU | HU=0 | NA | . | Not Due to Start
Progress or change since last report
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | A 2.1.2 Review of the mandates and establish BOCCIM as an Apex body |  |  | 5 | PSDP/CDE has completed all their responsibilities and handed over the reports to BOCCIM for further action therefore the score has been upgraded to 5. Following this action from BOCCIM, the M&E team also conduct a follow up.
S. No | Name of Activity |  |  | Rating | Alert / Observations, Lessons Learnt and Suggestions for way forward
1 | A 2.1.1 Internal Monitoring and Evaluation of PSDP |  |  | 4 | There is an improvement in the alignment of the weekly progress report and the inputs required for the M&E framework. Further efforts required to enhance the quality of the weekly report minutes and an improvement in the internal communication systems.
2 | A 2.1.2 Review of the mandates and establish BOCCIM as an Apex body |  |  | 5 | The activity has been completed and the file has been closed. BOCCIM is implementing recommendations. The reviewed constitution was accepted at a BOCCIM general meeting, and is now undergoing a process of registration with the competent authority. Work-plans and end of activity reports would be useful to trigger future evaluations.
3 | A2.1.3 BOCCIM capacity building to render better services to its members |  |  | 2 | The Interim report was yet to be submitted by the consultant in June and yet the contract was meant to end in April 2015.
4 | A 2.1.5 Training BOCCIM and other IOs in policy research, lobbying & advocacy |  |  | NA | ToR and Budget still to be prepared. The activity falls under foreseen projects.
5 | A 2.1.4 Assistance to the establishment of market intelligence information |  |  | 4 | The activity is due to start in the second half of the year and out of the three parts one is successfully completed and 2 are in progress. Web based platform still to be established under result area 2. Lessons can only be drawn from post-activity evaluation.
6 | A 2.2.1 Assistance to BITC in Export Development and Promotion (BWP/1406/01) |  |  | 3 | There have been significant achievements in the indicator and it should be upgraded to moderately satisfactory.
7 | A 2.2.2 Assistance to BITC for implementation of its new strategy (sector approach) |  |  | 3 | Out of the three parts two parts are completed. Inception report for profiling ICT and mining sectors for potential investors is still to be submitted. The indicator should be downgraded as a result of this. Sector profiles are to be presented to BITC management by the consultants. Final report still pending and the project is to be taken over by BITC.
8 | A 2.3.1 Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) (BWP/1420/01) |  |  | 3 | The activity has been completed and closed. M&E team to conduct an evaluation.
9 | A 2.3.2 Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export |  |  | 3 | There has been some achievements made in this activity and it should be upgraded to MU. It is now opportune to conduct impact evaluations because those who have been trained have put this training to use during the field diagnostics of their respective SMMEs.
11 | A2.3.4 Assistance to honey sector associations |  |  | 0 | Indicator should be changed to Highly unsatisfactory due to the fact the activity was supposed to begin in April but the ToRs and the budget are still to be prepared.
12 | A 2.4 Capacity Building for BOBS on Quality and Certification and all sub activities |  |  | 3.5 | These were supposed to start in May and April 2015. The terms of references are still to be prepared. Although the TBT Workshop commenced with beneficiaries and service providers at BOBS. The Activity should be awarded an unsatisfactory score because of the failure to meet the initial timetable.
Note on F43: Author: What does the last sentence mean?
Note on I17: Author: What are the learnings from this activity so far? What was the outcome of the meeting held on the 2nd of July?
Note on K18: Author: What was completed and what is the outcome?
Note on K19: Author: What was done under this activity and what is the outcome and learnings?
Note on K24: Author: Has this been completed?
Note on K25: Author: This is historic, please update this.

## Result Area 2(D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 2: Service delivery of targeted Intermediary Organisations (IOs) and Business Development Service Providers (BDSP) is enhanced
Contributing Activity Number | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievement |  | Score | RATING CODE | RATING | Reporting Responsibility
A 2.1 | Capacity Building of BOCCIM
A 2.1.1 | Internal Monitoring and Evaluation of PSDP | Web based M&E system is not available | Web based M&E system is fully operational | PSDP M&E Reports; | 2010-03-27 | 2011-11-30 | The final M&E report has been formally accepted by PSDP. Training has been done and completed as planned. Evaluation of the Workshop has been done and the report has been submitted. Particip is working with the M&E until 31st December as per the contract. |  | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
A 2.1.2 | Review of the mandates and establish BOCCIM as an Apex body | Review of Mandates not taken place | BOCCIM established as Apex Body for Private Sector in Botswana | PSDP M&E Reports; | 2010-03-27 | 2011-11-30 | Review of the mandates and establish BOCCIM as an Apex body (BOT/1402/01) | The final report with recommendations to establish BOCCIM as an apex body has been submitted. Payment to Particip has been made. BOCCIM is gearing to go onto the implementation stage. | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
[7 empty] | Review of BOCCIM Constitution (BWP/140/01) | Reports of the work done received for uploading by M&E team . BOCCIM is gearing to go onto the implementation stage.
[7 empty] | BOCCIM Membership model (BWP/1402/01) | Reports of the work done received for uploading by M&E team. BOCCIM is gearing to go onto the implementation stage.
[7 empty] | Consultative Workshop for BOCCIM (BWP/1416/01) | Reports of the work done received for uploading by M&E team. The report says nothing about the workshops. Experts reviewing the mandates, membership model and the constitution all had focus groups that were spoken to as a means of validating the work undertaken. What is significant is that Amendments made to the constitution were approved by a Special General Meeting of BOCCIM.
A 2.1.3 | BOCCIM capacity building to render better services to its members | No Membership satisfaction survey carried out | BOCCIM Membership increases by 10% by December 2015 | PSDP M&E Reports; | 2010-03-27 | 2011-11-30 | Inception Report submitted for the upgrade of services. ToR and Budget Plan under preparation for the implementation of the BOCCIM Action Plan. With respect to the Exchange Application form, a response has been received and an alternative has since been identified. BOCCIM is now going to be working with Belgian Chambers and Paris Chambers. The interim payment has not been done as the consultant is still to submit his progress report for the upgrading services of BOCCIM activity. |  | 2 | MODERATELY UNSATISFACTORY | MU | CDE / BOCCIM Staff – direct system update;
A 2.1.5 | Training BOCCIM and other IOs in policy research, lobbying & advocacy | DNA | DNA | PSDP M&E Reports; | DNA | 2011-11-30 | TOR and Budget still to be prepared. The activity falls under foreseen projects. |  | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
A 2.1.4 | Assistance to the establishment of market intelligence information system/web based platform | No MIIS | An operational MIIS | PSDP M&E Reports; Hits on website | 2010-09-30 | 2011-06-29 | Benchmarking Boccim Web Portal (BWP/1434/01) | Mission for the market intelligence completed in November 2014. Justification has been conducted and approved. The portal is up and running. Site hits reached 2429 visits by 30 June 2015. The portal however is not being used at a frequent rate. | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
[7 empty] | Feasibility study for the market intelligence being done under Value chain analysis for beef, tourism, and horticulture sectors | Web based platform for networking and information dissemination will be established under Result Area 2. The first mission was undertaken in December 2014. Mission report has been submitted and approved. Second mission completed. A project proposal on setting up of the MIIS was presented to BOCCIM and approved on principle. Activity is being paid under ITC budget. Preparation for market consultation dossier underway. 7 companies have been invited to submit profiles. This is likely to start around August or September 2015.
[7 empty] | Assistance to the establishment of market intelligence information | CVs shortlisted for market consultation. Next phase is to launch a market consultation for the implementation of the project proposal.
A 2.2 | Capacity Building of BITC
A 2.2.1 | Assistance to BITC in Export Development and Promotion | No Export Strategy is in place at BITC. The PSDP identified SMMES are not exporting. | One export strategy implemented, 3 partnerships are established with external trading partners outside Botswana’s borders. Ten SMMEs are export ready. | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2011-01-04 | 2011-12-29 | Comments from BITC on the Inception Report received. The expected project outputs are ; (1) Trade portal complementing BITC website. A manual to be produced on the usage of the portal. (2) Training manuals for BITC staff and exporting firms. (3) Networking (database and contacts to be utilized by BITC). Needs assessment phase started on 20 January 2015 and has now been completed. Feedback meeting was held on the 7th of April. The activity is on-going and the consultant is on site. The Interim report has been submitted. The second mission will begin on the 30th of June 2015. Meetings to be held with BITC, the EU and the World Bank on 2nd July 2015 to discuss avoiding overlaps and repetition. |  | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
A 2.2.2 | Assistance to BITC for implementation of its new strategy (sector approach) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; SMME annual reports; BITC annual reports; MTI annual reports | 2011-01-04 | 2011-12-29 | Participation of Ios to trade missions & trainings - (BWP/1307/01) | WTO International Trade & Development course, Geneva, Switzerland. Completed | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
[7 empty] | participation of Ios to trade missions & trainings - (BWP/1307/01) | Support for training on Exports and Investment Promotion Programme –report submitted, Dublin Ireland.
[7 empty] | BITC sector association experts - (BWP/1503/01) | Working with BITC staff to profile 10 companies in the respective sector. Inception report to be submitted. Work began in February 2015 to profile the ICT sector in mining for potential investors. PSDP ICT beneficiaries shared with the sector experts for profiling 5 companies. The activity is on-going.
A 2.3 | Capacity Building of Intermediary Organisations and Sector Associations
A 2.3.1 | Training and coaching of IOs and services providers on SME Diagnosis BNPC, CEDA, LEA, HATAB, BEMA, BIDPA) | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2011-01-04 | 2011-12-29 | 62 local staff from Intermediary Organisation were trained- the activity has been completed and closed. |  | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
A 2.3.2 | Assistance to meat sector – beef, piggery, goat, poultry, etc…: capacity building of farmers and producers associations, PPD meeting, branding of Botswana beef for export | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2011-01-04 | 2011-12-29 | PPD Meeting on Beef Value Chain (BWP/1428/01) | Successfully Completed | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
[7 empty] | Management Tools for Commercial farmers (BWP/1508/01) | he consultant was in Gaborone for his 2nd and final mission from the 22-30 May 2015. An interim report has been submitted by the Consultants and the interim payment is being processed.
[7 empty] | Technical Tools for Graduating communal farmers (BWP/1510/01) | The consultant has submitted his inception report and comments have been submitted to him for consideration. He is also planning for the workshop starting from the 26th June 2015.
[7 empty] | upgrading Capacity of farmers Associations (BWP/1511/01) | The experts were in Gaborone for their first mission from the 23 June to 28 June which covered mainly the needs assessment for the Ghanzi and Ngamiland associations. This is mainly at inception phase and the experts will be continuing with their work.
[7 empty] | SME's Sensitisation on foot and mouth Diseases | TOR and Budget have already been prepared. File number to be requested. The file has been committed and the contract will be sent for a signature from the expert. There is no indication of the dates for when this is to be commenced and completed.
2.3.3 | Assistance to the tourism sector in partnership with BTO and HATAB | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2011-01-04 | 2011-12-29 | Assistance to the tourism sector in partnership with BTO and HATAB | Actions related to this activity have been rolled out and are going as planned. Experts are currently on the ground. | 3 | MODERATELY SATISFACTORY | MS | CDE / BOCCIM Staff – direct system update;
[7 empty] | HATAB Tourism Conference(BWP/1443/01) | Activity completed and file has been de-committed.
A 2.3.4 | Assistance to honey sector associations | DNA | DNA | Contracts awarded and reports tracking the contract; PSDP M&E Reports; TSI and BSDPs annual reports; SMME survey reports; Tourism industry reports | 2011-01-04 | 2011-12-29 | TOR and Budget to be prepared to start April 2015 but as of 30th June 2015, this had not happened yet. |  | 0 | HIGHLY UNSATISFACTORY | HU | CDE / BOCCIM Staff – direct system update;
A 2.4 | Capacity Building for BOBS on Quality and Certification
A 2.4.1 | Support the development of a National Quality Policy | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2011-01-04 | 2011-12-29 | Support the development of a National Quality Policy | Validation of report completed (Work in progress) | 3.5 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
A 2.4.2 | Upgrade the existing capacities of the Botswana Bureau of Standards | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2011-01-04 | 2011-12-29 | Upgrade the existing capacities of the Botswana Bureau of Standards | (work in progress) | 3.5 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
A 2.4.3 | Support the process of certification for SMEs | DNA | DNA | PSDP M&E Reports; BOBS annual reports | 2011-01-04 | 2011-12-29 | Support the process of certification for SMEs | TBT Workshop commenced with beneficiaries and service providers at BOBS (work in progress) | 3.5 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
A 2.5.1 | Technical Advisor in Tourism for HATAB and BTO | DNA | DNA | . | . | . | Technical Advisor in Tourism (BWP/1408/01) | Activity has been completed and closed. The file has been de-committed. | . | . | . | .
[7 empty] | Anthropologist for Tsodilo Hills | Contract has been signed and a follow-up expert mission is expected in the second half of the year. (Work in progress)
A 2.5.2 | Short-term Experts (PSD support Staff) | DNA | DNA | . | . | . | Short-term Experts (PSDP support staff) BWP/1305/01, BWP/1407/01 ,BWP/1311/01, BWP/1442/01 | Support rendered to PSDP Junior experts and interns (work in progress) | . | . | . | .
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 |  | U | 0< U <=1 | HU | HU=0
NA | Not Applicable |  | DNA | Data Not Available |  | .
Note on G3: Author: Pse check the end dates as most of these activities are overdue as shown and would therefore require comments.

## Result Area 3
Result Area Activity Monitoring Report (Summary) :30th June 2015
RESULT AREA 3: | [12 empty] | Score | Rating Code
Business environment (reduction of red tape and pilot on accessing finance) for enterprises is enhanced. | [12 empty] | 4 | S
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity |  |  | Remarks on Significant Achievements |  |  | Score | Rating Code
IND 3.1 | 4 | S | Capacity building conducted on trade and specific negotiation skills • Recommendations submitted by PSDP to MTI on the reduction of; the cost of doing business; and the cost and time required for registration and operationalization of SMMEs in Botswana by June 2015. • Members of the Trade Facilitation and Advisory Group (TFAG) and National Committee on Trade Policy and Negotiations (NCTPN) are trained on MTI Trade Capacity Building Strategy by June 2015. • At least 10 IO staff members are trained in EPA implementation by September 2015 |  |  | A 3.1 | Capacity Building on Trade and Specific Negotiation Skills
[6 empty] | A 3.1.1 | Establish trade facilitation group and provide capacity building (BWP/1314/02) |  |  | Completed and final report submitted |  |  | 4 | S
[6 empty] | A 3.1.2 | Training of TFAG and NTCPN on negotiation and trade facilitation (BWP/1314/02) |  |  | Contract has been awarded for the expert to begin his work. Activity can now be monitored. |  |  | 3.5 | S
[6 empty] | A 3.1.3 | Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation |  |  | Contract has been awarded for the expert to begin his work. Activity can now be monitored. |  |  | 3.5 | S
IND 3.2 | 5 | HS | Improved Policy Framework to access finance • At least 1 new financial product (post loan support mechanism) targeting SMMEs is introduced by commercial banks and or other financial institutions supporting SMME financing by December 2015 • 30 SMME’s under PSDP are assisted to prepare their business plans for submission to commercial banks and other financial institutions by December 2015. • At least 5 PSDP SMMEs assisted are accessing finance by February 2016. • Micro finance policy framework is established and presented to Government for adoption by September 2014. • A microfinance Act is drafted and submitted to government by September 2014. |  |  | A 3.2 | Policy Framework to Improve Access to Finance
[6 empty] | A 3.2.1 | Draft a microfinance policy framework (BWP/1403/01), (BWP/1418/01), (BWP/1415/01) |  |  | Activity completed. Submitted to the Competent Authority in the Government of Botswana |  |  | 5 | HS
[6 empty] | A 3.2.2 | Draft a micro-finance Act for Botswana (BWP/1422/01) |  |  | Legal Expert for Micro Finance Act- Activity pending approval of the framework policy. |  |  | NA | NA
IND 3.3 | 4 | S | Improved Business Environment (Ease of Doing Business) • A compilation of recommendations submitted to MTI by December 2015 to simplify tax registration with a view to improve tax compliance by SMMEs. • A compilation of labour laws affecting SMMEs with recommendations for reforms submitted to MTI by December 2015. |  |  | A 3.3 | Improving Business Environment (Ease of Doing Business)
[6 empty] | A 3.3.1 | Review the registration process and tax compliance |  |  | Contract has been awarded 26 January 2015 to 30 August 2015. Consultants had their first mission between 17-19 March 2015. Having met with key stakeholders, their inception report is expected on 19 April 2015 (Work in Progress). |  |  | 4 | S
[6 empty] | A 3.3.2 | Review of labour laws and recommend labour productivity improvement strategies (BWP/1433/01) |  |  | First mission complete. Activity still awaiting confirmation of dates for the 2nd mission (work in progress). |  |  | 4 | S
. | . | . | . |  |  | . | . |  |  | . |  |  | . | .
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA | NOT APPLICABLE
| Progress or change since last report |  |  | . | .
|  |  | . | . | . | . | . | . | . | . | . | . | . | .
Justification For Activities Graded Highly Satisfactory or Highly Unsatisfactory
S. No | Name of Activity Awarded HS or HU |  |  | Rating | Justification for Extreme Score
1 | A 3.2.1 Draft a microfinance policy framework |  |  | 5 | The draft Policy completed in time and submitted to the relevant authority.
S. No | Name of Activity |  |  | Rating | Alert / Observations, Lessons Learnt and Suggestions for way forward
1 | A 3.1.1. Establish trade facilitation group and provide capacity building. |  |  | 4 | Although the weekly report indicate that the report is completed and final report is submitted, the score should still remain the same due to the fact that there is no indication that the evidence from the report has been accepted by PSDP.
2 | A 3.1.2 Training of TFAG and NTCPN on negotiation and trade facilitation |  |  | 3.5 | There has been some achievement in that the contract has been awarded for the expert to begin his work. Activity can now be monitored.
3 | A 3.1.3 Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation |  |  | 3.5 | There has been some achievement in that the contract has been awarded for the expert to begin his work. Activity can now be monitored.
4 | A 3.2.2. Draft a micro-finance Act for Botswana |  |  | NA | This particular intervention was dropped from the list of activities. This was a decision taken by the MC as it did with the Micro Finance Policy.
6 | A 3.3.2 Review of labour laws and recommend labour productivity improvement strategies. |  |  | 4 | (Work in progress).
Note on F28: Author: This comment is different from what is stated above.
Note on F29: Author: What does this mean?
Note on K12: Author: Who is the competent authority?
Note on K15: Author: Please provide an update

## Result Area 3 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
Result Area 3: Business Environment for enterprises is improved (reduction of red tape and pilot on improved access to finance by SMMEs)
Contributing Activity Number | DESCRIPTION OF ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievements | Score | RATING CODE | RATING | Reporting Responsibility
A 3.1 | Capacity building on Trade and Specific Negotiation Skills
3.1.1 | Establish trade facilitation group and provide capacity building | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Completed and final report submitted | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
3.1.2 | Training of TFAG and NTCPN on negotiation and trade facilitation | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Contract has been awarded for the expert to begin his work. Activity can now be monitored. | 3.5 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
3.1.3 | Capacity building of MTI on trade issues including the Economic Partnership Agreement (EPA) implementation | Status Quo | DNA | Activity Progress Reports | DNA | DNA | Contract has been awarded for the expert to begin his work. Activity can now be monitored. | 3.5 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
A 3.2 | Policy Framework to Improve Access to Finance
3.2.1 | Draft a microfinance policy framework | No Policy | DNA | Activity Progress Reports | DNA | DNA | Activity completed. Submitted to the Competent Authority in the Government of Botswana | 5 | HIGHLY SATISFACTORY | HS | CDE / BOCCIM Staff – direct system update;
3.2.2 | Draft a micro-finance Act for Botswana | No Act | DNA | Activity Progress Reports | DNA | 2015-12-15 | Legal Expert for Micro Finance Act- Activity pending approval of the framework policy | NA | NA | NA | CDE / BOCCIM Staff – direct system update;
A 3.3 | Improving Business Environment (Ease of Doing Business)
3.3.1 | Review the registration process and tax compliance | No Review | DNA | Activity Progress Reports | DNA | 2015-12-30 | Contract has been awarded 26 January 2015 to 30 August 2015. Consultants had their first mission between 17-19 March 2015. Having met with key stakeholders, their inception report is expected on 19 April 2015 (Work in Progress). | 4 | SATISFACTORTY | S | CDE / BOCCIM Staff – direct system update;
3.3.2 | Review of labour laws and recommend labour productivity improvement strategies | DNA | DNA | Activity Progress Reports | DNA | 2015-12-30 | First mission complete. Activity still awaiting confirmation of dates for the 2nd mission (work in progress). | 4 | SATISFACTORY | S | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Applicable |  | DNA | Data Not Available |  | .

## Component 4
Component Activity Monitoring Report Implementation Phase(Summary) : 30th June 2015
Component 4 | [12 empty] | Score | Rating Code
Common Activities Management and Communications | [12 empty] | 5 | HS
Log Frame Indicator Number | Score | Rating Code | Description of Indicator |  |  | Contributing Activity Number | Description of Activity |  |  | Remarks on Significant Achievements |  |  | Score | Rating Code
NA | NA | NA | NA |  |  | A 4.1 | Recruitment of a service provider to develop the Monitoring and evaluation System |  |  | Activity A 4.1 Completed Service Provider in place since June 2014 and M&E Progress Reporting shifted to Result Area 2 A 2.1.1 |  |  | 5 | HS
[6 empty] | A 4.2 | Design and Implementation of a PSDP Communication and Visibility Plan |  |  | Communication and visibility plan approved; PSDP News letter launched; 4 press releases of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced |  |  | 5 | HS
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU =0 | NA | Not Applicable
| Progress or change since last report |  |  | . | .
|  |  | . | . | . | . | . | . | . | . | . | . | .
8 | A 4.1 Recruitment of a service provider to develop the Monitoring and evaluation System. |  |  | 5 | The task has been successfully completed and it is going according to plan.
9 | A 4.2 Communications plan implementation agency in place. |  |  | 5 | The task has been successfully completed and it is going according to plan.
S. No | Name of Activity |  |  | Rating | Alert / Observations, Lessons Learnt and Suggestions for way forward
7 | A 4.1 Recruitment of a service provider to develop the Monitoring and evaluation System. |  |  | 5 | The task has been successfully completed and it is going according to plan.
8 | A 4.2 Communications plan implementation agency in place. |  |  | 5 | The task has been successfully completed and it is going according to plan.

## Component 4 (D)
Monitoring and Evaluation Report for Quarter Ending December 2014
COMPONENT FOUR: PROGRAMME MANAGEMENT AND VISIBILITY
Contributing Activity Number | ACTIVITIES | BASELINE | TARGET | OUTPUT/ SOURCES OF VERIFICATION | Start Date | End Date | Remarks on Significant Achievement | Score | RATING CODE | RATING | Reporting Responsibility
. | .
A 4.1 | Recruitment of a service provider for the design of PSDP Monitoring and Evaluation (M&E) System | No M&E System | Online M&E System operational | Consultants engaged and system developed | 28-05-14 | 31-01-16 | Activity A 4.1 Completed Service Provider in place since June 2014 and M&E Progress Reporting shifted to Result Area 2 A 2.1.1 | 5 | HIGHLY SATISFACTORY | HS | CDE / BOCCIM Staff – direct system update;
A 4.2 | Design and implement PSDP Communication and Visibility Plan | No Communication and Visibility Plan | Effective implementation of the Communication and Visibility Plan | Plan is developed | 14/05/2014 | 14-01-16 | Communication and visibility plan approved; PSDP News letter launched; 4 press releases of major events completed; Radio interview of PSDP team on Gabs FM; 2 Programme Banners produced. | 5 | HIGHLY SATISFACTORY | HS | CDE / BOCCIM Staff – direct system update;
HS | 4< HS <=5 | S | 3< S <=4 | MS | 2< MS <=3 | MU | 1< MU <=2 | U | 0< U <=1 | HU | HU=0
NA | Not Applicable |  | DNA | Data Not Available |  | .